## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF DEULI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09931 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Deuli (Zone-I) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001655/2021-2022 | 614/CSD | 06/08/2021 | 21/08/2021 | INDRANIL DUTTA & ASSOCIATES | 4.64 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF DEULI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09931 | Augmentation | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Deuli (Zone-I) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001657/2021-2022 | 615/CSD | 06/08/2021 | 21/08/2021 | INDRANIL DUTTA & ASSOCIATES | 2.46 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF DEULI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09931 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Deuli (Zone-II) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001659/2021-2022 | 617/CSD | 06/08/2021 | 21/08/2021 | INDRANIL DUTTA & ASSOCIATES | 4.28 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF DEULI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09931 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Deuli (Zone-II) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001662/2021-2022 | 619/CSD | 06/08/2021 | 21/08/2021 | INDRANIL DUTTA & ASSOCIATES | 2.64 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF DEULI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09931 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Deuli (Zone-I) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001658/2021-2022 | 616/CSD | 06/08/2021 | 21/08/2021 | INDRANIL DUTTA & ASSOCIATES | 2.85 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF DEULI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09931 | Augmentation | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Deuli (Zone-II) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001661/2021-2022 | 618/CSD | 06/08/2021 | 21/08/2021 | INDRANIL DUTTA & ASSOCIATES | 2.54 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF DEULI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09931 | Augmentation | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Deuli Water Supply Scheme (Zone-I) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001341/2021-2022 | 6020/AD | 15/02/2022 | 15/02/2023 | MAHAVIR PUMPS MANUFACTURING PVT. LTD | 228.74 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF DEULI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09931 | Augmentation | Sinking of 01 (one) no. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Tube Well No. - 3 at Deuli (Zone - I) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000474/2022-2023 | 5524/AD | 29/09/2022 | 29/10/2022 | SIMPLEX DRILLING CO. | 18.76 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF DEULI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09931 | Augmentation | Laying of pipe line in place of existing damage line at Deuli Water Supply Scheme (Zone-I), Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000589/2022-2023 | 5865/AD | 18/10/2022 | 02/12/2022 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 97.22 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF DEULI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09931 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000062/2022-2023 | 3950/AD | 12/08/2022 | 12/08/2022 | Resource Division | 11.97 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF DEULI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09931 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000073/2022-2023 | 4850/AD | 21/09/2022 | 21/09/2022 | Resource Division | 24.6 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF DEULI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09931 | Augmentation | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Deuli W/S Scheme (Zone-I) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001566/2021-2022 | 6798/AD | 22/03/2022 | 20/07/2022 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 278.33 | 0 | 0 | 72
13 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF DEULI PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09931 | Augmentation | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Deuli W/S Scheme (Zone-II) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000116/2022-2023 | 1661/AD | 10/06/2022 | 08/10/2022 | MAHAVIR PUMPS MANUFACTURING PVT. LTD | 267.47 | 0 | 0 | 71
Total | [13 empty] | 946.5 | 0 | 0