## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF HOMRAPOLTA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09932 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Homrapalta Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001676/2021-2022 | 643/CSD | 11/08/2021 | 26/08/2021 | INDRANIL DUTTA & ASSOCIATES | 4.42 | 3.04 | 68.81 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF HOMRAPOLTA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09932 | Augmentation | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Homrapalta Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001677/2021-2022 | 644/CSD | 11/08/2021 | 26/08/2021 | INDRANIL DUTTA & ASSOCIATES | 2.1 | 2.1 | 100 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF HOMRAPOLTA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09932 | Augmentation | Improvement & Retrofitting of UPVC pipe line (balance part) in distribution system due to damage of pipe line by widening of road by South 24 Pgs. Zilla Parishad at Improvement & Retrofitting of Homrapolta W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000814/2022-2023 | 6809/AD | 16/11/2022 | 16/12/2022 | TANMAY ROY CHOWDHURY | 60.33 | 54.07 | 89.62 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF HOMRAPOLTA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09932 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2022-2023 | 3951/AD | 12/08/2022 | 12/08/2022 | Resource Division | 0.86 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF HOMRAPOLTA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09932 | Augmentation | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Homrapolta Water Supply Scheme Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001458/2021-2022 | 6071/AD | 17/02/2022 | 17/02/2023 | M/S. BLUE BELL ENTERPRISE | 169.37 | 109.22 | 64.49 | 75
6 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF HOMRAPOLTA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09932 | Augmentation | 03 (three) nos. 40 mm dia. 375 mtr. deep Trial Bore by water jet method for Improvement & Retrofitting of Homrapolta and its adjoining Mouza W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer 1 |  | ORD/001382/2022-2023 | 1065/CSD | 15/12/2022 | 24/01/2023 | S.P. CONSTRUCTION (I) | 0.96 | 0.96 | 100 | 90
7 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF HOMRAPOLTA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09932 | Augmentation | Inter connection and rising main with supply of specials at PH-III of Homrapolta W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001080/2023-2024 | 3539/AD | 17/10/2023 | 31/05/2025 | TIYASHA ENTERPRISE | 96.43 | 0 | 0 | 35
Total | [13 empty] | 334.47 | 169.39 | 50.65