## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Nagartala (Zone-I) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001672/2021-2022 | 637/CSD | 10/08/2021 | 25/08/2021 | INDRANIL DUTTA & ASSOCIATES | 3.43 | 3.43 | 100 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Nagartala (Zone-II) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001674/2021-2022 | 639/CSD | 10/08/2021 | 25/08/2021 | INDRANIL DUTTA & ASSOCIATES | 2.67 | 2.67 | 100 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Nagartala (Zone-II) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001675/2021-2022 | 642/CSD | 11/08/2021 | 26/08/2021 | INDRANIL DUTTA & ASSOCIATES | 1.35 | 1.35 | 99.96 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Nagartala (Zone-I) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001670/2021-2022 | 635/CSD | 10/08/2021 | 25/08/2021 | INDRANIL DUTTA & ASSOCIATES | 4.78 | 4.78 | 99.92 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Nagartala (Zone-I) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001671/2021-2022 | 636/CSD | 10/08/2021 | 25/08/2021 | INDRANIL DUTTA & ASSOCIATES | 4.28 | 3.08 | 71.87 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Nagartala (Zone-II) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001673/2021-2022 | 638/CSD | 10/08/2021 | 25/08/2021 | INDRANIL DUTTA & ASSOCIATES | 4.64 | 3.89 | 83.98 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Laying distribution system of Nagartala W/S Scheme (Zone-II) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000010/2022-2023 | 65/AD | 06/04/2022 | 04/08/2022 | DIVINE | 245.35 | 245.1 | 99.9 | 100
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Supply and installation of 20 KVA servo motor operated copper wound line voltage stabilizer at P.H No. 1, Zone-I of Nagartala w/s Scheme under SMD, PHE. Dte. [Block- Canning-II] |  |  | ORD/002504/2022-2023 | ..550/SMD | 10/06/2022 | 10/07/2022 | DIPALI CONSTRUCTION | 2.69 | 2.64 | 98.36 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 3948/AD | 12/08/2022 | 12/08/2022 | Resource Division | 16.35 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Laying of DI Pipeline form OHR to Distribution line of Augmentation Nagartala (Zone- I & II) W/S Scheme, Block-Canning - II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001267/2023-2024 | 1212/CSD | 17/11/2023 | 17/12/2023 | SUKANTA HALDER | 2.44 | 0 | 0 | 98
11 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Nagartala (Zone - II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001678/2022-2023 | 11487/AD | 15/02/2023 | 01/04/2023 | PAL AGENCY | 7.1 | 6.83 | 96.19 | 98
12 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Construction of boundary wall and Land development for Tube Well no 5 Site for Augmentation of Nagartala (Zone-I & II) W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (at Zone-II) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001056/2024-2025 | 4996/AD | 05/12/2024 | 04/01/2025 | MAA SOLAR ENTERPRISE | 10.73 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Construction of boundary wall and Land development for Tube Well no. 3 Site for Augmentation of Nagartala (Zone-I & II) W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (at Zone-II) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001054/2024-2025 | 4995/AD | 05/12/2024 | 02/08/2025 | KUNDU CONSTRUCTION CO. | 11.11 | 0 | 0 | 98
14 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Inter connection & rising main with supply of specials from Head work site to PH - 3, 4 & 5 of Nagartala (Zone I & II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. [Nagartala - Z-II] (SM/09935) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000694/2024-2025 | 4295/AD | 29/10/2024 | 27/04/2025 | RAKHI CONSTRUCTION | 61.46 | 0 | 0 | 98
15 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF NAGARTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09935 | Augmentation | Construction of boundary wall and Land development for Tube Well no 4 Site for Augmentation of Nagartala (Zone-I & II) W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (at Zone-I) (2nd call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000305/2025-2026 | 2958/AD | 25/06/2025 | 25/07/2025 | SUNIL ENTERPRISE | 8.93 | 0 | 0 | 0
Total | [13 empty] | 387.3 | 273.78 | 70.69