## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Dakshin Ramkrishnapur, Zone-II including Operation & Maintenance of scheme for 1 (one) year, Block - Kulpi under Diamond Harbour Sub-Divi | SM/09974 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000101/2022-2023 | 7497/AD | 26/11/2022 | 26/11/2022 | Resource Division | 3.31 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Dakshin Ramkrishnapur, Zone-II including Operation & Maintenance of scheme for 1 (one) year, Block - Kulpi under Diamond Harbour Sub-Divi | SM/09974 | Retrofitting | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. (period from 01/11/2023 to 30/04/2024) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 1 DHSD | ORD/001144/2023-2024 | 556/DHSD | 31/10/2023 | 30/04/2024 | SUMAN HALDER | 2.4 | 2.24 | 93.35 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Dakshin Ramkrishnapur, Zone-II including Operation & Maintenance of scheme for 1 (one) year, Block - Kulpi under Diamond Harbour Sub-Divi | SM/09974 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000123/2022-2023 | 12049/AD | 27/02/2023 | 27/02/2023 | Resource Division | 3.51 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Dakshin Ramkrishnapur, Zone-II including Operation & Maintenance of scheme for 1 (one) year, Block - Kulpi under Diamond Harbour Sub-Divi | SM/09974 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000932/2023-2024 | 1274/AD | 02/03/2024 | 02/03/2024 | Resource Division | 0.62 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Dakshin Ramkrishnapur, Zone-II including Operation & Maintenance of scheme for 1 (one) year, Block - Kulpi under Diamond Harbour Sub-Divi | SM/09974 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000864/2023-2024 | 771/AD | 03/02/2024 | 03/02/2024 | Resource Division | 16.91 | 0 | 0 | 0
Total | [13 empty] | 26.75 | 2.24 | 8.38