## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KAKDWIP & AKSHOYNAGAR PWSS ) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000497/2022-2023 | 313/AD | 13/04/2022 | 28/05/2022 | LEMNISCATE | 12.61 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Kakdwip & Akshaynagar Zone-II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000050/2023-2024 | 36/KSD | 24/04/2023 | 28/04/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Surging of 02 nos. Big dia Tubewell of Kakdwip Akshaynagar Zone-I W/S Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000234/2023-2024 | 164/KSD | 02/06/2023 | 22/06/2023 | S.K.GOLUI | 2.84 | 2.84 | 100 | 95
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Allied works for pile and pile cap portion regarding the construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Kakdwip Akshaynagar (Zone-II), South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000273/2023-2024 | 1423/AD | 13/07/2023 | 27/08/2023 | M/S. JHARNA ENTERPRISE | 41.66 | 41.35 | 99.25 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000264/2023-2024 | 3064/AD | 28/09/2023 | 28/09/2023 | Resource Division | 0.6 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000467/2023-2024 | 4727/AD | 18/12/2023 | 18/12/2023 | Resource Division | 95.8 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Kakdwip & Akshaynagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-C) [No. of FHTC = 1220] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000768/2022-2023 | 6498/AD | 11/11/2022 | 09/02/2023 | A.K. SIKDAR | 109.54 | 78.67 | 71.81 | 80
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Kakdwip & Akshaynagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000503/2022-2023 | 4930/AD | 15/09/2022 | 26/01/2026 | M/S. JHARNA ENTERPRISE | 280.09 | 192.63 | 68.77 | 90
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Construction of Household Tap Platform at different household, fitting fixing supplying specials, etc. for Augmentation of Kakdwip Akshaynagar (Zone- I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-II) (Part-A) (SM/09998) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000303/2024-2025 | 2710/AD | 24/06/2024 | 23/08/2024 | M/S. JHARNA ENTERPRISE | 144.99 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2024 to 31.05.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002843/2023-2024 | 409/KSD | 27/02/2024 | 29/05/2024 | ANANTA KUMAR GIRI | 1.2 | 1.11 | 92.77 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Sinking of 01 no. 100mm x 50mm dia. having 4 nos. Strainer upto 360 mtr (Average) depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying PVC Pipe for providing FHTC at Augmentation of Kakdwip Akshaynagar Zone-II W/S Scheme for implementation of JJM under Kakdwip Sub - Division of Alipore Division, P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002566/2023-2024 | 511/KSD | 15/03/2024 | 25/03/2024 | M/S. R.M. CONSTRUCTION | 2.81 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.06.2024 to 31.08.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000665/2024-2025 | 981/KSD | 27/05/2024 | 27/08/2024 | ANANTA KUMAR GIRI | 1.2 | 1.12 | 93.19 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.09.2023 to 29.02.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002841/2023-2024 | 380/KSD | 17/08/2023 | 17/02/2024 | ANANTA KUMAR GIRI | 2.4 | 2.29 | 95.54 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Making and fixing of permanent display board at headwork site of Mrinalnagar, Koaberia, Hesamabad, Kakdwip, Kakdwip & Akshaynagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002144/2023-2024 | 944/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.94 | 0.31 | 33.32 | 100
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000836/2023-2024 | 681/AD | 30/01/2024 | 30/01/2024 | Resource Division | 58.18 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Kakdwip Akshaynagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Zone - I) (Part-B) [ No. of FHTC = 800] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001110/2022-2023 | 8486/AD | 16/12/2022 | 12/09/2025 | M/S KALPANA CONSTRUCTION | 109.65 | 74.28 | 67.75 | 90
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Laying distribution system for providing FHTC and Construction of Platform to all households for Augmentation of Kakdwip Akshaynagar Zone-II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000200/2024-2025 | 2583/AD | 19/06/2024 | 01/05/2025 | SWASTIK ENTERPRISE (NEW) | 10.04 | 0 | 0 | 100
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Repairing of Pump House with construction of approach road at 1st Tubewell site of Zone-I of Kakdwip Akshaynagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002204/2024-2025 | 2106/KSD | 30/12/2024 | 14/01/2025 | IMAGINEER VENTURES | 3.2 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Repairing of Pump House with construction of approach road at 2nd Tubewell site of Zone-I of Kakdwip Akshaynagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002211/2024-2025 | 2107/KSD | 30/12/2024 | 14/01/2025 | IMAGINEER VENTURES | 3.16 | 0 | 0 | 0
20 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Repairing of Pump House and boundary wall with construction of approach road at 4th Tubewell site of Zone-I of Kakdwip Akshaynagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002212/2024-2025 | 2108/KSD | 30/12/2024 | 14/01/2025 | IMAGINEER VENTURES | 3.09 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Repairing of Pump House and boundary wall with construction of approach road at 1st Tubewell site of Zone-II of Kakdwip Akshaynagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002213/2024-2025 | 2109/KSD | 30/12/2024 | 14/01/2025 | IMAGINEER VENTURES | 3.18 | 0 | 0 | 0
22 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.09.2024 to 30.11.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000666/2024-2025 | 1254/KSD | 28/08/2024 | 27/11/2024 | ANANTA KUMAR GIRI | 1.2 | 1.12 | 93.22 | 0
23 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2025 to 31.05.2025. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/003034/2024-2025 | 349/KSD | 27/02/2025 | 30/05/2025 | ANANTA KUMAR GIRI | 1.2 | 0.75 | 62.48 | 0
24 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.12.2024 to 28.02.2025. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002891/2024-2025 | 1665/KSD | 27/11/2024 | 25/02/2025 | NAMITA PRADHAN | 1.2 | 1.15 | 96.07 | 0
25 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.12.2024 to 28.02.2025. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002846/2024-2025 | 1655/KSD | 26/11/2024 | 24/02/2025 | ANANTA KUMAR GIRI | 1.2 | 1.13 | 94.31 | 0
26 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal after dismantling of dilapidated R.C.C. Elevated Reservoir of Capcaity 700 CuM at Kakdwip Akshaynagar Zone I, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (SM/09998) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000495/2025-2026 | 4426/AD | 09/09/2025 | 14/10/2026 | SARADA CONSTRUCTION | 148.07 | 0 | 0 | 0
27 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2025 to 31.05.0225. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000778/2025-2026 | 968/KSD | 25/11/2025 | 25/02/2026 | NAMITA PRADHAN | 1.21 | 0 | 0 | 0
28 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2025 to 31.05.0225. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/003682/2024-2025 | 353/KSD | 27/02/2025 | 30/05/2025 | NAMITA PRADHAN | 1.21 | 0 | 0 | 0
29 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Kakdwip & Akshaynagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) [No. of FHTC = 1100] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000628/2022-2023 | 5980/AD | 20/10/2022 | 16/01/2025 | M/S B.N.ENTERPRISE | 134.44 | 116.34 | 86.54 | 100
30 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Construction of Household Tap Platform at different household etc. for augmentation of Kakdwip Akshaynagar (Zone-I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) (SM/09998) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000201/2024-2025 | 2584/AD | 19/06/2024 | 04/02/2025 | M/S B.N.ENTERPRISES | 37.98 | 0 | 0 | 100
31 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Construction of Household Tap Platform at different household, fitting fixing supplying of different dia. specials etc. for Augmentation of Kakdwip Akshaynagar (Zone- I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-I) (Part-A) (SM/09998) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000305/2024-2025 | 2688/AD | 24/06/2024 | 30/07/2025 | L.N. ENTERPRISE | 125.1 | 0 | 0 | 40
32 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Repairing of Pump House and boundary wall at 2nd Tubewell site of Zone-II of Kakdwip Akshaynagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002214/2024-2025 | 258/KSD | 31/01/2025 | 15/02/2025 | M/S S.M. CONSTRUCTION | 2.98 | 0 | 0 | 100
33 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAKDWIP & AKSHOYNAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/09998 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Kakdwip & Akshaynagar (Zone- I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone-II) (SM/09998) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000421/2024-2025 | 3072/AD | 25/07/2024 | 16/03/2025 | M/S MODINA ENTERPRISE | 28.94 | 0 | 0 | 100
Total | [13 empty] | 1372.38 | 515.58 | 37.57