## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Kalikatala (Zone-I) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001663/2021-2022 | 620/CSD | 06/08/2021 | 21/08/2021 | INDRANIL DUTTA & ASSOCIATES | 4.28 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Kalikatala (Zone-I) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001665/2021-2022 | 621/CSD | 06/08/2021 | 21/08/2021 | INDRANIL DUTTA & ASSOCIATES | 3.2 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Kalikatala (Zone-II) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001668/2021-2022 | 633/CSD | 10/08/2021 | 25/08/2021 | INDRANIL DUTTA & ASSOCIATES | 3.53 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Kalikatala (Zone-II) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001669/2021-2022 | 634/CSD | 10/08/2021 | 25/08/2021 | INDRANIL DUTTA & ASSOCIATES | 2.35 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Kalikatala (Zone-I) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001666/2021-2022 | 622/CSD | 06/08/2021 | 21/08/2021 | INDRANIL DUTTA & ASSOCIATES | 1.57 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Kalikatala W/S Scheme (Zone-I) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001541/2021-2022 | 6708/AD | 16/03/2022 | 14/07/2022 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 341.37 | 0 | 0 | 86
7 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Route Survey for Providing FHTC at Ground Water Based Kalikatala (Zone-II) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer, Canning sub division |  | ORD/001667/2021-2022 | 632/CSD | 10/08/2021 | 25/08/2021 | INDRANIL DUTTA & ASSOCIATES | 3.92 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000064/2022-2023 | 3952/AD | 12/08/2022 | 12/08/2022 | Resource Division | 180.31 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000084/2022-2023 | 5547/AD | 29/09/2022 | 29/09/2022 | Resource Division | 12.32 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Construction of 500 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Ground Water Based Augmentation Piped Water Supply Scheme of Kalikatala (Zone - I & II) of Canning-II Block under Canning Sub- Division of Alipore Division, PHE Dte. (Zone-II) (SM/10051) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000695/2024-2025 | 4307/AD | 29/10/2024 | 26/07/2025 | AMWOODO ECO PRODUCTS PRIVATE LIMITED | 159.68 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Additional pipeline for FHTC work of Kalikatala W/S Scheme (Zone-II), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001972/2022-2023 | 12591/AD | 13/03/2023 | 27/04/2023 | M/S. S.S. ENTERPRISE | 90.52 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Kalikatala W/S Scheme (Zone-II) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000047/2022-2023 | 600/AD | 28/04/2022 | 08/12/2025 | M/S. S.S. ENTERPRISE | 537.16 | 0 | 0 | 73
13 | SOUTH 24 PARGANAS |  | Alipore Division | IMPROVEMENT & RETROFITTING OF KALIKATALA & ITS ADJOINING MOUZA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10051 | Augmentation | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (2500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalikatala (Zone - I & II) Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub- Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000322/2023-2024 | 1548/AD | 17/07/2023 | 26/11/2025 | M/S. S.S. ENTERPRISE | 177.08 | 0 | 0 | 30
Total | [13 empty] | 1517.31 | 0 | 0