## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | Augmentation | Route Survey for Providing FHTC at Debnibus W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001605/2021-2022 | 600/KSD | 27/09/2021 | 04/10/2021 | LEMNISCATE | 4.38 | 3.23 | 73.87 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DEBNIBAS PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000486/2022-2023 | 300/AD | 12/04/2022 | 27/05/2022 | M/S R.DUTTA & CO. | 8.18 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Debnibas PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002053/2022-2023 | 731/KSD | 14/03/2023 | 18/03/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | Augmentation | Development of Land for sinking of tubewell at 4th tubewell site of Namkhana W/S scheme under JJM, Block : Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000431/2022-2023 | 204/KSD | 01/06/2022 | 08/06/2022 | SIMPLEX DRILLING CO. | 0.87 | 0.85 | 97.47 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2022-2023 | 3903/AD | 12/08/2022 | 12/08/2022 | Resource Division | 145.02 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | Augmentation | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Debnibus Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000767/2022-2023 | 6497/AD | 11/11/2022 | 07/09/2023 | K.P. CONSTRUCTION | 473.08 | 308.92 | 65.3 | 25
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | Augmentation | Construction Platform with laying distribution system for providing FHTC, construction of Rising Main, Road Restoration for Augmentation of Debnibus W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (SM/10092) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000407/2024-2025 | 3190/AD | 31/07/2024 | 14/10/2024 | K.P. CONSTRUCTION | 89.87 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | Augmentation | Allied works for pile and pile cap portion regarding the construction of 350 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Debnibus, South 24 Parganas, Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000274/2023-2024 | 1424/AD | 13/07/2023 | 27/08/2023 | K.P. CONSTRUCTION | 45.78 | 43.44 | 94.88 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | Augmentation | Surging of 2 nos. Tubewell for augmentation of Debnibus W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000538/2023-2024 | 356/KSD | 09/08/2023 | 29/08/2023 | S.K.GOLUI | 2.74 | 2.74 | 100 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | Augmentation | Making and fixing of permanent display board at headwork site of Debnibus, Shibpur, Budhakhali Zone-II (Part- I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002136/2023-2024 | 938/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.63 | 0.16 | 24.95 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | Augmentation | Construction of brick platform, Road Restoration, for Augmentation of Debnibus W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-III) (SM/10092) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000460/2024-2025 | 3419/AD | 21/08/2024 | 05/10/2024 | ANANTA KUMAR GIRI | 45.45 | 37.35 | 82.17 | 60
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000974/2023-2024 | 1767/AD | 27/03/2024 | 27/03/2024 | Resource Division | 1.3 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000801/2023-2024 | 646/AD | 30/01/2024 | 30/01/2024 | Resource Division | 29.38 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Debnibus Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 600] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000773/2022-2023 | 6496/AD | 11/11/2022 | 28/07/2025 | J.K. CONSTRUCTION | 118.07 | 71.57 | 60.62 | 70
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | Augmentation | Repairing of Pump House and Boundary wall at 1st Tube well site of Debnibus W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/10092) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002137/2024-2025 | 1977/KSD | 23/12/2024 | 12/01/2025 | COPE ENTERPRISE | 1.79 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | Augmentation | Repairing of Pump House and Boundary wall at 2nd Tube well site of Debnibus W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/10092) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002138/2024-2025 | 1978/KSD | 23/12/2024 | 12/01/2025 | FORTUNE ENGINEERING | 1.96 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DEBNIBAS PWSS TO ACCOMMODATE FHTC IN NAMKHANA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10092 | Augmentation | Repairing of Pump House and Boundary wall at 3rd Tube well site of Debnibus W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/10092) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002139/2024-2025 | 1979/KSD | 23/12/2024 | 12/01/2025 | FORTUNE ENGINEERING | 1.95 | 0 | 0 | 0
Total | [13 empty] | 970.95 | 468.74 | 48.28