## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAMALPUR RUDRANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10151 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KAMALPUR RUDRANAGAR) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000476/2022-2023 | 296/AD | 12/04/2022 | 27/05/2022 | VOYAGER | 8.2 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAMALPUR RUDRANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10151 | Augmentation | Sanitary arrangement works and painting works for Pump House No. 4 of Kamalpur Rudranagar W/S Scheme, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000493/2021-2022 | 564/KSD | 10/09/2021 | 25/10/2021 | PRADIP KUMAR MONDAL | 1.29 | 1.28 | 99.21 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAMALPUR RUDRANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10151 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000325/2023-2024 | 3140/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAMALPUR RUDRANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10151 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000289/2023-2024 | 3088/AD | 28/09/2023 | 28/09/2023 | Resource Division | 20.14 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KAMALPUR RUDRANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10151 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at Replacement of TW-1, Zone-I, Augmentation of Kamalpur Rudranagar (Phase-B) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -II | Junior Engineer | ORD/000712/2024-2025 | 3420/SMD | 28/10/2024 | 26/01/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 10.85 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KAMALPUR RUDRANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10151 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at Replacement of TW-1, Zone-I, Augmentation of Kamalpur Rudranagar (Phase-B) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -II | Junior Engineer | ORD/000714/2024-2025 | 3420/SMD | 28/10/2024 | 26/01/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 10.85 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAMALPUR RUDRANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10151 | Augmentation | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Kamalpur Rudranagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000369/2022-2023 | 4120/AD | 18/08/2022 | 14/06/2023 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 564.7 | 228.48 | 40.46 | 86
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KAMALPUR RUDRANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10151 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at TW-3, Zone-II, Augmentation of Kamalpur Rudranagar (Phase-B) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -II | Junior Engineer | ORD/000716/2024-2025 | 3422/SMD | 28/10/2024 | 26/01/2025 | AMIT DAS | 11.25 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF KAMALPUR RUDRANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10151 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at TW-3, Zone-I, Augmentation of Kamalpur Rudranagar (Phase-B) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -II | Junior Engineer | ORD/000715/2024-2025 | 3421/SMD | 28/10/2024 | 26/01/2025 | SMILE | 11.29 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAMALPUR RUDRANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10151 | Augmentation | Allied works for pile and pile cap portion regarding the construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Kamalpur Rudranagar (Zone-I), South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000407/2023-2024 | 1780/AD | 26/07/2023 | 09/09/2023 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 47.04 | 31.74 | 67.46 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAMALPUR RUDRANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10151 | Augmentation | inking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Kamalpur Rudranagar W/S Scheme, Block - Sagar under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000419/2023-2024 | 1908/AD | 01/08/2023 | 31/08/2023 | FORTUNE ENGINEERING | 25.2 | 22.17 | 88 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAMALPUR RUDRANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10151 | Augmentation | Allied works for pile and pile cap portion regarding the construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Kamalpur Rudranagar (Zone-II), South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000347/2023-2024 | 1707/AD | 22/07/2023 | 05/09/2023 | UNITED BUILDERS | 49.55 | 47.56 | 95.99 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAMALPUR RUDRANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10151 | Augmentation | Surging of 1 no. Tubewell for augmentation of Kamalpur Rudranagar W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000540/2023-2024 | 358/KSD | 09/08/2023 | 10/10/2023 | S.K.GOLUI | 1.77 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF KAMALPUR RUDRANAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10151 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000533/2023-2024 | 17/AD | 02/01/2024 | 02/01/2024 | Resource Division | 20.14 | 0 | 0 | 0
Total | [13 empty] | 782.57 | 331.23 | 42.33