## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divi | SM/10217 | Augmentation | Hiring of Diesel Maxi Cab for Office of the Assistant Engineer, Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/08/2022 to 31/07/2023. | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle.,Junior Engineer1, Raidghi Sub Division | ORD/000850/2022-2023 | 227/RSD | 29/07/2022 | 29/07/2023 | NITYANANDA MONDAL | 4.8 | 1.63 | 33.86 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divi | SM/10217 | Augmentation | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/11/2022 to 31/12/2022. | Assistant Engineer, Raidighi sub division |  | ORD/001130/2022-2023 | 384/RSD | 28/10/2022 | 28/12/2022 | BAPPA DAS | 0.8 | 0.71 | 88.56 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divi | SM/10217 | Augmentation | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/09/2022 to 31/10/2022. | Assistant Engineer, Raidighi sub division |  | ORD/001129/2022-2023 | 276/RSD | 31/08/2022 | 31/10/2022 | BAPPA DAS | 0.8 | 0.53 | 66.06 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divi | SM/10217 | Augmentation | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/01/2023 to 28/02/2023. | Assistant Engineer, Raidighi sub division |  | ORD/001143/2022-2023 | 679/RSD | 29/12/2022 | 31/12/2022 | BAPPA DAS | 0.8 | 0.7 | 87.59 | 100
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Zone-VII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divi | SM/10217 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-VII of Mega Surface ( Phase-I) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mathurapur-II] | Assistant Engineer | Junior Engineer | ORD/000563/2022-2023 | 579/SMD | 23/02/2023 | 24/05/2023 | BARISAL TRADING CO. | 26.11 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divi | SM/10217 | Augmentation | Hiring of Diesel Maxi Cab for Office of the Assistant Engineer, Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/08/2023 to 31/07/2024. | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle.,Junior Engineer1, Raidghi Sub Division | ORD/002446/2023-2024 | 212/RSD | 28/07/2023 | 28/07/2024 | NITYANANDA MONDAL | 4.8 | 4.67 | 97.31 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divi | SM/10217 | Augmentation | Supply and delivery different dia of C.I.D.F. Sluice valve for different zone of Mathurapur I and II Block of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) of Raidighi Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000113/2023-2024 | 198/AD | 19/04/2023 | 04/05/2023 | SSPR VALVE MANUFACTURING PVT. LTD | 22.66 | 9.01 | 39.78 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divi | SM/10217 | Augmentation | Hiring of Diesel Maxi Cab for official use of Assistant Engineer, Raidighi Sub-Division, PHE Dte. [For 01.11.2024 to 31.01.2025] | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division,Junior Engineer-1, South 24 WS Circle. | ORD/002375/2024-2025 | 768E/RSD | 30/10/2024 | 30/01/2025 | DILIP DHALI | 1.2 | 1.08 | 90.3 | 10
9 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divi | SM/10217 | Augmentation | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01.11.2024 to 31.01.2025] |  | Junior Engineer-1, South 24 WS Circle. | ORD/002473/2024-2025 | 768D/RSD | 30/10/2024 | 30/01/2025 | SANKAR HALDER | 1.2 | 1.15 | 95.91 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divi | SM/10217 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000646/2023-2024 | 256/AD | 15/01/2024 | 15/01/2024 | Resource Division | 47.12 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divi | SM/10217 | Augmentation | Hiring of Diesel Maxi Cab for official use of Assistant Engineer, Raidighi Sub-Division, PHE Dte. [For 01.02.2025 to 30.04.2025] | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002914/2024-2025 | 1032/RSD | 30/01/2025 | 30/04/2025 | DILIP DHALI | 1.2 | 1.1 | 91.79 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divi | SM/10217 | Augmentation | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01.02.2024 to 30.04.2025] | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002916/2024-2025 | 1033/RSD | 30/01/2025 | 30/04/2025 | SANKAR HALDER | 1.2 | 1.17 | 97.16 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divi | SM/10217 | Augmentation | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01.05.2024 to 31.07.2025] | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000447/2025-2026 | 73/RSD | 30/04/2025 | 31/07/2025 | SANKAR HALDER | 1.2 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divi | SM/10217 | Augmentation | Hiring of Diesel Maxi Cab for official use of Assistant Engineer, Raidighi Sub-Division, PHE Dte. [For 01.05.2025 to 31.07.2025] | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000446/2025-2026 | 72/RSD | 30/04/2025 | 31/07/2025 | DILIP DHALI | 1.2 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VII, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divi | SM/10217 | Augmentation | Laying distribution system of piped water supply scheme, Construction of boundary wall with approached road and construction of Pump House No. 1 & 2 at Zone- VII A (Barodanagar) of Mathurapur-II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/10217 & SM/18377) | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001698/2026-2027 | 3838/AD | 07/08/2026 | 05/11/2026 | MATRI ENTERPRISE | 351.02 | 0 | 0 | 0
Total | [13 empty] | 466.11 | 21.75 | 4.67