## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System of Zone-I, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/10218 | Augmentation | Extension of distribution system (Node no. AB-CD) of Ghatbakultala W/S scheme at Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000043/2022-2023 | 35/RSD | 19/04/2022 | 18/06/2022 | R.G. ENTERPRISE (I) | 4.77 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System of Zone-I, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/10218 | Augmentation | Remodeling of distribution system (Node No. 16-15-13-14, 16-17-18-19-20-21, 15-23-22-24) at Zone-XIII of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000108/2022-2023 | 05/RSD | 04/04/2022 | 03/06/2022 | KAKALI ENTERPRISE | 4.79 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System of Zone-I, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/10218 | Augmentation | Bamboo pilling walling at Zone-X of Mathurapur - I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (Node point -255 - 255A, 255-255E, 255-255D, 255-255C) | Assistant Engineer, Raidighi sub division |  | ORD/000267/2022-2023 | 103/RSD | 13/06/2022 | 12/08/2022 | SUPRITI ENTERPRISE | 4.65 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System of Zone-I, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/10218 | Augmentation | Special repairing work of pipeline and allied works to mitigate water supply problem at Rajapur & adjacent area Uttar Durgapur water supply scheme ( Zone-I of Mathurapur-I Block) under Mega surface water based water supply scheme-Falta Mathurapur, Dist. ¿ South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000634/2022-2023 | 95/RSD | 07/06/2022 | 07/07/2022 | R.G. ENTERPRISE (I) | 4.75 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System of Zone-I, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/10218 | Augmentation | Dismantling and restoration of concrete village road for laying pipe line work at Zone-I (Nodal point 354-356-357-359-361-363-367) of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001133/2022-2023 | 598/RSD | 23/12/2022 | 22/01/2023 | RAIS ALI MOLLA | 1.82 | 0 | 0 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System of Zone-I, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/10218 | Augmentation | Construction of culvert at Zone-I of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega surface water based water supply scheme-Falta Mathurapur, Dist. South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001804/2022-2023 | 934/RSD | 10/03/2023 | 09/04/2023 | SUKUMAR HALDAR | 1.07 | 0 | 0 | 99
7 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System of Zone-I, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/10218 | Augmentation | Supply and delivery different dia of C.I.D.F. Sluice valve for different zone of Mathurapur I and II Block of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) of Raidighi Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000113/2023-2024 | 198/AD | 19/04/2023 | 04/05/2023 | SSPR VALVE MANUFACTURING PVT. LTD | 22.66 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System of Zone-I, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/10218 | Augmentation | Construction of thrust block for D.I. pipe line at Zone - I, Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000426/2022-2023 | 282/RSD | 01/09/2022 | 31/10/2022 | M/S KUNDU CONSTRUCTION | 0.81 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System of Zone-I, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/10218 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000637/2023-2024 | 241/AD | 15/01/2024 | 15/01/2024 | Resource Division | 52.95 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Distribution System of Zone-I, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/10218 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-I of Mega Surface (Phase-I) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mathurapur-I] | Assistant Engineer | Junior Engineer | ORD/000559/2022-2023 | 573/SMD | 22/02/2023 | 30/06/2025 | DEBJYOTI BASU | 13.13 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Distribution System of Zone-I, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Math | SM/10218 | Augmentation | Construction of 1500 cum capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system and other allied works at Zone- I of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division,Junior Engineer-1, South 24 WS Circle. | ORD/000576/2023-2024 | 2262/AD | 14/08/2023 | 05/04/2025 | M/S. S.S. ENTERPRISE | 1185.63 | 0 | 0 | 10
Total | [13 empty] | 1297.03 | 0 | 0