## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Route Survey for Providing FHTC at Ganeshpur Kalinagar (Zone-I) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001018/2021-2022 | 536/KSD | 01/09/2021 | 21/09/2021 | LEMNISCATE | 2.82 | 2.22 | 78.5 | 100
2 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Route Survey for Providing FHTC at Ganeshpur Kalinagar (Zone-II) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001023/2021-2022 | 537/KSD | 01/11/2021 | 21/11/2021 | INDRANIL DUTTA & ASSOCIATES | 4.6 | 4.56 | 99.08 | 100
3 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Route Survey for Providing FHTC at Ganeshpur Kalinagar (Zone-II) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001616/2021-2022 | 615/KSD | 27/09/2021 | 04/10/2021 | INDRANIL DUTTA & ASSOCIATES | 2.62 | 1.96 | 74.86 | 100
4 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Route Survey for Providing FHTC at Gangasagar Zone - I & Gangasagar Zone - II W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001617/2021-2022 | 616/KSD | 27/09/2021 | 04/10/2021 | INDRANIL DUTTA & ASSOCIATES | 1.27 | 1.01 | 80 | 100
5 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Rathtala, Bangheri and others (Phase-III) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000152/2021-2022 | 404/KSD | 07/07/2021 | 22/07/2021 | M/S. MANIMALA ENTERPRISE | 4.77 | 4.24 | 88.9 | 100
6 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gheri Uttar, Dakshin and others (Phase-III) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000137/2021-2022 | 392/KSD | 07/07/2021 | 22/07/2021 | UNIQUE CONSTRUCTION (II) | 4.39 | 3.96 | 90.09 | 100
7 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( GANESHPUR KALINAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000490/2022-2023 | 303/AD | 12/04/2022 | 27/05/2022 | LEMNISCATE | 12.79 | 12.79 | 100 | 100
8 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-III) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001916/2020-2021 | 1326/KSD | 23/02/2021 | 05/03/2021 | FIDERE MARINE SERVICES PVT. LTD. | 4.74 | 4.39 | 92.69 | 100
9 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia (Phase-IV) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001905/2020-2021 | 1321/KSD | 23/02/2021 | 05/03/2021 | KHOKAN MONDAL | 4.3 | 4.28 | 99.54 | 100
10 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia (Phase-III) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001896/2020-2021 | 1318/KSD | 23/02/2021 | 05/03/2021 | KHOKAN MONDAL | 4.74 | 4.71 | 99.5 | 100
11 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bangheri (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001782/2020-2021 | 1227/KSD | 23/02/2021 | 05/03/2021 | M/S. MANIMALA ENTERPRISE | 4.26 | 4.23 | 99.08 | 100
12 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia and others for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000138/2021-2022 | 393/KSD | 07/07/2021 | 22/07/2021 | KHOKAN MONDAL | 4.39 | 3.97 | 90.45 | 100
13 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Rathtala, Bangheri and others (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000150/2021-2022 | 402/KSD | 07/07/2021 | 22/07/2021 | M/S. MANIMALA ENTERPRISE | 4.78 | 4.42 | 92.55 | 100
14 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Rathtala, Bangheri and others (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000132/2021-2022 | 387/KSD | 07/07/2021 | 22/07/2021 | M/S. MANIMALA ENTERPRISE | 4.78 | 4.41 | 92.21 | 100
15 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-IV) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001891/2020-2021 | 1313/KSD | 23/02/2021 | 05/03/2021 | M/S. SUNITY ENTERPRISE | 4.7 | 4.49 | 95.49 | 100
16 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia (Phase-V) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001914/2020-2021 | 1324/KSD | 23/02/2021 | 05/03/2021 | KHOKAN MONDAL | 4.61 | 4.58 | 99.5 | 100
17 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bangheri (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001854/2020-2021 | 1285/KSD | 23/02/2021 | 05/03/2021 | M/S. MANIMALA ENTERPRISE | 4.38 | 3.2 | 73 | 100
18 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia and others for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000129/2021-2022 | 384/KSD | 07/07/2021 | 22/07/2021 | KHOKAN MONDAL | 4.39 | 4.12 | 93.85 | 100
19 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-VI) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001893/2020-2021 | 1315/KSD | 23/02/2021 | 05/03/2021 | M/S. SUNITY ENTERPRISE | 2.91 | 2.8 | 96.19 | 100
20 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Ganeshpur Kalinagar Zone - I PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division | ORD/000046/2023-2024 | 31/KSD | 24/04/2023 | 28/04/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 0
21 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Ganeshpur Kalinagar Zone - II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division | ORD/000047/2023-2024 | 32/KSD | 24/04/2023 | 28/04/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 0
22 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Ganeshpur Kalinagar (Zone-I) W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001040/2021-2022 | 2271/AD | 06/09/2021 | 13/09/2021 | INDRANIL DUTTA & ASSOCIATES | 2.58 | 0 | 0 | 0
23 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Carriage of Chlorine from Ganeshpur store to different Pump house of different PWSS of Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001733/2021-2022 | 1006/KSD | 21/02/2022 | 21/02/2023 | SARADA CONSTRUCTION | 1.46 | 0 | 0 | 80
24 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - I) (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000420/2022-2023 | 4346/AD | 25/08/2022 | 24/10/2022 | G.M. ENTERPRISE | 41.23 | 17.9 | 43.42 | 20
25 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Ganeshpur Kalinagar (Zone-II) W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001041/2021-2022 | 2272/AD | 06/09/2021 | 13/09/2021 | LEMNISCATE | 4.45 | 0 | 0 | 0
26 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Laying distribution system for providing FHTC for Augmentation of Ganeshpur Kalinagar Zone-I W/S Scheme under JJM under Kakdwip Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/000635/2023-2024 | 2463/AD | 24/08/2023 | 08/10/2023 | M/S. BRINDABAN DAS & SONS | 8.5 | 0 | 0 | 0
27 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Surging of 02 nos. Big dia Tubewell of Ganeshpur Kalinagar Zone-II W/S Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000233/2023-2024 | 162/KSD | 01/06/2023 | 21/06/2023 | S.K.GOLUI | 2.74 | 2.74 | 100 | 95
28 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Road Restoration for Laying distribution system of Augmentation of Ganeshpur Kalinagar Water Supply Scheme for providing FHTC, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone - II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000986/2023-2024 | 3005/AD | 26/09/2023 | 25/11/2023 | STAR ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 76.51 | 0 | 0 | 0
29 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Deployment of Clerical Staff on contract basis under Agency for the office of The Assistant Engineer, Kakdwip Sub-Division under Alipore Division P.H.E. Directorate. (For the period from 01.06.2023 to 31.05.2024) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001173/2023-2024 | 133/KSD | 26/05/2023 | 25/05/2024 | M. MUKHERJEE | 2.09 | 0 | 0 | 0
30 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000055/2022-2023 | 3905/AD | 12/08/2022 |  | Resource Division | 147.3 | 0 | 0 | 0
31 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000090/2022-2023 | 5594/AD | 29/09/2022 |  | Resource Division | 14.31 | 0 | 0 | 0
32 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Rathtala, Bangheri and others (Phase-IV) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000153/2021-2022 | 406/KSD | 07/07/2021 | 22/07/2021 | TAPAN DAS | 4.77 | 1.18 | 24.64 | 95
33 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Construction of 1 no. 550 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) (Part-A) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/000554/2022-2023 | 5728/AD | 13/10/2022 | 09/08/2023 | GARGO TRADERS | 320.99 | 14.42 | 4.49 | 25
34 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Construction of 1 no. 550 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - I) (Part-A) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/000525/2022-2023 | 5607/AD | 29/09/2022 | 26/07/2023 | ASHIT BARAN BOSE | 291.65 | 76.44 | 26.21 | 65
35 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) (Part-C) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/000424/2022-2023 | 4347/AD | 25/08/2022 | 24/09/2022 | ASHIS ENTERPRISE | 16.81 | 13.28 | 78.99 | 90
36 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) (Part-D) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/000433/2022-2023 | 4348/AD | 25/08/2022 | 24/09/2022 | UNIQUE CONSTRUCTION (II) | 16.37 | 7.62 | 46.54 | 75
37 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction of 01 no. Pump House for Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) [No. of FHTC = 500] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000670/2022-2023 | 6155/AD. | 01/11/2022 | 30/01/2023 | STAR ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 168.21 | 27.81 | 16.53 | 50
38 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2024 to 31.05.2024 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002536/2023-2024 | 408/KSD | 27/02/2024 | 29/05/2024 | ANAMIKA BERA | 1.2 | 0 | 0 | 0
39 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Material Requisition To Resource Division |  |  | RTOR001001/2023-2024 | 1800/AD | 27/03/2024 |  | Resource Division | 18.82 | 0 | 0 | 0
40 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Making and fixing of permanent display board at headwork site of Hardwood Point, Ganeshpur Kalinagar Zone - I & II, Kashinagar, Srinagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002145/2023-2024 | 945/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.94 | 0 | 0 | 100
41 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - I) (Part-D) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/000382/2023-2024 | 1775/AD | 26/07/2023 | 09/09/2023 | SWASTIK CONSTRUCTION | 14.02 | 6.12 | 43.62 | 100
42 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction of 01 no. Pump House for Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) [No. of FHTC = 700] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000669/2022-2023 | 6154/AD. | 01/11/2022 | 30/01/2023 | S.S. ENTERPRISE (I) | 134.59 | 37.65 | 27.97 | 55
43 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Allied works for pile and pile cap portion regarding the construction of 600 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Ganeshpur Kalinagar (Zone-I), South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000271/2023-2024 | 1421/AD | 13/07/2023 | 27/08/2023 | ASHIT BARAN BOSE | 61.55 | 30.35 | 49.3 | 100
44 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Augmentation of Ganeshpur Kalinagar Zone- I & II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-II) (SM/10336) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000203/2024-2025 | 2586/AD | 19/06/2024 | 03/08/2024 | GARGO TRADERS | 46.46 | 0 | 0 | 0
45 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. At Head Work Site for Augmentation of Ganeshpur Kalinagar Zone-I & II Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (SM/10336) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000202/2024-2025 | 2585/AD | 19/06/2024 | 03/08/2024 | SOHINI ENTERPRISE | 5.6 | 0 | 0 | 0
46 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe and Pre-packed Resin Bonded Gravel Filter for Augmentation of Ganeshpur Kalinagar (Zone-I and II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division | ORD/000119/2024-2025 | 2396AD | 07/06/2024 | 22/07/2024 | FORTUNE ENGINEERING | 39.72 | 0 | 0 | 0
47 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Allied works for pile and pile cap portion regarding the construction of 600 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Ganeshpur Kalinagar (Zone-II), South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000272/2023-2024 | 1422/AD | 13/07/2023 | 27/08/2023 | GARGO TRADERS | 65.44 | 0 | 0 | 100
48 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Augmentation of Ganeshpur Kalinagar Zone- I & II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-I) (SM/10336) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000335/2024-2025 | 2750/AD | 27/06/2024 | 26/08/2024 | SUDIP PRADHAN | 111.95 | 0 | 0 | 0
49 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Ganeshpur Kalinagar Zone- I & II W/S Scheme, Block - Kakdwip under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/10336) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division | ORD/000164/2024-2025 | 2515/AD | 15/06/2024 | 15/07/2024 | SHREE J M CONSTRUCTION | 20.39 | 0 | 0 | 100
50 | SOUTH 24 PARAGANAS |  | Alipore Division | AUGMENTATION OF GANESHPUR KALINAGAR PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) | SM/10336 | Augmentation | Carriage of Chlorine from Ganeshpur store to different Pump house of different PWSS of Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002187/2022-2023 | 689/KSD | 23/02/2023 | 23/02/2024 | SARADA CONSTRUCTION | 1.54 | 0 | 0 | 100
Total | [13 empty] | 1729.4 | 316.82 | 18.32