## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HERAMBAGOPALPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | SM/10480 | Augmentation | Route Survey for Providing FHTC at Herambagopalpur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001076/2021-2022 | 546/KSD | 03/09/2021 | 23/09/2021 | LEMNISCATE | 4.6 | 4.58 | 99.54 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HERAMBAGOPALPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | SM/10480 | Augmentation | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for implementing of JAL SWAPNA (JJM) at 3rd Tubewell site of Herambagopalpur Water Supply Scheme (Augmentation), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000027/2022-2023 | 411/AD | 20/04/2022 | 20/05/2022 | AQUATECH ENGINEER | 18.32 | 15.63 | 85.34 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HERAMBAGOPALPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | SM/10480 | Augmentation | Route Survey for Providing FHTC at Herambagopalpur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001606/2021-2022 | 604/KSD | 27/09/2021 | 04/10/2021 | LEMNISCATE | 1.56 | 1.48 | 95 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HERAMBAGOPALPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | SM/10480 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Herambogopalpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000458/2022-2023 | 293/AD | 12/04/2022 | 27/05/2022 | INDRANIL DUTTA & ASSOCIATES | 6.27 | 6.27 | 100 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HERAMBAGOPALPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | SM/10480 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Herambagopalpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division | ORD/000066/2023-2024 | 47/KSD | 28/04/2023 | 02/05/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HERAMBAGOPALPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | SM/10480 | Augmentation | Route Survey for Providing FHTC at Laxmi Janardanpur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001080/2021-2022 | 558/KSD | 08/09/2021 | 28/09/2021 | LEMNISCATE | 4.24 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HERAMBAGOPALPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | SM/10480 | Augmentation | Construction of 1 (one) no. Pump House (5.40m x 3.60m) including sanitary arrangement as per departmental drawing for implementing of JAL SWAPNA (JJM) at 3rd Tubewell site of Herambagopalpur Water Supply Scheme (Augmentation), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000018/2022-2023 | 213/AD | 11/04/2022 | 11/05/2022 | M/S BABUSONA ENTERPRISE | 5.15 | 5.08 | 98.65 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HERAMBAGOPALPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | SM/10480 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2022-2023 | 3908/AD | 12/08/2022 | 12/08/2022 | Resource Division | 19.42 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HERAMBAGOPALPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | SM/10480 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000312/2023-2024 | 3121/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HERAMBAGOPALPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | SM/10480 | Augmentation | Surging of 2 nos. Tubewell for augmentation of Herambagopalpur W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000504/2023-2024 | 349/KSD | 09/08/2023 | 29/08/2023 | S.K.GOLUI | 2.73 | 2.73 | 100 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HERAMBAGOPALPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | SM/10480 | Augmentation | Surging of 6 nos. Tubewell for Augmentation of Hesamabad- 2 nos., Block- Kakdwip, Herambagopalpur- 2 nos., Gurdaspur- 2 nos. W/S Scheme, Block - Pathar Pratima under JJM under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/000503/2024-2025 | 3606/AD | 06/09/2024 | 06/10/2024 | COPE ENTERPRISE | 8.23 | 2.74 | 33.33 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HERAMBAGOPALPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | SM/10480 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000940/2023-2024 | 1674/AD | 22/03/2024 | 22/03/2024 | Resource Division | 7.49 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HERAMBAGOPALPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | SM/10480 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000571/2023-2024 | 76/AD | 03/01/2024 | 03/01/2024 | Resource Division | 21.58 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HERAMBAGOPALPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | SM/10480 | Augmentation | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for 1 year after completion of FHTC works for Augmentation of Herambagopalpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000551/2022-2023 | 5725/AD. | 13/10/2022 | 01/04/2025 | GARGO TRADERS | 706.06 | 532.53 | 75.42 | 36
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED HERAMBAGOPALPUR PWSS TO ACCOMMODATE FHTC IN PATHARPRATIMA BLOCK UNDER KAKDWIP SUB-DIVISION OF ALIPORE DIVISION, PHE DTE IN SOUTH 24 PARGANAS DISTRCT | SM/10480 | Augmentation | Allied works for pile and pile cap portion regarding the construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Herambagopalpur W/S Scheme, South 24 Parganas, Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000276/2023-2024 | 1426/AD | 13/07/2023 | 01/03/2025 | GARGO TRADERS | 42.5 | 34.54 | 81.28 | 70
Total | [13 empty] | 848.92 | 606.07 | 71.39