## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN SHIBGANJ PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10482 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Dakshin Shibganj PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000457/2022-2023 | 298/AD | 12/04/2022 | 27/05/2022 | INDRANIL DUTTA & ASSOCIATES | 3.29 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN SHIBGANJ PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10482 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2022-2023 | 3913/AD | 12/08/2022 | 12/08/2022 | Resource Division | 72.71 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN SHIBGANJ PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10482 | Augmentation | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of foundation after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Augmentation of Dakshin Shibganj Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000789/2023-2024 | 2785/AD | 12/09/2023 | 08/07/2024 | TRIPTI ENTERPRISE | 191.9 | 39.69 | 20.68 | 30
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN SHIBGANJ PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10482 | Augmentation | Carriage of Chlorine from Ganeshpur store to different Pump house of different PWSS of Patharpratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002185/2022-2023 | 691/KSD | 23/02/2023 | 23/02/2024 | M/S B. ENTERPRISE | 1.05 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN SHIBGANJ PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10482 | Augmentation | Surging of 02 nos. Big dia Tubewell of Dakshin Shibganj W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000230/2023-2024 | 156/KSD | 01/06/2023 | 26/06/2023 | S.K.GOLUI | 3.36 | 3.36 | 100 | 99
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN SHIBGANJ PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10482 | Augmentation | Making and fixing of permanent display board at headwork site of Paschim Surendranagar Zone-I (Part - I, II & III), Madhabnagar Zone - I, Madhabnagar Zone - II, Dakshin Shibganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002098/2023-2024 | 924/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.95 | 0.16 | 16.66 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN SHIBGANJ PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10482 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000310/2023-2024 | 3119/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN SHIBGANJ PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10482 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Dakshin Shibganj W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/10482) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000418/2024-2025 | 3069/AD | 25/07/2024 | 13/08/2026 | M/S B. ENTERPRISE | 28.74 | 0 | 0 | 60
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN SHIBGANJ PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10482 | Augmentation | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc for Augmentation of Dakshin Shibganj W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/10482) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000380/2024-2025 | 3056/AD | 25/07/2024 | 23/09/2024 | TRIPTI ENTERPRISE | 171.55 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN SHIBGANJ PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10482 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dakshin Shibganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002607/2023-2024 | 293/KSD | 07/02/2024 | 12/02/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED DAKSHIN SHIBGANJ PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/10482 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000774/2023-2024 | 608/AD | 29/01/2024 | 29/01/2024 | Resource Division | 11.08 | 0 | 0 | 0
Total | [13 empty] | 485.41 | 43.7 | 9