## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore | SM/10520 | Augmentation | Land Development at head work site of Zone-VI, Mathurapur-II block under 'Mega surface water based water supply scheme-Falta Mathurapur under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000440/2022-2023 | 4354/AD | 25/08/2022 | 24/09/2022 | TARUN KUMAR BHATTACHARYA, PROP.- AVINABA BHATTACHARYA | 23.26 | 17.02 | 73.19 | 75
2 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore | SM/10520 | Augmentation | Construction of service road for head work site of Zone-VI, Mathurapur-II block under Mega surface water based water supply scheme-FaltaMathurapur under Raidighi Sub-Division of AliporeDivision,P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001136/2022-2023 | 601/RSD | 23/12/2022 | 22/01/2023 | M/S M.B.ENTERPRISE | 4.7 | 0 | 0 | 20
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Zone-VI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore | SM/10520 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-VI of Mega Surface ( Phase-I) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mathurapur-II] | Assistant Engineer | Junior Engineer | ORD/000565/2022-2023 | 581/SMD | 23/02/2023 | 24/05/2023 | M.S.ENTERPRISE | 26.7 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore | SM/10520 | Augmentation | Providing FHTC at Zone- VI of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (New FHTC =4922 nos) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000121/2023-2024 | 592/AD | 15/05/2023 | 13/08/2023 | M/S. JHARNA ENTERPRISE | 272.12 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore | SM/10520 | Augmentation | Supply and delivery different dia of C.I.D.F. Sluice valve for different zone of Mathurapur I and II Block of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) of Raidighi Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000113/2023-2024 | 198/AD | 19/04/2023 | 04/05/2023 | SSPR VALVE MANUFACTURING PVT. LTD | 22.66 | 9.01 | 39.78 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-VI, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore | SM/10520 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 3587/AD | 29/07/2022 | 29/07/2022 | Resource Division | 700.28 | 0 | 0 | 0
Total | [13 empty] | 1049.71 | 26.04 | 2.48