## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-XV, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divisi | SM/10532 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000242/2023-2024 | 2913/AD | 20/09/2023 | 20/09/2023 | Resource Division | 1.38 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Zone-XV, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divisi | SM/10532 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/02638/2023-2024 | BP-2023-24-279 | 03/10/2023 | 03/10/2023 | WBSEDCL | 3.06 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-XV, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divisi | SM/10532 | Augmentation | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-XV, Mathurapur-I in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (New FHTC = 718 Nos.) [Part - B] | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000112/2023-2024 | 38/AD | 05/04/2023 | 20/05/2023 | BANERJEE ENTERPRISE | 44.3 | 11.51 | 25.99 | 10
4 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-XV, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divisi | SM/10532 | Augmentation | Laying distribution system of piped water supply at Zone- XV of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000111/2023-2024 | 37/AD | 05/04/2023 | 04/06/2023 | M/S. JHARNA ENTERPRISE | 93.18 | 74.53 | 79.98 | 80
5 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-XV, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divisi | SM/10532 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000638/2023-2024 | 242/AD | 15/01/2024 | 15/01/2024 | Resource Division | 4.42 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Zone-XV, Mathurapur-I Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore Divisi | SM/10532 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 & 2 for Augmentation of Zone-XV water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block:Mathgurapur-I] (Phase-I) (SM/10532) | Assistant Engineer | Junior Engineer | ORD/000063/2025-2026 | 1439/SMD | 21/05/2025 | 03/10/2025 | S.P. CONSTRUCTION | 24.8 | 0 | 0 | 0
Total | [13 empty] | 171.14 | 86.04 | 50.28