## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Zone-XIV, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore | SM/10534 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-XIV of Mega Surface ( Phase-I) water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Mathurapur-II] | Assistant Engineer | Junior Engineer | ORD/000564/2022-2023 | 580/SMD | 23/02/2023 | 24/05/2023 | M.S.ENTERPRISE | 26.7 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-XIV, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore | SM/10534 | Augmentation | Hydraulic testing and disinfection of laying distribution system including excavation of trial pit of piped water supply at Zone- XIV of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000996/2023-2024 | 293/RSD | 29/09/2023 | 28/11/2023 | M/S. GANGA ENTERPRISE | 2.44 | 2.39 | 97.69 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-XIV, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore | SM/10534 | Augmentation | Protection work for pipe lines at Radhakantapur Abad W/S Scheme (Node point 4-5, 3-4, 6-7, 150-151, 154-155, 73-74, 79-80), modified as Zone- XIV of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001906/2023-2024 | 435/RSD | 08/01/2024 | 08/03/2024 | M/S. M.M. ENTERPRISE | 4.71 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-XIV, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore | SM/10534 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000655/2023-2024 | 259/AD | 15/01/2024 | 15/01/2024 | Resource Division | 10.9 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Zone-XIV, Mathurapur-II Block for Providing Functional Household Tap Connection (FHTC) to all the households in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, under Alipore | SM/10534 | Augmentation | Laying distribution system of piped water supply at Zone- XIV of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/10534 & SM/15506) | Assistant Engineer, Raidighi sub division | Junior Engineer-1, South 24 WS Circle. | ORD/001930/2024-2025 | 109/AD | 08/01/2025 | 09/03/2025 | A.K. INDUSTRIES | 179.67 | 0 | 0 | 0
Total | [13 empty] | 224.42 | 2.39 | 1.06