## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF MANDIRTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10783 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (MANDIRTALA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000477/2022-2023 | 31/AD | 04/04/2022 | 19/05/2022 | VOYAGER | 7.71 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF MANDIRTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10783 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories for Augmentation of Mandirtala water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I | Junior Engineer | ORD/000568/2022-2023 | 587/SMD | 24/02/2023 | 25/05/2023 | M/S. S.S. ENTERPRISE | 60.45 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF MANDIRTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10783 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Mandirtala PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000077/2023-2024 | 61/KSD | 02/05/2023 | 06/05/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF MANDIRTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10783 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000094/2022-2023 | 5588/AD | 29/09/2022 | 29/09/2022 | Resource Division | 14.31 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF MANDIRTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10783 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2022-2023 | 3902/AD | 12/08/2022 | 12/08/2022 | Resource Division | 148.87 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF MANDIRTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10783 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000283/2023-2024 | 3058/AD | 28/09/2023 | 28/09/2023 | Resource Division | 110.39 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF MANDIRTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10783 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000323/2023-2024 | 3138/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF MANDIRTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10783 | Augmentation | Construction of 600 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Mandirtala Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000781/2022-2023 | 6535/AD | 11/11/2022 | 07/09/2023 | SUPRITI ENTERPRISE | 821.1 | 637.03 | 77.58 | 78
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF MANDIRTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10783 | Augmentation | Surging of 01 no. Tubewell for augmentation of Mandirtala W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000524/2023-2024 | 351/KSD | 09/08/2023 | 29/08/2023 | S.K.GOLUI | 1.77 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF MANDIRTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10783 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000683/2023-2024 | 453/AD | 24/01/2024 | 24/01/2024 | Resource Division | 1.44 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF MANDIRTALA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) [PHASE - B] | SM/10783 | Augmentation | Allied works for pile and pile cap portion regarding the construction of 600 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Mandirtala (Zone-I & II) W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000278/2023-2024 | 1428/AD | 13/07/2023 | 03/04/2025 | SUPRITI ENTERPRISE | 80.97 | 0 | 0 | 86
Total | [13 empty] | 1247.8 | 637.51 | 51.09