## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Route Survey for Providing FHTC at Ramganga W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001077/2021-2022 | 547/KSD | 03/09/2021 | 23/09/2021 | ROY CHOWDHURY ASSOCIATES | 4.6 | 4.59 | 99.92 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Ramganga PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000461/2022-2023 | 295/AD | 12/04/2022 | 27/05/2022 | INDRANIL DUTTA & ASSOCIATES | 7.33 | 7.33 | 100 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for implementing of JAL SWAPNA (JJM) at 3rd Tubewell site of Ramganga Water Supply Scheme (Augmentation), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000026/2022-2023 | 2926/AD | 07/07/2022 | 06/08/2022 | AQUATECH ENGINEER | 18.32 | 17.38 | 94.9 | 98
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2022-2023 | 3910/AD | 12/08/2022 | 12/08/2022 | Resource Division | 36.27 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000309/2023-2024 | 3118/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Ramganga Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1200] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000858/2022-2023 | 6941/AD | 18/11/2022 | 18/03/2023 | RAMEN GHOSH | 219.32 | 79.45 | 36.23 | 60
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Construction of 1 (one) no. Pump House (5.40m x 3.60m) including sanitary arrangement as per departmental drawing for implementing of JAL SWAPNA (JJM) at 3rd Tubewell site of Ramganga Water Supply Scheme (Augmentation), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000017/2022-2023 | 3836/AD | 08/08/2022 | 07/09/2022 | ABONTICA ENTERPRISE | 5.15 | 5.07 | 98.37 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Making and fixing of permanent display board at headwork site of Meherpur, Srinarayanpur (Part - I, II & II), Rajrajeswarpur, Ramganga PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002090/2023-2024 | 922/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.95 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Supply & delivery of submersible pumping machinery for PH-1 of Augmentation of Ramganga W/s Scheme under South 24pgs Mechanical Division, PHE. Dte. (Block-Patharpratima) (SM/11281) | Assistant Engineer -II | Junior Engineer | ORD/000119/2024-2025 | 850-AE-II-SMD | 15/07/2024 | 30/07/2024 | DITHI ENTERPRISE | 0.78 | 0.78 | 100 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000771/2023-2024 | 605/AD | 29/01/2024 | 29/01/2024 | Resource Division | 21.26 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000941/2023-2024 | 1675/AD | 22/03/2024 | 22/03/2024 | Resource Division | 19.24 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/05696/2023-2024 | BP-2023-24-612 | 28/03/2024 | 28/03/2024 | WBSEDCL | 4.55 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Ramganga Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000505/2022-2023 | 5091/AD | 20/09/2022 | 10/03/2025 | M/S. S.S. ENTERPRISE | 494.53 | 240.29 | 48.59 | 55
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Ramganga W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/001202/2023-2024 | 4079/AD | 23/11/2023 | 23/03/2025 | G.M. ENTERPRISE | 9.55 | 0 | 0 | 90
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Continuation order for Hiring of Motor Launch for Kakdwip Sub-Division under Alipore Division, P.H.E.D. for execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas. (Period from 10.04.2024 to 09.07.2024) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002155/2024-2025 | 1966/AD | 05/04/2024 | 05/07/2024 | RAJKUMAR MANNA | 8.97 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Ramganga PWSS, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11281) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000186/2024-2025 | 2546/AD | 18/06/2024 | 17/02/2025 | M/S. S.S. ENTERPRISE | 87.68 | 0 | 0 | 80
17 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Improvement of outdoor illumination arrangement with allied works at PH-1 of Ramganga W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima][SM/11281] | Assistant Engineer -II | Junior Engineer | ORD/001887/2024-2025 | 849-AE-II-SMD | 15/07/2024 | 30/07/2024 | DITHI ENTERPRISE | 0.9 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Repairing of Pump House and Boundary wall, approach road at 3nos Pump House site of Ramganga Water Supply Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11281) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000132/2025-2026 | 2630/AD | 05/06/2025 | 20/07/2025 | AZAD RAHAMAN LASKAR | 5.99 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Hiring of Inspection vehicle (Motor Cab) under JJM for the office of the Executive Engineer South 24 Pgs Mechanical Division PHE Dte. | Assistant Engineer -II | Junior Engineer | ORD/002487/2024-2025 | 1608-AE-II/SMD | 27/12/2024 | 26/06/2025 | S.P. CONSTRUCTION | 0.86 | 0 | 0 | 0
20 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 of Ramganga Augmentation water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000567/2022-2023 | 583/SMD | 23/02/2023 | 30/07/2025 | DITHI ENTERPRISE | 11.27 | 9.41 | 83.48 | 90
21 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Ramganga PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (SM/11281) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/003195/2023-2024 | 1199/KSD | 26/12/2023 | 05/01/2024 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0 | 100
22 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMGANGA PWSS TO ACCOMMODATE FHTC IN PATHAR PRATIMA BLOCK UNDER KAKDWIP SUB DIVISION OF ALIPORE DIVISION IN SOUTH 24PARGANAS DISTRICT | SM/11281 | Augmentation | Hiring of Motor Launch for Kakdwip Sub-Division under Alipore Division, P.H.E.D. for execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas. (Period from 10.01.2024 to 09.04.2024) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001870/2023-2024 | 199/AD | 09/01/2024 | 09/04/2024 | RAJKUMAR MANNA | 8.97 | 0 | 0 | 0
Total | [13 empty] | 967.26 | 364.31 | 37.66