## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/11745 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (MEHERPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000467/2022-2023 | 1708/AD | 14/06/2022 | 29/07/2022 | INDRANIL DUTTA & ASSOCIATES | 3.77 | 3.77 | 100 | 100
2 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/11745 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Meherpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I | Junior Engineer | ORD/000353/2022-2023 | 3757/SMD | 29/12/2022 | 29/03/2023 | ALPHA ENTERPRISE | 19.33 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/11745 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Meherpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000921/2023-2024 | 2974/AD | 26/09/2023 | 10/11/2023 | RAMKRISHNA ENTERPRISE | 9.54 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/11745 | New | Material Requisition To Resource Division |  |  | RTOR000065/2022-2023 | 3953/AD | 12/08/2022 | 12/08/2022 | Resource Division | 13.52 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/11745 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00011/2023-2024 | BP-2023-24-42 | 18/05/2023 | 18/05/2023 | WBSEDCL | 5.72 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/11745 | New | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at PH-1 of Meherpur W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Patharpratima] | Assistant Engineer -I | Junior Engineer | ORD/001893/2023-2024 | 1181/SMD | 22/03/2024 | 12/04/2024 | ALPHA ENTERPRISE | 8.42 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/11745 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Meherpur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11745) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000188/2024-2025 | 2549/AD | 18/06/2024 | 17/08/2024 | TANMAY ROY CHOWDHURY | 65.22 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/11745 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Meherpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000299/2022-2023 | 3835/AD | 08/08/2022 | 22/09/2022 | M/S. L.P. CONSTRUCTION | 37.08 | 37.08 | 100 | 100
9 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/11745 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Meherpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000305/2022-2023 | 3841/AD | 08/08/2022 | 07/09/2022 | KUNDU CONSTRUCTION CO. | 9.96 | 9.21 | 92.48 | 50
10 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/11745 | New | Supply & delivery of submersible pumping machinery with allied materials for JJM works at PH-1 of Meherpur W/S Scheme under South 24pgs Mechanical Division, PHE. Dte. |  |  | ORD/000885/2023-2024 | 2781/SMD | 24/08/2023 | 23/09/2023 | T.S. CONSTRUCTION | 2.99 | 2.99 | 100 | 100
11 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/11745 | New | Making and fixing of permanent display board at headwork site of Meherpur, Srinarayanpur (Part - I, II & II), Rajrajeswarpur, Ramganga PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002090/2023-2024 | 922/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.95 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/11745 | New | Material Requisition To Resource Division |  |  | RTOR000578/2023-2024 | 52/AD | 03/01/2024 | 03/01/2024 | Resource Division | 6.41 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/11745 | New | Material Requisition To Resource Division |  |  | RTOR000942/2023-2024 | 1676/AD | 22/03/2024 | 22/03/2024 | Resource Division | 14.42 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/11745 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Meherpur W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000158/2023-2024 | 680/AD | 17/05/2023 | 01/04/2026 | M/S B. ENTERPRISE | 28.72 | 0 | 0 | 60
15 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MEHERPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/11745 | New | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 2 nos. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Meherpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000298/2023-2024 | 1492/AD | 14/07/2023 | 09/05/2024 | TANMAY ROY CHOWDHURY | 311.15 | 170.55 | 54.81 | 30
Total | [13 empty] | 537.17 | 223.59 | 41.62