## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-II) under Alipore Division, PHE Dte. (for the period from 01.09.2022 to 28.02.2023) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000465/2022-2023 | 200/HQ-I/AD | 29/08/2022 | 04/09/2022 | DEEPAK KUMAR PRASAD | 2.4 | 1.04 | 43.2 | 60
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KRISHNANAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000479/2022-2023 | 1709/AD | 14/06/2022 | 29/07/2022 | VOYAGER | 5.47 | 5.47 | 100 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-G) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000312/2022-2023 | 3860/AD | 08/08/2022 | 07/09/2022 | SARKAR ENTERPRISE | 11.97 | 11.94 | 99.78 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000309/2022-2023 | 3857/AD | 08/08/2022 | 07/09/2022 | A. K. INDUSTRIES | 13.48 | 13.27 | 98.42 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Inter connection between tubewell no. 1 and 2 to distribution system of Krishnanagar Water Supply Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001148/2021-2022 | 5536/AD | 20/01/2022 | 04/02/2022 | JHARNA ENTERPRISE | 6.17 | 2.74 | 44.4 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-K) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000316/2022-2023 | 3864/AD | 08/08/2022 | 07/09/2022 | SWASTIK ENTERPRISE (NEW) | 6.95 | 5.4 | 77.74 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000297/2022-2023 | 3833/AD | 08/08/2022 | 07/09/2022 | SIMPLEX DRILLING CO. | 22.93 | 22.4 | 97.7 | 99
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-H) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000313/2022-2023 | 3861/AD | 08/08/2022 | 07/09/2022 | DEY ENTERPRISE (III) | 11.47 | 11.28 | 98.36 | 100
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000314/2022-2023 | 3862/AD | 08/08/2022 | 23/08/2022 | SRI DURGA ENTERPRISE | 7.2 | 7.15 | 99.37 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000310/2022-2023 | 3858/AD | 08/08/2022 | 07/09/2022 | A. K. INDUSTRIES | 13.15 | 13.14 | 99.9 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-F) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000311/2022-2023 | 3859/AD | 08/08/2022 | 07/09/2022 | JOY GURU TRADING | 13.82 | 13.52 | 97.88 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-J) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000315/2022-2023 | 3863/AD | 08/08/2022 | 23/08/2022 | NARAYAN ENTERPRISE | 6.95 | 5.41 | 77.77 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC =510] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000407/2022-2023 | 4661/AD | 07/09/2022 | 05/01/2023 | UNIVERSAL CORPORATION | 148.05 | 146.97 | 99.27 | 75
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-L) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000317/2022-2023 | 3865/AD | 08/08/2022 | 07/09/2022 | M/S SNEHALATA ENTERPRISE | 5.57 | 5.56 | 99.96 | 100
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-M) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000318/2022-2023 | 3866/AD | 08/08/2022 | 07/09/2022 | M/S AMULLYA SARASWATI ENTERPRISE & CO. | 5.11 | 5.11 | 100 | 100
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Supplying, fitting, fixing and delivery of different dia. specials for Augmentation of Krishnanagar W/S Scheme, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000144/2023-2024 | 143/KSD | 30/05/2023 | 09/06/2023 | M/S. P. GIRI ENTERPRISE | 3.38 | 3.38 | 100 | 100
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000093/2022-2023 | 5591/AD | 29/09/2022 | 29/09/2022 | Resource Division | 14.31 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000501/2023-2024 | 4826/AD | 20/12/2023 | 20/12/2023 | Resource Division | 58.78 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000331/2023-2024 | 3146/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
20 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00012/2023-2024 | BP-2023-24-41 | 18/05/2023 | 18/05/2023 | WBSEDCL | 2.38 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | VEHICLE BILL FOR ASSISTANT ENGINEER HQ-II |  |  | BILL/00787/2022-2023 | BP-2022-23-981 | 21/03/2023 | 21/03/2023 | DEEPAK KUMAR PRASAD | 0.38 | 0 | 0 | 0
22 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Laying distribution system, Construction of 01 No. Pump House for Providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000308/2022-2023 | 3856/AD | 08/08/2022 | 22/09/2022 | MODERN CONSTRUCTION | 59.61 | 59.19 | 99.3 | 100
23 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) (SM/11747) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000174/2024-2025 | 2533/AD | 18/06/2024 | 18/07/2024 | M/S B.S. ENTERPRISE | 5.73 | 0 | 0 | 0
24 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Construction of Household Tap Platform at different household in habitation - Krishnanagar for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11747) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000170/2024-2025 | 2529/AD | 18/06/2024 | 18/07/2024 | ANANDA MAITY | 7.98 | 0 | 0 | 0
25 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Construction of Household Tap Platform at different household in habitation - Paschim Gharai Para for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11747) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000171/2024-2025 | 2530/AD | 18/06/2024 | 18/07/2024 | M/S SNEHALATA ENTERPRISE | 7.66 | 0 | 0 | 0
26 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) (SM/11747) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000177/2024-2025 | 2536/AD | 18/06/2024 | 18/07/2024 | M/S MODINA ENTERPRISE | 5.52 | 0 | 0 | 0
27 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-F) (SM/11747) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000179/2024-2025 | 2538/AD | 18/06/2024 | 18/07/2024 | M/S. BABA KAPIL MUNI ENTERPRISE | 7.01 | 0 | 0 | 0
28 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Krishnanagar W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002419/2023-2024 | 1346/AD | 06/03/2024 | 05/04/2024 | M/S. NAYAK CONSTRUCTION | 11.59 | 8.11 | 70.03 | 50
29 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Improvement of outdoor illumination arrangement with allied works at PH-1 Krishnanagar Aug W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Sagar] | Assistant Engineer -I | Junior Engineer | ORD/002866/2023-2024 | 1217/AE-I/SMD | 24/11/2023 | 09/12/2023 | KARUNAMOY ENGINEERING | 0.9 | 0 | 0 | 0
30 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Construction of Household Tap Platform at different household in habitation - Gholapara for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11747) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000173/2024-2025 | 2532/AD | 18/06/2024 | 18/07/2024 | M/S. MOYNA ENTERPRISE | 7.06 | 0 | 0 | 0
31 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) (SM/11747) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000178/2024-2025 | 2537/AD | 18/06/2024 | 18/07/2024 | M/S. JOYGURU ENTERPRISE | 5.43 | 0 | 0 | 0
32 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Construction of Household Tap Platform at different household in habitation - Gholapara South for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11747) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000172/2024-2025 | 2531/AD | 18/06/2024 | 18/07/2024 | M/S. JOYGURU ENTERPRISE | 5.66 | 0 | 0 | 0
33 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) (SM/11747) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000175/2024-2025 | 2534/AD | 18/06/2024 | 18/07/2024 | PRADIP KUMAR MONDAL | 5.62 | 0 | 0 | 0
34 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-G) (SM/11747) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000180/2024-2025 | 2539/AD | 18/06/2024 | 18/07/2024 | M/S PIR BABA ENTERPRISE | 5 | 0 | 0 | 0
35 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC =510] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000409/2022-2023 | 4678/AD | 07/09/2022 | 05/01/2023 | M/S. P. GIRI ENTERPRISE | 151.6 | 137.74 | 90.86 | 100
36 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Laying distribution system along the East side of Main Road for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-N) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001840/2023-2024 | 128/AD | 05/01/2024 | 28/02/2024 | KHOKAN MONDAL | 29.23 | 29.21 | 99.95 | 100
37 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Making and fixing of permanent display board at headwork site of Krishnanagar, Khansaheber Abad, Naraharipur, Khas Ramkarchar PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002171/2023-2024 | 953/KSD | 19/12/2023 | 24/12/2023 | ANANTA KUMAR GIRI | 0.81 | 0.2 | 24.99 | 100
38 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Laying distribution system for providing FHTC, for Augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-P) (SM/11747) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000169/2024-2025 | 2528/AD | 18/06/2024 | 18/07/2024 | M/S. P. GIRI ENTERPRISE | 7.62 | 7.46 | 97.85 | 100
39 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Supply & delivery of submersible pumping machinery at PH No-1 of Augmentation of Krishnanagar W/S Scheme under south 24 Pgs Mechanical Division PHE Dte. [Block: Sagar] | Assistant Engineer -I | Junior Engineer | ORD/002360/2023-2024 | 1227-AE-I-SMD | 04/12/2023 | 19/12/2023 | KARUNAMOY ENGINEERING | 0.94 | 0.94 | 100 | 100
40 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED KRISHNANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11747 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, for Augmentation of Krishnanagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000344/2022-2023 | 3748/SMD | 29/12/2022 | 29/03/2023 | KARUNAMOY ENGINEERING | 11.2 | 9.59 | 85.66 | 5
Total | [13 empty] | 696.36 | 526.24 | 75.57