## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for 4(four) months (period from 01/01/2022 to 30/04/2022) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001206/2021-2022 | 403/DHSD | 28/12/2021 | 01/01/2022 | MADHUSUDAN MAITY | 1.6 | 0.78 | 48.75 | 55
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (COMPANIR CHAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000480/2022-2023 | 1710/AD | 14/06/2022 | 29/07/2022 | VOYAGER | 6.12 | 6.12 | 100 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Companir Char PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000076/2023-2024 | 60/KSD | 02/05/2023 | 06/05/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Relaying UPVC pipe line from Nodal Point 18 to 20, 13 to 48, 13 to 64 of Companirchar W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000390/2020-2021 | 952/KSD | 03/11/2020 | 03/12/2020 | SK ENTERPRISE | 4.42 | 4.41 | 99.93 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Companirchar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000296/2022-2023 | 3832/AD | 08/08/2022 | 07/09/2022 | SIMPLEX DRILLING CO. | 22.93 | 21.55 | 93.97 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000095/2022-2023 | 5597/AD | 29/09/2022 | 29/09/2022 | Resource Division | 14.31 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000285/2023-2024 | 3087/AD | 28/09/2023 | 28/09/2023 | Resource Division | 56.81 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000333/2023-2024 | 3148/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00013/2023-2024 | BP-2023-24-03 | 25/04/2023 | 25/04/2023 | WBSEDCL | 2.69 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Companir char Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000306/2022-2023 | 3842/AD | 08/08/2022 | 07/09/2022 | DIPA CHHETRI | 11.78 | 11.75 | 99.72 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Companirchar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000307/2022-2023 | 3855/AD | 08/08/2022 | 23/08/2022 | GHOSH CONSTRUCTION | 8.03 | 8.01 | 99.74 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Companirchar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000446/2022-2023 | 4645/AD | 06/09/2022 | 04/01/2023 | RELIABLE CONSTRUCTION | 149.69 | 131.11 | 87.58 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Companir char W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002179/2023-2024 | 815/AD | 05/02/2024 | 06/03/2024 | M/S. MANDAL ENTERPRISE | 11.65 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Supply & installation of LED board at P.H. No-1 of Comanirchar Aug & PH-1 of Mrityunjaynagar Aug water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Sagar] | Assistant Engineer -I | Junior Engineer | ORD/000659/2024-2025 | 764-AE-I-SMD | 03/06/2024 | 18/06/2024 | MAA SUSOMA & COMPANY | 0.82 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Improvement of outdoor illumination arrangement with allied works at PH No-1 of Companirchar Augmentation W/S Scheme under JJM south 24 Pgs Mechanical Division PHE Dte [Block - Sagar] | Assistant Engineer -I | Junior Engineer | ORD/002070/2023-2024 | 679-AE-I-SMD | 21/06/2023 | 06/07/2023 | ROY & BISWAS ENGG. CO. | 0.83 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Companirchar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I | Junior Engineer | ORD/000003/2023-2024 | 988/SMD | 06/04/2023 | 05/07/2023 | ROY & BISWAS ENGG. CO. | 10.14 | 9.76 | 96.34 | 100
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Allied works for pile and pile cap portion regarding the construction of 350 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Companirchar W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000280/2023-2024 | 1430/AD | 13/07/2023 | 27/08/2023 | TANMAY ROY CHOWDHURY | 88.41 | 75.13 | 84.98 | 50
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Supplying, fitting, fixing and delivery of different dia. specials for Augmentation of Companir Char W/S Scheme under JJM, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000717/2023-2024 | 2535/AD | 28/08/2023 | 27/09/2023 | TANMAY ROY CHOWDHURY | 9.03 | 9.03 | 100 | 100
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Making and fixing of permanent display board at headwork site of Mrityunjoynagar, Radhakrishnapur, Companirchar, Kachuberia PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002168/2023-2024 | 952/KSD | 19/12/2023 | 24/12/2023 | ANANTA KUMAR GIRI | 0.81 | 0.2 | 24.99 | 100
20 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000901/2023-2024 | 887/AD | 07/02/2024 | 07/02/2024 | Resource Division | 3.44 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 1 no. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Companirchar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000671/2022-2023 | 6156/AD | 01/11/2022 | 21/04/2025 | TANMAY ROY CHOWDHURY | 344.09 | 257.1 | 74.72 | 95
22 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED COMPANIR CHAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/11748 | Augmentation | Repairing of 1 no. Pump House, Earth Filling, Boundary Wall Painting and Repair, Approach Road at 1st Tubewell site for Companir Char Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11748) (SM/09077) (SM/08802) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000021/2025-2026 | 2007/AD | 28/04/2025 | 12/06/2025 | PALASH HALDAR | 8.27 | 0 | 0 | 0
Total | [13 empty] | 756.64 | 535.43 | 70.76