## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMCHANDRANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11749 | Augmentation | Laying distribution system, Construction of 1 no. Pump House for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Ramchandranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000320/2022-2023 | 3867/AD | 08/08/2022 | 22/09/2022 | S.S. ENTERPRISE (I) | 60.13 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED RAMCHANDRANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11749 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, for Augmentation of Ramchandranagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/000428/2022-2023 | 3824/SMD | 29/12/2022 | 29/03/2023 | K.S.P ENTERPRISE | 11.09 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMCHANDRANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11749 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Ramchandranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000389/2022-2023 | 4483/AD | 31/08/2022 | 30/09/2022 | M/S BHAGABATI ENTERPRISE | 11.83 | 11.2 | 94.74 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMCHANDRANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11749 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( RAMCHANDRANAGAR, PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000491/2022-2023 | 1749/AD | 15/06/2022 | 30/07/2022 | LEMNISCATE | 5.29 | 5.29 | 100 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMCHANDRANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11749 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2022-2023 | 3917/AD | 12/08/2022 | 12/08/2022 | Resource Division | 43.94 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMCHANDRANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11749 | Augmentation | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Ramchandranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 412] | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000488/2023-2024 | 1788/AD | 26/07/2023 | 27/12/2026 | ASIATIC ENGINEERS CO OPERATIVE SOCIETY LIMITED | 374.21 | 154.86 | 41.38 | 40
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMCHANDRANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11749 | Augmentation | Making and fixing of permanent display board at headwork site of Gobindapur, Ramchandrapur, Ramchandranagar, Srikrishnanagar, Sibnagar, Manmathapur (Manmathanagar) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002143/2023-2024 | 943/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.94 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMCHANDRANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11749 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000275/2023-2024 | 3074/AD | 28/09/2023 | 28/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMCHANDRANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11749 | Augmentation | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc. for Augmentation of Ramchandranagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11749) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000306/2024-2025 | 2680/AD | 24/06/2024 | 18/10/2025 | AKKRITI CONSTRUCTION | 82.24 | 0 | 0 | 30
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMCHANDRANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11749 | Augmentation | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Ramchandranagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11749) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000560/2024-2025 | 3812/AD | 19/09/2024 | 19/10/2024 | S. CHAKRABORTY AND CO. | 20.39 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMCHANDRANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11749 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Ramchandranagar W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000132/2024-2025 | 2408/AD | 07/06/2024 | 07/07/2024 | SUKUMAR HALDAR | 9.51 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMCHANDRANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11749 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Ramchandranagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002601/2023-2024 | 179/KSD | 09/01/2024 | 14/01/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMCHANDRANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11749 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000675/2023-2024 | 441/AD | 24/01/2024 | 24/01/2024 | Resource Division | 7.18 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED RAMCHANDRANAGAR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11749 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000826/2023-2024 | 671/AD | 30/01/2024 | 30/01/2024 | Resource Division | 13.45 | 0 | 0 | 0
Total | [13 empty] | 640.99 | 171.85 | 26.81