## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( GANGADHARPUR (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000492/2022-2023 | 1750/AD | 15/06/2022 | 30/07/2022 | LEMNISCATE | 6.22 | 6.22 | 100 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/05/2022 to 30/04/2023) | Assistant Engineer, Diamond Harbour sub division |  | ORD/000216/2022-2023 | 45/DHSD | 29/04/2022 | 30/04/2022 | GOPAL KUMAR JHA | 4.8 | 1.96 | 40.88 | 71
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-I&II for Augmentation of Gangadharpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/000372/2022-2023 | 3776/SMD | 29/12/2022 | 29/03/2023 | BHUNIA BUILDERS | 9.3 | 8.38 | 90.08 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Gangadharpur (Zone-I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000294/2022-2023 | 3831/AD | 08/08/2022 | 22/09/2022 | M/S AHAMED CONSTRUCTION | 36.53 | 33.64 | 92.09 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Gangadharpur (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000322/2022-2023 | 3869/AD | 08/08/2022 | 07/09/2022 | MS S.M. ENTERPRISE | 14.79 | 14.51 | 98.11 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000089/2022-2023 | 5596/AD | 29/09/2022 | 29/09/2022 | Resource Division | 14.31 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000459/2023-2024 | 4722/AD | 18/12/2023 | 18/12/2023 | Resource Division | 33.17 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00019/2023-2024 | BP-2023-24-04 | 25/04/2023 | 25/04/2023 | WBSEDCL | 3.28 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Payment of electric bills for new service connection under SMD, PHE Dte. |  |  | BILL/01559/2022-2023 | BP-2022-23-452 | 20/03/2023 | 20/03/2023 | WBSEDCL | 1.42 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gangadharpur (Zone - I & II) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002616/2023-2024 | 864(A)/KSD | 13/12/2023 | 23/12/2023 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gangadharpur (Zone - I & II) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002615/2023-2024 | 733/KSD | 05/12/2023 | 15/12/2023 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Laying distribution system, Construction of 2 nos. Pump House for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Gangadharpur (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000321/2022-2023 | 3868/AD | 08/08/2022 | 07/09/2022 | SANKAR HALDER | 59.33 | 59.13 | 99.66 | 85
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 2, Zone-I&II for Augmentation of Gangadharpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -II | Junior Engineer | ORD/000810/2023-2024 | 2925/SMD | 01/09/2023 | 30/11/2023 | T.S. CONSTRUCTION | 9.08 | 9.03 | 99.46 | 80
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Making and fixing of permanent display board at headwork site of Taktipur Abad Zone - I & II, Chandipur, Bamanagar, Gangadharpur Zone - I &II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002141/2023-2024 | 941/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.94 | 0.31 | 33.32 | 100
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Supply & installation of LED board at Zone-I & II PH-1&2 of Gangadharpur Aug. W/S Scheme under South 24-Pgs Mechanical Division PHE Dte.(Block-Kakdwip) |  |  | ORD/001653/2023-2024 | 1026/AE-I/SMD | 20/09/2023 | 05/10/2023 | DITHI ENTERPRISE | 0.78 | 0.78 | 100 | 100
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gangadharpur Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002599/2023-2024 | 177/KSD | 09/01/2024 | 14/01/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gangadharpur Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002600/2023-2024 | 178/KSD | 09/01/2024 | 14/01/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000996/2023-2024 | 1789/AD | 27/03/2024 | 27/03/2024 | Resource Division | 30.96 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Construction of 2 nos. 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Gangadharpur (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 600] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000543/2023-2024 | 2209/AD | 10/08/2023 | 01/01/2026 | M/S PIONEER CONSTRUCTION | 450.22 | 197.73 | 43.92 | 60
20 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st and 2nd Tubewell Site for Augmentation of Gangadharpur (Zone-I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/11805) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001330/2024-2025 | 5414/AD | 24/12/2024 | 07/02/2025 | L G CONSTRUCTION | 39.76 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED GANGADHARPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11805 | Augmentation | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Gangadharpur (Zone - I &II) PWSS, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11805) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000573/2024-2025 | 4027/AD | 30/09/2024 | 01/01/2026 | M/S PIONEER CONSTRUCTION | 154.01 | 0 | 0 | 20
Total | [13 empty] | 870.83 | 332.66 | 38.2