## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | SM/11848 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (BANASHYAM NAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000463/2022-2023 | 2490/AD | 27/06/2022 | 11/08/2022 | INDRANIL DUTTA & ASSOCIATES | 6.47 | 6.47 | 100 | 100
2 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | SM/11848 | New | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-II) under Alipore Division, PHE Dte. (for the period from 01.03.2023 to 31.08.2023) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001828/2022-2023 | 520/HQ-II/AD | 27/02/2023 | 27/08/2023 | DEEPAK KUMAR PRASAD | 2.4 | 2.21 | 91.9 | 100
3 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | SM/11848 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Banashyam Nagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I | Junior Engineer | ORD/000354/2022-2023 | 3758/SMD | 29/12/2022 | 29/03/2023 | M.S.ENTERPRISE | 22.24 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | SM/11848 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Banashyamnagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000067/2023-2024 | 48/KSD | 28/04/2023 | 02/05/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 0
5 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | SM/11848 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Banashyamnagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000974/2023-2024 | 2993/AD | 06/10/2023 | 20/11/2023 | M/S RAKESH ENTERPRISE | 33.2 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | SM/11848 | New | Material Requisition To Resource Division |  |  | RTOR000520/2023-2024 | 4938/AD | 22/12/2023 | 22/12/2023 | Resource Division | 16.27 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | SM/11848 | New | Material Requisition To Resource Division |  |  | RTOR000089/2023-2024 | 535/AD | 12/05/2023 | 12/05/2023 | Resource Division | 10.85 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | SM/11848 | New | Vehicle bill for month of December'22 to January'2023 |  |  | BILL/00461/2022-2023 | BP-2022-23-791 | 22/02/2023 | 22/02/2023 | DEEPAK KUMAR PRASAD | 0.79 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | SM/11848 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction of 02 nos. Pump House for Banashyam Nagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1000] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000784/2022-2023 | 6538/AD | 11/11/2022 | 11/03/2023 | M/S A.K. GHATAK | 273.49 | 137.53 | 50.29 | 55
10 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | SM/11848 | New | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-II) under Alipore Division, PHE Dte. (From 01.09.2023 to 29.02.2024 | Assistant Engineer,HQ-II |  | ORD/000887/2023-2024 | 165/HQ-II/AD | 24/08/2023 | 24/02/2024 | DEEPAK KUMAR PRASAD | 2.4 | 1.83 | 76.41 | 45
11 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | SM/11848 | New | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-II) under Alipore Division, PHE Dte. (From 01.03.2024 to 31.08.2024) | Assistant Engineer,HQ-II | Junior Engineer-1 | ORD/002317/2023-2024 | 1103/AD | 23/02/2024 | 23/08/2024 | DEEPAK KUMAR PRASAD | 2.4 | 2.3 | 95.96 | 100
12 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | SM/11848 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Banashyamnagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000127/2024-2025 | 2405/AD | 07/06/2024 | 07/07/2024 | SANJIVINI ENTERPRISE | 11.78 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | SM/11848 | New | Allied works for pile and pile cap portion regarding the construction of 350 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Banashyamnagar W/S Scheme, South 24 Parganas, Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000587/2023-2024 | 2344/AD | 18/08/2023 | 02/10/2023 | UNIQUE AGENCY (PARTNER) | 58.37 | 52.92 | 90.66 | 90
14 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | SM/11848 | New | Making and fixing of permanent display board at headwork site of Banashyamnagar, Shibnagar, Gangapur, Chhoto Banashyamnagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002117/2023-2024 | 933/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.81 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | SM/11848 | New | Material Requisition To Resource Division |  |  | RTOR000947/2023-2024 | 1681/AD | 22/03/2024 | 22/03/2024 | Resource Division | 23.18 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | SM/11848 | New | Material Requisition To Resource Division |  |  | RTOR000741/2023-2024 | 576/AD | 29/01/2024 | 29/01/2024 | Resource Division | 1.94 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED BANASHYAM NAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION PHE DTE., BLOCK-PATHARPRATIMA, DISTRICT - SOUTH 24 PARGANAS | SM/11848 | New | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Banashyam Nagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000668/2022-2023 | 6153/AD. | 01/11/2022 | 28/08/2023 | UNIQUE AGENCY | 333.06 | 191.55 | 57.51 | 50
Total | [13 empty] | 800.13 | 395.3 | 49.4