## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.02.2022 to 31.07.2022 | Assistant Engineer, Kakdwip Sub Division |  | ORD/001679/2021-2022 | 935/KSD | 31/01/2022 | 31/07/2022 | PIKASU BOSE | 2.4 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.08.2021 to 31.01.2022 | Assistant Engineer, Kakdwip Sub Division |  | ORD/001331/2021-2022 | 456/KSD | 29/07/2021 | 29/01/2022 | PIKASU BOSE | 2.4 | 0 | 0 | 100
3 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (HARENDRANAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000501/2022-2023 | 2494/AD | 27/06/2022 | 11/08/2022 | LEMNISCATE | 4.71 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Harendranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) |  | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_3, Kakdwip Sub Division | ORD/000335/2022-2023 | 4065/AD | 18/08/2022 | 17/09/2022 | M/S MODINA ENTERPRISE | 19.21 | 0 | 0 | 40
5 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Harendranagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000343/2022-2023 | 4070/AD | 18/08/2022 | 02/10/2022 | AQUATECH ENGINEER | 37.06 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Harendranagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/000430/2022-2023 | 3826/SMD | 29/12/2022 | 29/03/2023 | RELIABLE CONSTRUCTION | 18.86 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Harendragnagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000048/2023-2024 | 33/KSD | 24/04/2023 | 28/04/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0 | 100
8 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile andile cap upto pedestal at Harendranagar, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000277/2023-2024 | 1427/AD | 13/07/2023 | 27/08/2023 | SUPRITI ENTERPRISE | 32 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Harendranagar W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000947/2023-2024 | 2979/AD | 26/09/2023 | 26/10/2023 | DEBIKA CONSTRUCTION | 9.52 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Harendranagar W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000945/2023-2024 | 2978/AD | 26/09/2023 | 10/11/2023 | C L B SYNDICATE | 27.65 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Laying distribution systemfor Providing Functional Household Tap Connection (FHTC) to all households for Harendranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000337/2022-2023 | 4067/AD | 18/08/2022 | 08/09/2022 | M/S. MOYNA ENTERPRISE | 7.49 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Trial bore (1 no.) of 100mm dia depth up to 450 mtr for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Head Work Site of Harendranagar W/S Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer-1,Juniour Engineer_3, Kakdwip Sub Division | ORD/001008/2023-2024 | 512/KSD | 03/10/2023 | 10/10/2023 | S.K.GOLUI | 2.72 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Material Requisition To Resource Division |  |  | RTOR000118/2023-2024 | 654/AD | 17/05/2023 | 17/05/2023 | Resource Division | 7.62 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Material Requisition To Resource Division |  |  | RTOR000440/2023-2024 | 4708/AD | 18/12/2023 | 18/12/2023 | Resource Division | 12.49 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Harendranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000783/2022-2023 | 6537/AD | 11/11/2022 | 07/09/2023 | SUPRITI ENTERPRISE | 371.44 | 0 | 0 | 20
16 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Making and fixing of permanent display board at headwork site of Harendranagar, Ramgopalpur, Uttar Kashiabad, Dakshin Kashiabad, Thangara, Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002140/2023-2024 | 940/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.94 | 0 | 0 | 100
17 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Material Requisition To Resource Division |  |  | RTOR000807/2023-2024 | 652/AD | 30/01/2024 | 30/01/2024 | Resource Division | 1.37 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Material Requisition To Resource Division |  |  | RTOR000990/2023-2024 | 1783/AD | 27/03/2024 | 27/03/2024 | Resource Division | 27 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED HARENDRANAGAR PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, PHE DTE., BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11849 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Harendranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000336/2022-2023 | 4066/AD | 18/08/2022 | 01/01/2025 | M/S. PARAMESWAR ENTERPRISE | 12.68 | 0 | 0 | 100
Total | [13 empty] | 598.03 | 0 | 0