## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Thangara water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/000432/2022-2023 | 3828/SMD | 29/12/2022 | 29/03/2023 | M/S. S.S. ENTERPRISE | 21.52 | 19.74 | 91.75 | 98
2 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Thangara Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/000334/2022-2023 | 4064/AD | 18/08/2022 | 17/09/2022 | M/S. GANGA ENTERPRISE | 11.81 | 11.76 | 99.55 | 100
3 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Thangara W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000344/2022-2023 | 4071/AD | 18/08/2022 | 02/10/2022 | AQUATECH ENGINEERS | 37.06 | 32.64 | 88.07 | 0
4 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (THANGARA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000502/2022-2023 | 2495/AD | 27/06/2022 | 11/08/2022 | LEMNISCATE | 3.94 | 3.94 | 100 | 100
5 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Thangara Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/000333/2022-2023 | 4063/AD | 18/08/2022 | 17/09/2022 | MUKHERJEE ENTERPRISE (II) | 17.79 | 16.56 | 93.06 | 95
6 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Thangara Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/001316/2022-2023 | 9881/AD | 10/01/2023 | 06/11/2023 | PATHIK PABAN NANDI | 281.34 | 156.42 | 55.6 | 55
7 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Thangara PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division | ORD/000051/2023-2024 | 37/KSD | 24/04/2023 | 28/04/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 0
8 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Thangara W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001155/2023-2024 | 3718/AD | 03/11/2023 | 03/12/2023 | M/S. M.S. ENTERPRISE | 9.51 | 8.42 | 88.53 | 100
9 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Thangara W/S Scheme, Block: Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001480/2023-2024 | 4683/AD | 18/12/2023 | 18/09/2024 | M/S IDEAL WORKS | 25.92 | 0 | 0 | 100
10 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Making and fixing of permanent display board at headwork site of Harendranagar, Ramgopalpur, Uttar Kashiabad, Dakshin Kashiabad, Thangara, Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002140/2023-2024 | 940/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.94 | 0.16 | 16.66 | 100
11 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Material Requisition To Resource Division |  |  | RTOR000119/2023-2024 | 655/AD | 17/05/2023 | 17/05/2023 | Resource Division | 5.66 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Material Requisition To Resource Division |  |  | RTOR000441/2023-2024 | 4709/AD | 18/12/2023 | 18/12/2023 | Resource Division | 42.17 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01714/2023-2024 | BP-2023-24-203 | 09/08/2023 | 09/08/2023 | WBSEDCL | 8.38 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary etc. at Thangara W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11850) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000464/2024-2025 | 3423/AD | 21/08/2024 | 20/09/2024 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 21.44 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Improvement of outdoor illumination arrangement with allied works at , PH-1 of Thangara W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/002994/2023-2024 | 443-AE-I-SMD | 20/02/2024 | 06/03/2024 | M/S. S.S. ENTERPRISE | 0.89 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Improvement of outdoor illumination arrangement with allied works at , PH-2 of Thangara W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/002995/2023-2024 | 444-AE-I-SMD | 20/02/2024 | 06/03/2024 | M/S. S.S. ENTERPRISE | 0.89 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Supply & installation of LED board at P.H. No-1 & 2 of Thangara water supply scheme, under South 24-Pgs Mechanical Division PHE Dte.[Block-Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/000589/2024-2025 | 746-AE-I-SMD | 28/05/2024 | 12/06/2024 | M/S. GLOBAL POWER CONCERN | 0.78 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Material Requisition To Resource Division |  |  | RTOR000808/2023-2024 | 653/AD | 30/01/2024 | 30/01/2024 | Resource Division | 1.02 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED THANGARA PIPE WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION BLOCK KAKDWIP DISTRICT SOUTH 24PARGANAS DISTRICT | SM/11850 | New | Material Requisition To Resource Division |  |  | RTOR000991/2023-2024 | 1784/AD | 27/03/2024 | 27/03/2024 | Resource Division | 5.39 | 0 | 0 | 0
Total | [13 empty] | 496.94 | 250.11 | 50.33