## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (SHIBPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000484/2022-2023 | 1748/AD | 15/06/2022 | 30/07/2022 | M/S R.DUTTA & CO. | 4.54 | 4.54 | 100 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Construction of 350 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 1 no. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Sibpur (Phase-B) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 250] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001785/2022-2023 | 11557/AD | 17/02/2023 | 14/12/2023 | R.P. ENTERPRISE | 176.39 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, Zone-I for Augmentation of Shibpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Namkhana] | Assistant Engineer -I | Junior Engineer | ORD/000422/2022-2023 | 3818/SMD | 29/12/2022 | 29/03/2023 | MAHAMAYA ENTERPRISE | 9.63 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Shibpur (Part-B) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000058/2023-2024 | 41/KSD | 27/04/2023 | 01/05/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000284/2023-2024 | 3081/AD | 28/09/2023 | 28/09/2023 | Resource Division | 0.6 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Sibpur W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002279/2023-2024 | 969/AD | 12/02/2024 | 13/03/2024 | M/S ASHA ENGINEERING | 9.66 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.12.2022 to 30.11.2023. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_3, Kakdwip Sub Division | ORD/002423/2022-2023 | 562/KSD | 02/12/2022 | 30/11/2023 | SARADA CONSTRUCTION | 4.8 | 4.33 | 90.29 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.03.2024 to 31.05.2024 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_3, Kakdwip Sub Division | ORD/003032/2023-2024 | 410/KSD | 27/02/2024 | 29/05/2024 | SARADA CONSTRUCTION | 1.2 | 1.08 | 90.08 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.06.2024 to 31.08.2024 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_3, Kakdwip Sub Division | ORD/000667/2024-2025 | 982/KSD | 27/05/2024 | 27/08/2024 | SARADA CONSTRUCTION | 1.2 | 1.16 | 96.58 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.12.2023 to 29.02.2024 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_3, Kakdwip Sub Division | ORD/003031/2023-2024 | 713/KSD | 30/11/2023 | 29/02/2024 | SARADA CONSTRUCTION | 1.2 | 1.12 | 93.03 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Making and fixing of permanent display board at headwork site of Debnibus, Shibpur, Budhakhali Zone-II (Part- I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002136/2023-2024 | 938/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.63 | 0.16 | 24.74 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Providing support services for data mapping of available data within command area for preparation of GMIS of Shibpur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001994/2023-2024 | 467/KSD | 22/09/2023 | 22/10/2023 | INDRANIL DUTTA & ASSOCIATES | 3.81 | 3.8 | 99.94 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Shibpur W/S Scheme, Block - Namkhana, for implementing of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11875) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000605/2024-2025 | 4092/AD | 03/10/2024 | 02/11/2024 | MEHAI TECHNOLOGY LIMITED | 20.27 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000986/2023-2024 | 1779/AD | 27/03/2024 | 27/03/2024 | Resource Division | 37.58 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000798/2023-2024 | 643/AD | 30/01/2024 | 30/01/2024 | Resource Division | 3.38 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.09.2024 to 30.11.2024 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_3, Kakdwip Sub Division | ORD/000668/2024-2025 | 1255/KSD | 28/08/2024 | 27/11/2024 | SARADA CONSTRUCTION | 1.2 | 1.07 | 89.44 | 0
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.12.2024 to 28.02.2025 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002923/2024-2025 | 1654/KSD | 26/11/2024 | 24/02/2025 | SARADA CONSTRUCTION | 1.2 | 1.13 | 94.38 | 0
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.03.2025 to 31.05.2025 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_3, Kakdwip Sub Division | ORD/003006/2024-2025 | 350/KSD | 27/02/2025 | 30/05/2025 | SARADA CONSTRUCTION | 1.2 | 0.74 | 61.71 | 0
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Allied works for pile and pile cap portion regarding the construction of 350 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Augmentation of Sibpur W/S Scheme, South 24 Parganas, Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000589/2023-2024 | 2346/AD | 18/08/2023 | 01/01/2025 | R.P. ENTERPRISE | 45.18 | 0 | 0 | 100
20 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Construction of Platform, rising main and Road Restoration for Augmentation of Shibpur (Phase-B) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) (SM/11875) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000461/2024-2025 | 3420/AD | 21/08/2024 | 04/04/2025 | BIMALENDU GIRI | 58.17 | 8.57 | 14.73 | 30
21 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Repairing of Pump House and Boundary wall at 1st Tube well site of Sibpur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11875) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002140/2024-2025 | 1980/KSD | 23/12/2024 | 12/01/2025 | USHA ENTERPRISE | 2.43 | 0 | 0 | 98
22 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Repairing of Pump House and Boundary wall at 2nd Tube well site of Sibpur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11875) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002141/2024-2025 | 1981/KSD | 23/12/2024 | 12/01/2025 | USHA ENTERPRISE | 1.81 | 0 | 0 | 95
23 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | New Service connection and security deposit for Shibpur PH-3 under JJM Application No-1008616957 Ref ID- 107086022 |  |  | BILL/01055/2025-2026 | 42152 | 01/08/2025 | 01/08/2025 | WBSEDCL | 6.27 | 0 | 0 | 0
24 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION FOR GROUND WATER BASED SHIBPUR PIPE WATER SUPPLY SCHEME, Phase-B, UNDER ALIPORE DIVISION, BLOCK : NAMKHANA, DISTRICT : SOUTH 24 PARGANAS | SM/11875 | Augmentation | Construction of Rising Main, Platform, Road Restoration and Y junction for Augmentation of Shibpur (Phase-B) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-I) (SM/11875) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000405/2024-2025 | 3188/AD | 31/07/2024 | 05/03/2025 | BIMALENDU GIRI | 40.92 | 0 | 0 | 0
Total | [13 empty] | 433.75 | 28.18 | 6.5