## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-I) under Alipore Division, PHE Dte. (for the period from 01.09.2022 to 28.02.2023) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000469/2022-2023 | 316/HQ-I/AD | 29/08/2022 | 28/02/2023 | FIROJA KHATUN | 2.4 | 1.56 | 64.96 | 38
2 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Laxmipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000362/2022-2023 | 4117/AD | 18/08/2022 | 17/09/2022 | M/S NAIYA & MAITY | 18.12 | 16.4 | 90.5 | 100
3 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( LASKHMIPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000494/2022-2023 | 2493/AD | 27/06/2022 | 11/08/2022 | LEMNISCATE | 5.79 | 5.79 | 100 | 100
4 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Laskhmipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001724/2022-2023 | 11750/AD | 21/02/2023 | 23/03/2023 | MODERN CONSTRUCTION (NEW) | 19.3 | 0 | 0 | 20
5 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-I) under Alipore Division, PHE Dte. (for the period from 01.03.2023 to 31.08.2023). | Assistant Engineer,HQ-I |  | ORD/001836/2022-2023 | 551/HQ-I/AD | 27/02/2023 | 27/08/2023 | FIROJA KHATUN | 2.4 | 2.01 | 83.61 | 40
6 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Laying distribution system, Rising Main, construction of 01 no. Pump House Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Lakshmipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000360/2023-2024 | 1561/AD | 17/07/2023 | 15/10/2023 | SHIBU BISWAS | 189.75 | 162.57 | 85.67 | 92
7 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-I) under Alipore Division, PHE Dte. (From 01.09.2023 to 29.02.2024) | Assistant Engineer,HQ-I | Junior Engineer-1 | ORD/001043/2023-2024 | 155-/HQ-I/AD | 31/08/2023 | 29/02/2024 | FIROJA KHATUN | 2.4 | 1.57 | 65.32 | 20
8 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st Tubewell Site of Laxmipur W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001159/2023-2024 | 3721/AD | 03/11/2023 | 03/12/2023 | ANANDA CONSTRUCTION | 9.63 | 9.58 | 99.46 | 88
9 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Making and fixing of permanent display board at headwork site of Bhubannagar, Gobindarampur, Laxmipur, Madhusudanpur, Ramtanunagar, Shibkalinagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002142/2023-2024 | 942/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.94 | 0.16 | 16.66 | 100
10 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Material Requisition To Resource Division |  |  | RTOR000444/2023-2024 | 4711/AD | 18/12/2023 | 18/12/2023 | Resource Division | 25.6 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Construction of Platform and Road Restoration for Lakshmipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (PART-II) (SM/11877) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000462/2024-2025 | 3421/AD | 21/08/2024 | 22/02/2025 | ANANTA KUMAR GIRI | 67.99 | 0 | 0 | 20
12 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-I) under Alipore Division, PHE Dte. (From 01.03.2024 To 31.08.2024) | Assistant Engineer,HQ-I | Junior Engineer-1 | ORD/002393/2023-2024 | 1195/AD | 28/02/2024 | 28/08/2024 | FIROJA KHATUN | 2.4 | 1.94 | 80.74 | 100
13 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc. at Lakshmipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11877) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000198/2024-2025 | 2581/AD | 19/06/2024 | 03/08/2024 | SHIBU BISWAS | 38.17 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-I) under Alipore Division, PHE Dte. (From 01.09.2024 To 28.02.2025) | Assistant Engineer,HQ-I | Junior Engineer-1 | ORD/000648/2024-2025 | 3815/AD | 29/08/2024 | 28/02/2025 | FIROJA KHATUN | 2.4 | 0.62 | 25.8 | 100
15 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Material Requisition To Resource Division |  |  | RTOR000586/2023-2024 | 85/AD | 03/01/2024 | 03/01/2024 | Resource Division | 1.49 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Material Requisition To Resource Division |  |  | RTOR000993/2023-2024 | 1786/AD | 27/03/2024 | 27/03/2024 | Resource Division | 36.04 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Material Requisition To Resource Division |  |  | RTOR000809/2023-2024 | 654/AD | 30/01/2024 | 30/01/2024 | Resource Division | 13.01 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Payment for New Service connection of Laxmipur W/S Scheme PH-1 Application No:- 1007169430 Reference ID:- 106214425 |  |  | BILL/00966/2024-2025 | BP-2024-25-192 | 23/07/2024 | 23/07/2024 | WBSEDCL | 5.32 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED LASKHMIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/11877 | New | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including soil investigation including for Laxmipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11877) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001588/2024-2025 | 100/AD | 08/01/2025 | 05/10/2025 | KALPANA TRADERS | 134.8 | 0 | 0 | 0
Total | [13 empty] | 577.94 | 202.18 | 34.98