## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Annual Maintenance Contract (AMC) for Computers,Printers,UPS and other related peripherals of 15(Fifteen) laboratories 1) South 24 Parganas District Laboratory,Bijoygarh 2)Southern Health Improvement Society 3) Akshay Nagar Pallisri Sangha 4) Kensily Azad Sporting Club 5) Paschim Banga Vigyan Mancha 6) Narendrapur Ramkrishna Mission Loke Siksha Parishad 7) Mathurapur Ramkrishna Mission Loke Siksha Parishad 8) Sagar Mangal (under RKMLSP) 9) Raidighi Sub- District Laboratory 10) Diamond Harbour Sub-District Laboratory 11) Buita Sub-District Laboratory 12) Bakkhali Sub-District Laboratory 13) Canning Sub-District Laboratory 14) Basanti Sub-District Laboratory 15) Ramganga Sub-District Laboratory in the Dist. of South 24 Parganas under Alipore Division,PHE Dte. (period from 01/01/2021 to 31/12/2021) | Assistant Engineer, RWS |  | ORD/000790/2020-2021 | 663/RWS | 28/12/2020 | 28/12/2021 | RKLICK TECHNOLOGIES | 2.25 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Laboratory Maintenance charges of District Water Testing Laboratory at Bijoygarh under Alipore Division,PHE Dte.(Period from 01/07/2021 to 30/06/2022. |  |  | ORD/000248/2021-2022 | 167/RWS | 30/06/2021 | 30/06/2022 | ABONTICA ENTERPRISE | 0.99 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Remuneration of Chemist / Bacteriologist and Laboratory Assistant 04(Four) nos. New P.H.E Dte. Laboratories (Buita Sub-District Laboratory, Canning Sub-District Laboratory, Basanti Sub-District Laboratory, Diamond Harbour Sub-District Laboratory) under Alipore Division, PHE Dte. for 01 (One) year w.e.f 01/02/2021 to 31/01/2022. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000773/2020-2021 | 4753/AD | 23/01/2021 | 23/01/2022 | CLIFFORD FACILITY SERVICES PRIVATE LIMITED | 13.83 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Remuneration of Chemist-Bacteriologist 05 (Five) nos & Laboratory Assistant 04 (Four) nos. New P.H.E Dte. Laboratories (Kakdwip Sub-District Laboratory, Ramganga Sub-District Laboratory, Raidighi Sub-District Laboratory, Basanti Sub-District Laboratory) under Alipore Division, PHE Dte. for 01 (One) year w.e.f 01/02/2022 to 31/01/2023. | Assistant Engineer,HQ-I |  | ORD/000937/2021-2022 | 5035/AD | 20/12/2021 | 20/12/2022 | NATURAL RESOURCES CONSORTIUM | 15.94 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Remuneration of Chemist-Bacteriologist and Lab. Assistant of District Water Testing Laboratory, South 24 Parganas situated at Bijoygarh State General Hospital Complex, Kolkata under Alipore Division, PHE Dte. from 01/02/2022 to 31/01/2023. | Assistant Engineer,HQ-I |  | ORD/000938/2021-2022 | 4992/AD | 17/12/2021 | 17/12/2022 | NATURAL RESOURCES CONSORTIUM | 6.49 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Remuneration of Chemist-Bacteriologist and Laboratory Assistant 04(Four) nos. New P.H.E Dte. Laboratories ( Buita Sub-District Laboratory, Canning Sub-District Laboratory, Bakkhali Sub-District Laboratory, Diamond Harbour Sub-District Laboratory) under Alipore Division, PHE Dte. for 01 (One) year w.e.f 01/02/2022 to 31/01/2023. | Assistant Engineer,HQ-I |  | ORD/000939/2021-2022 | 4993/AD | 17/12/2021 | 17/12/2022 | NATURAL RESOURCES CONSORTIUM | 13.98 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Laboratory Maintenance charges of Basanti Water Testing Laboratory under Canning Sub-Division of Alipore Division, PHE Dte. (122 days) | Assistant Engineer, Canning sub division |  | ORD/001583/2021-2022 | 1600/CSD | 28/02/2022 | 30/06/2022 | SUSHANTA MANDAL | 0.23 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Annual maintenance bill of NGO managed Laboratories under Alipore Division, PHE Dte. |  |  | BILL/01175/2022-2023 | BP-2023-24-8 | 13/04/2023 | 13/04/2023 | RAMKRISHNA MISSION ASHRAMA | 0.75 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Remuneration of Lab Personnel of NGO managed Lab. under Alipore Division, PHE Dte. (Period for Jan. to March'23) |  |  | BILL/00680/2023-2024 | BP-2023-24-291 | 27/07/2023 | 27/07/2023 | RAMKRISHNA MISSION ASHRAMA | 1.35 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Remuneration of Laboratory personnel of NGO managed Laboratories under Alipore Division, PHE Dte. |  |  | BILL/01282/2023-2024 | BP-2023-24-331 | 08/08/2023 | 08/08/2023 | RAMKRISHNA MISSION ASHRAMA | 0.81 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Bill for remuneration of Lab personnel |  |  | BILL/01324/2023-2024 | BP-2023-24-348 | 17/08/2023 | 17/08/2023 | SAGAR MANGAL | 1.35 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Payment for Laboratory maintenance. |  |  | BILL/01322/2023-2024 | BP-2023-24-346 | 17/08/2023 | 17/08/2023 | PASCHIMBANGA VIGYAN MANCHA | 0.27 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Bill for remuneration of Lab personnel. |  |  | BILL/01325/2023-2024 | BP-2023-24-347 | 17/08/2023 | 17/08/2023 | PASCHIMBANGA VIGYAN MANCHA | 1.35 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Bonus for Lab personnel of NGO managed laboratories under Alipore Division, PHE Dte. |  |  | BILL/01470/2023-2024 | BP-2023-24-523 | 10/10/2023 | 10/10/2023 | RAMKRISHNA MISSION ASHRAMA | 0.13 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Bill for remuneration for Lab Personnel (Period of April'2023 to June'23) |  |  | BILL/01752/2023-2024 | BP-2023-24-603 | 19/10/2023 | 19/10/2023 | RAMKRISHNA MISSION ASHRAMA | 1.35 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Remuneration of Lab personnel of NGO managed laboratories under Alipore Division, PHE Dte.[Oct'20 to Dec'20] |  |  | BILL/01469/2023-2024 | BP-2023-24-522 | 10/10/2023 | 10/10/2023 | RAMKRISHNA MISSION ASHRAMA | 0.72 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Festival Bonus for Lab Personnel of 2023 |  |  | BILL/01876/2023-2024 | BP-2023-24-606 | 19/10/2023 | 19/10/2023 | PASCHIMBANGA VIGYAN MANCHA | 0.16 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Bill for remuneration for Lab Personnel (Period of March'2023 to July'23) |  |  | BILL/01754/2023-2024 | BP-2023-24-604 | 19/10/2023 | 19/10/2023 | SOUTHERN HEALTH IMPROVEMENT SAMITY | 1.65 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Maintenance billfor expenditure of Sagar Mangalunder Alipore Division, PHE Dte. (March'23 to August'23) |  |  | BILL/01903/2023-2024 |  | 16/10/2023 | 16/10/2023 | SAGAR MANGAL | 0.4 | 0 | 0 | 0
20 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Bill for Lab personnel remuneration. |  |  | BILL/01323/2023-2024 | BP-2023-24-349 | 17/08/2023 | 17/08/2023 | KENSILY AZAD SPORTING CLUB | 1.35 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Remuneration of Lab personnel under Alipore Division, PHE Dte |  |  | BILL/01875/2023-2024 | BP-2023-24-605 | 19/10/2023 | 19/10/2023 | PASCHIMBANGA VIGYAN MANCHA | 1.35 | 0 | 0 | 0
22 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Festival bonus Lab Personnel for the year 2023 |  |  | BILL/01877/2023-2024 | BP-2023-24-607 | 19/10/2023 | 19/10/2023 | KENSILY AZAD SPORTING CLUB | 0.16 | 0 | 0 | 0
23 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Annual maintenance bill of NGO managed Laboratories under Alipore Division, PHE Dte. |  |  | BILL/01176/2022-2023 | BP-2023-24-9 | 12/04/2023 | 12/04/2023 | RAMKRISHNA MISSION ASHRAMA | 0.75 | 0 | 0 | 0
24 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Remuneration of Lab personnel of NGO managed laboratories under Alipore Division, PHE Dte.[July'20 to Sept'20] |  |  | BILL/01468/2023-2024 | BP-2023-24-521 | 10/10/2023 | 10/10/2023 | RAMKRISHNA MISSION ASHRAMA | 0.99 | 0 | 0 | 0
25 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Remuneration of Lab personnel of NGO managed laboratories under Alipore Division, PHE Dte.[Oct'22 to Dec'22] |  |  | BILL/01471/2023-2024 | BP-2023-24-524 | 10/10/2023 | 10/10/2023 | RAMKRISHNA MISSION ASHRAMA | 0.99 | 0 | 0 | 0
26 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Remuneration of Chemist, Bacteriologist and Lab. Assistant of South 24 Parganas District Water Testing Laboratory situated at Bijoygarh State General Hospital Complex, Kolkata under Alipore Division, PHE Dte. from 01/02/2023 to 31/01/2024 | Assistant Engineer,HQ-I |  | ORD/001285/2022-2023 | 9238/AD | 29/12/2022 | 29/12/2023 | NATURAL RESOURCES CONSORTIUM | 6.9 | 0 | 0 | 35
27 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Remuneration of Chemist/Bacteriologist & Laboratory Assistant for 04 nos P.H.E Dte. Water Testing Laboratories (Buita Sub-District Laboratory, Canning Sub-District Laboratory, Bakkhali Sub-District Laboratory, Diamond Harbour Sub-District Laboratory) under Alipore Division, PHE Dte. for 01 (One) year w.e.f 01/02/2023 to 31/01/2024. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001286/2022-2023 | 9239/AD | 29/12/2022 | 29/12/2023 | NATURAL RESOURCES CONSORTIUM | 15.6 | 0 | 0 | 35
28 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Remuneration of Chemist/Bacteriologist & Laboratory Assistant for 04 nos P.H.E Dte. Water Testing Laboratories (Kakdwip Sub-District Laboratory,Ramganga Sub-District Laboratory,Raidighi Sub-District Laboratory,Basanti Sub-District Laboratory) under Alipore Division, PHE Dte. for 01 (One) year w.e.f 01/02/2023 to 31/01/2024. | Assistant Engineer, RWS |  | ORD/001287/2022-2023 | 9240/AD | 29/12/2022 | 29/12/2023 | NATURAL RESOURCES CONSORTIUM | 17.76 | 0 | 0 | 35
29 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Engagement of 10 (Ten) nos Lab. Personnel (Sampling Assistant and Lab. Attendant), actual travelling expenses and IEC activities to the Laboratory personnel for 07 nos Laboratories in the District of South 24 Parganas under Alipore Division, PHE Dte. for the period from 01/04/2023 to 31/03/2024. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/001384/2022-2023 | 10511/AD | 30/01/2023 | 30/01/2024 | NATURAL RESOURCES CONSORTIUM | 19.64 | 0 | 0 | 100
30 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Monthly remuneration of Chemist,Bacteriologist & Lab.Assistant of South 24 Parganas Ditrict Water Testing Laboratory situated at Bijoygarh State General Hospital Complex,Kolkata under Alipore Division, PHE Dte.from 01/02/2023 to 31/01/2024 | Assistant Engineer, RWS |  | ORD/002084/2022-2023 | 875/RWS | 23/03/2023 | 22/03/2024 | NATURAL RESOURCES CONSORTIUM | 2.52 | 0 | 0 | 35
31 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Enhancement of monthly remuneration of Chemist/Bacteriologist & Laboratory Assistant for 04 nos P.H.E Dte. Water Testing Laboratories (Buita Sub-District Laboratory, Canning Sub-District Laboratory, Bakkhali Sub-District Laboratory, Diamond Harbour Sub-District Laboratory) under Alipore Division, PHE Dte.for the period from 01/04/2023 to 31/01/2024 | Assistant Engineer, Diamond Harbour sub division |  | ORD/000620/2023-2024 | 362/RWS | 23/08/2023 | 23/06/2024 | NATURAL RESOURCES CONSORTIUM | 4.16 | 0 | 0 | 50
32 | SOUTH 24 PARGANAS |  | Alipore Division | OPERATION AND MAINTENANCE CHARGES OF 09 NOS PHED AND 06 NOS NGO MANAGED LABORATORIES UNDER ALIPORE DIVISION WITHIN THE DISTRICT OF SOUTH 24 PARGANAS RELATED TO WATER QUALITY MONITORING AND SURVEILLANCE UNDER JAL JEEVAN MISSION FOR THE F.Y. - 2022-2023 | SM/11981 | Support-WQMSP | Enhancement of monthly remuneration for engagement of 10(Ten) nos Lab. Personnal (Sampling Assistant and Lab. Attendent), actual travelling expenses and IEC activites to the Laboratory personnel for 07 nos Laboratories in the District. of South 24 Parganas under Alipore Division, PHE Dte.for the period from 01/04/2023 to 31/03/2024. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/000628/2023-2024 | 366/RWS | 23/08/2023 | 23/08/2024 | NATURAL RESOURCES CONSORTIUM | 4.16 | 0 | 0 | 100
Total | [13 empty] | 140.33 | 0 | 0