## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | REGULAR UPKEEP OF MOBILE LABORATORY VAN (MLV) UNDER WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME RELATED TO JAL JEEVAN MISSION (JJM) | SM/12280 | Support-WQMSP | Annual Maintenance for Mobile Laboratory Van (MLV) under Water Quality Monitoring and Surveillance Programme related to Jal Jeevan Mission in the district of South 24 paraganas under Alipore Division,PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000548/2022-2023 | 5657/AD | 11/10/2022 | 11/10/2023 | SUNANDA ENVIRONMENTAL INTERNATIONAL PVT. LTD. | 26.66 | 21.74 | 81.54 | 25
2 | SOUTH 24 PARGANAS |  | Alipore Division | REGULAR UPKEEP OF MOBILE LABORATORY VAN (MLV) UNDER WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME RELATED TO JAL JEEVAN MISSION (JJM) | SM/12280 | Support-WQMSP | Annual Maintenance for Mobile Laboratory Van (MLV) under Water Quality Monitoring and Surveillance Programme related to Jal Jeevan Mission in the district of South 24 paraganas under Alipore Division,PHE Dte. | Assistant Engineer,HQ-I |  | ORD/000549/2022-2023 | 5658/AD | 11/10/2022 | 11/10/2023 | SAKTI ENTERPRISE | 1.24 | 1.24 | 100 | 95
3 | SOUTH 24 PARGANAS |  | Alipore Division | REGULAR UPKEEP OF MOBILE LABORATORY VAN (MLV) UNDER WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME RELATED TO JAL JEEVAN MISSION (JJM) | SM/12280 | Support-WQMSP | Continuation work order for Annual Maintenance for Mobile Laboratory Van (MLV) under Water Quality Monitoring and Surveillance Programme related to Jal Jeevan Mission in the District of South 24 Parganas under Alipore Division, PHE Dte. (Period from 11.10.2023 to 10.01.2024) [03 months]. |  |  | ORD/001383/2023-2024 | 3341/AD | 09/10/2023 | 09/01/2024 | SUNANDA ENVIRONMENTAL INTERNATIONAL PVT. LTD. | 5.37 | 4.33 | 80.58 | 85
4 | SOUTH 24 PARGANAS |  | Alipore Division | REGULAR UPKEEP OF MOBILE LABORATORY VAN (MLV) UNDER WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME RELATED TO JAL JEEVAN MISSION (JJM) | SM/12280 | Support-WQMSP | Continuation work order for Annual Maintenance for Mobile Laboratory Van (MLV) under Water Quality Monitoring and Surveillance Programme related to Jal Jeevan Mission in the District of South 24 Parganas under Alipore Division, PHE Dte. (Period from 11.10.2024 to 10.01.2025) [03 months]. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/002591/2024-2025 | 4164/AD | 10/10/2024 | 10/01/2025 | SUNANDA ENVIRONMENTAL INTERNATIONAL PVT. LTD. | 5.37 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | REGULAR UPKEEP OF MOBILE LABORATORY VAN (MLV) UNDER WATER QUALITY MONITORING & SURVEILLANCE PROGRAMME RELATED TO JAL JEEVAN MISSION (JJM) | SM/12280 | Support-WQMSP | Continuation work order for Annual Maintenance for Mobile Laboratory Van (MLV) under Water Quality Monitoring and Surveillance Programme related to Jal Jeevan Mission in the District of South 24 Parganas under Alipore Division, PHE Dte. (Period from 11.07.2024 to 10.10.2024) [03 months]. | Assistant Engineer, RWS | Junior Engineer,RWS | ORD/002455/2024-2025 | 2926/AD | 10/07/2024 | 10/10/2024 | SUNANDA ENVIRONMENTAL INTERNATIONAL PVT. LTD. | 5.37 | 0 | 0 | 100
Total | [13 empty] | 44.01 | 27.31 | 62.05