## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( SURYANAGAR (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000496/2022-2023 | 4189/AD | 22/08/2022 | 06/10/2022 | LEMNISCATE | 9.6 | 9.6 | 100 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-C) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_1, Kakdwip Sub Division | ORD/000570/2022-2023 | 5710/AD | 13/10/2022 | 12/12/2022 | R.S.CONSTRUCTION CO. | 63.91 | 48.16 | 75.36 | 0
3 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I&II for Augmentation of Suryanagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/000374/2022-2023 | 3778/SMD | 29/12/2022 | 29/03/2023 | M/S. S.S. ENTERPRISE | 21.52 | 19.61 | 91.16 | 75
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000571/2022-2023 | .5711/AD | 13/10/2022 | 12/11/2022 | TOJO ENTERPRISE | 10.65 | 10.53 | 98.85 | 95
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Suryanagar (Zone-I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/000470/2022-2023 | 5089/AD | 20/09/2022 | 04/11/2022 | NIRMAN CONSTRUCTION | 36.67 | 32.97 | 89.91 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Suryanagar (Zone-I & II) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000908/2023-2024 | 267(I)/KSD | 10/07/2023 | 14/07/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000460/2023-2024 | 4723/AD | 18/12/2023 | 18/12/2023 | Resource Division | 30.66 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000272/2023-2024 | 3071/AD | 28/09/2023 | 28/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Payment of electric bills for new service connection under SMD, PHE Dte. |  |  | BILL/01562/2022-2023 | BP-2022-23-450 | 20/03/2023 | 20/03/2023 | WBSEDCL | 1.42 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-A) [No. of FHTC = 100] | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_1, Kakdwip Sub Division | ORD/000913/2022-2023 | 7412/AD | 25/11/2022 | 23/02/2023 | M/S RAJKUMAR KHAN | 119.67 | 76.8 | 64.17 | 80
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_1, Kakdwip Sub Division | ORD/000577/2022-2023 | 5715/AD | 13/10/2022 | 12/12/2022 | SARADA CONSTRUCTION | 89.01 | 78.51 | 88.2 | 60
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.06.2024 to 31.08.2024 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000669/2024-2025 | 983/KSD | 27/05/2024 | 27/08/2024 | ANAMIKA BERA | 1.2 | 1.15 | 95.89 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Augmentation of Suryanagar Zone - II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-B) (SM/12572) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000209/2024-2025 | 2592/AD | 19/06/2024 | 03/08/2024 | MAA BHABANI CONSTRUCTION (DUM DUM) | 42.65 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Suryanagar (Zone - I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) (SM/12572) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000214/2024-2025 | 2597/AD | 19/06/2024 | 19/07/2024 | JOY ENGINEERING & CONSTRUCTION | 9.66 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Zone-I & II PH No-2 of Suryanagar Augmentation W/S Scheme under JJM south 24 Pgs Mechanical Division PHE Dte [Block - Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/002392/2023-2024 | 842-AE-I-SMD | 31/07/2023 | 15/08/2023 | M/S. S.S. ENTERPRISE | 0.89 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Zone-I & II PH No-1 of Suryanagar Augmentation W/S Scheme under JJM south 24 Pgs Mechanical Division PHE Dte [Block - Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/002271/2023-2024 | 841-AE-I-SMD | 31/07/2023 | 15/08/2023 | M/S. S.S. ENTERPRISE | 0.89 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Suryanagar (Zone - I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) (SM/12572) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000213/2024-2025 | 2596/AD | 19/06/2024 | 03/08/2024 | M/S. SUNITY ENTERPRISE | 28.44 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-E) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_1, Kakdwip Sub Division | ORD/000572/2022-2023 | 5712/AD | 13/10/2022 | 03/11/2022 | THE TOWER CONSTRUCTION | 7.9 | 7.87 | 99.65 | 100
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | aying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-D) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_1, Kakdwip Sub Division | ORD/000576/2022-2023 | 5714/AD | 13/10/2022 | 12/11/2022 | M/S. L.P. CONSTRUCTION | 16.87 | 15.71 | 93.11 | 80
20 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-C) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_1, Kakdwip Sub Division | ORD/000578/2022-2023 | 5716/AD | 13/10/2022 | 12/11/2022 | M/S BANERJEE ENGINEERING SYSTEM | 16.66 | 15.11 | 90.71 | 100
21 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Allied works for pile and pile cap portion regarding the construction of 600 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Suryanagar Zone - I & II W/S Scheme, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_1, Kakdwip Sub Division | ORD/000590/2023-2024 | 2347/AD | 18/08/2023 | 02/10/2023 | KAMIRUL SK AND CO. | 60.02 | 57.88 | 96.43 | 100
22 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Support services for preparation of documentation in relating to submission to other Department i.e. PWD (NH) for approval of laying rising main and distribution main along / across NH 117 from Nischintapur to Bakkhali for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001997/2023-2024 | 470/KSD | 22/09/2023 | 22/10/2023 | ROY CHOWDHURY ASSOCIATES | 3.14 | 3.14 | 100.03 | 100
23 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Making and fixing of permanent display board at headwork site of Ramratanpur, Suryanagar Zone - I & II, Ganeshpur Left Out area PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002147/2023-2024 | 946/KSD | 19/12/2023 | 24/12/2023 | ANANTA KUMAR GIRI | 0.63 | 0.31 | 49.99 | 100
24 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Supply & installation of LED board at Zone-I & II PH-1&2 of Suryanagar Aug. W/S Scheme under South 24-Pgs Mechanical Division PHE Dte.(Block-Kakdwip) |  |  | ORD/001655/2023-2024 | .1031/AE-I/SMD | 20/09/2023 | 05/10/2023 | MAA SUSOMA & COMPANY | 0.78 | 0.78 | 100 | 100
25 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000810/2023-2024 | 655/AD | 30/01/2024 | 30/01/2024 | Resource Division | 17.57 | 0 | 0 | 0
26 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000591/2023-2024 | 90/AD | 03/01/2024 | 03/01/2024 | Resource Division | 5.94 | 0 | 0 | 0
27 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000997/2023-2024 | 1790/AD | 27/03/2024 | 27/03/2024 | Resource Division | 25.73 | 0 | 0 | 0
28 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Construction of 1 no. 550 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001319/2022-2023 | 9884/AD | 10/01/2023 | 04/08/2025 | KAMIRUL SK AND CO. | 319.24 | 129.3 | 40.5 | 40
29 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connection etc. for Augmentation of Suryanagar Zone- I W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/12572) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000496/2024-2025 | 3580/AD | 05/09/2024 | 02/05/2025 | M/S RAJKUMAR KHAN | 82.06 | 0 | 0 | 40
30 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Augmentation of Suryanagar Zone - II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/12572) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000208/2024-2025 | 2591/AD | 19/06/2024 | 28/12/2025 | SARADA CONSTRUCTION | 52.8 | 0 | 0 | 30
31 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.09.2024 to 30.11.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000670/2024-2025 | 1256/KSD | 28/08/2024 | 27/11/2024 | ANAMIKA BERA | 1.2 | 1.1 | 92 | 0
32 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connection etc. for Augmentation of Suryanagar Zone- I W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part- B) (SM/12572) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000207/2024-2025 | 2590/AD | 19/06/2024 | 22/02/2025 | ANANTA KUMAR GIRI | 25.16 | 0 | 0 | 30
33 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2025 to 31.05.2025 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/003035/2024-2025 | 352/KSD | 27/02/2025 | 30/05/2025 | ANAMIKA BERA | 1.2 | 0.73 | 60.82 | 0
34 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SURYANAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12572 | Augmentation | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.12.2024 to 28.02.2025. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002847/2024-2025 | 1656/KSD | 26/11/2024 | 24/02/2025 | ANAMIKA BERA | 1.2 | 1.13 | 94.38 | 0
Total | [13 empty] | 1105.72 | 510.89 | 46.2