## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Canning-II | Alipore Division | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of PAR KALUGACHHI village of Deuli-I Gram Panchayet in Canning-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.5 km distribution syst | SM/12574 | New | Sinking of 150 X 100 mm dia. X 300 Mtr. Depth Rig bored Tube wells, Construction of Switch Room (3750 X 3750), boundary fencing, MS grill type gate,, Pipe connections, Laying of delivery main & Laying of Distribution System, Providing Functional Household Tap Connection, Supplying and installation PVC storage tank etc. of Ground Water Based Mini Piped Water Supply Scheme for the Par Kalugachi having village with maximum 82 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000749/2022-2023 | 6410/AD | 10/11/2022 | 09/01/2023 | GANGA TUBEWELL AND HARDWARE | 34.64 | 25.66 | 74.06 | 86
2 | SOUTH 24 PARGANAS | Canning-II | S24 Pgns Mechanical | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of PAR KALUGACHHI village of Deuli-I Gram Panchayet in Canning-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.5 km distribution syst | SM/12574 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00625/2023-2024 | BP-2023-24-91 | 14/06/2023 | 14/06/2023 | WBSEDCL | 2.89 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Canning-II | S24 Pgns Mechanical | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of PAR KALUGACHHI village of Deuli-I Gram Panchayet in Canning-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.5 km distribution syst | SM/12574 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Parkalugachi water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000522/2022-2023 | 391/SMD | 15/02/2023 | 16/05/2023 | KARUNAMOY ENGINEERING | 9.25 | 8.38 | 90.53 | 100
Total | [13 empty] | 46.79 | 34.03 | 72.74