## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARAGANAS | Canning - II | S24 Pgns Mechanical | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of KULER KHOJ village of Tambuldaha-II Gram Panchayet in Canning-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution sy | SM/12576 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Kuler Khoj water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000520/2022-2023 | 379/SMD | 15/02/2023 | 16/05/2023 | KARUNAMOY ENGINEERING | 9.25 | 0 | 0 | 0
2 | SOUTH 24 PARAGANAS | Canning - II | Alipore Division | Ground Water Based Mini Piped Water Supply Scheme (maximum 100 nos. households) of KULER KHOJ village of Tambuldaha-II Gram Panchayet in Canning-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 15000 Lit, 1.2 km distribution sy | SM/12576 | New | Sinking of 150 X 100 mm dia. X 300 Mtr. Depth Rig bored Tube wells, Construction of Switch Room (3750 X 3750), Pipe connections, Laying of delivery main & Laying of Distribution System, Providing Functional Household Tap Connection, &Supplying and installation PVC storage tank etc. of Ground Water Based Mini Piped Water Supply Scheme for the Kuler Khonj having village with maximum 85 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000766/2022-2023 | 6495/AD | 11/11/2022 | 10/01/2023 | SURYA ENTERPRISE | 33.84 | 13.08 | 38.64 | 88
Total | [13 empty] | 43.1 | 13.08 | 30.34