## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Diamond Harbour-II | Alipore Division | Ground Water Based Mini Piped Water Supply Scheme (maximum 50 nos. households) of KALIKAMERYA village of Sarisha Gram Panchayet in Diamond Harbour-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 7500 Lit, 1.2 km distribution s | SM/12577 | New | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the KALIKAMERYA having village with maximum 34 nos. households, Block - Diamond Harbour -II under Diamond Harbour Sub Division of Alipore Division, PHE Dte, | Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD,Junior Engineer 3 DHSD | ORD/001124/2022-2023 | 8768/AD | 21/12/2022 | 05/12/2025 | S.S. ENTERPRISE (II) | 26.74 | 0 | 0 | 30
2 | SOUTH 24 PARGANAS | Diamond Harbour-II | S24 Pgns Mechanical | Ground Water Based Mini Piped Water Supply Scheme (maximum 50 nos. households) of KALIKAMERYA village of Sarisha Gram Panchayet in Diamond Harbour-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 7500 Lit, 1.2 km distribution s | SM/12577 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Kalikamerya water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Diamond Harbour-II] | Assistant Engineer -II | Junior Engineer | ORD/000546/2022-2023 | 409/SMD | 16/02/2023 | 17/05/2023 | P.K. ENTERPRISE | 9.25 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Diamond Harbour-II | Alipore Division | Ground Water Based Mini Piped Water Supply Scheme (maximum 50 nos. households) of KALIKAMERYA village of Sarisha Gram Panchayet in Diamond Harbour-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 7500 Lit, 1.2 km distribution s | SM/12577 | New | Material Requisition To Resource Division |  |  | RTOR000885/2023-2024 | 759/AD | 03/02/2024 | 03/02/2024 | Resource Division | 0.21 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Diamond Harbour-II | S24 Pgns Mechanical | Ground Water Based Mini Piped Water Supply Scheme (maximum 50 nos. households) of KALIKAMERYA village of Sarisha Gram Panchayet in Diamond Harbour-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 7500 Lit, 1.2 km distribution s | SM/12577 | New | Payment for new power connection at Kalikamerya PH- I (JL 16, Plot 216/601) under Diamond Harbour- II Block, Dist.- South 24 Pgs. Application No.- 1007639138 Ref. ID- 106542411 |  |  | BILL/00380/2024-2025 |  | 30/05/2024 | 30/05/2024 | WBSEDCL | 7.63 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS | Diamond Harbour-II | S24 Pgns Mechanical | Ground Water Based Mini Piped Water Supply Scheme (maximum 50 nos. households) of KALIKAMERYA village of Sarisha Gram Panchayet in Diamond Harbour-II Block considering 1 no Tubewell (150 mm x 100 mm x 300 m depth), PVC Tank 7500 Lit, 1.2 km distribution s | SM/12577 | New | Quotation payment for new connection at pump house No.-I under Kalikamerya water supply Scheme, South 24 Parganas Mechanical Division, PHE Dte. ( Block- Diamond Harbour-II) Memo No. 1007923539/Quot/03, Dt. 12/07/2024 Ref. ID: 106665830 [ SM/12577 ] |  |  | BILL/01409/2024-2025 | BP-2024-25-328 | 31/08/2024 | 31/08/2024 | WBSEDCL | 2.71 | 0 | 0 | 0
Total | [13 empty] | 46.53 | 0 | 0