## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( BAMANAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000495/2022-2023 | 4193/AD | 22/08/2022 | 06/10/2022 | LEMNISCATE | 5.14 | 0 | 0 | 100
2 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Bamanagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000338/2022-2023 | 5707/AD. | 13/10/2022 | 12/11/2022 | R CONSTRUCTION | 13.63 | 0 | 0 | 70
3 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Bamanagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000049/2023-2024 | 34/KSD | 24/04/2023 | 28/04/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Bamanagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000471/2022-2023 | 5202/AD | 22/09/2022 | 06/11/2022 | AQUATECH ENGINEER | 37.06 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Material Requisition To Resource Division |  |  | RTOR000120/2023-2024 | 656/AD | 17/05/2023 | 17/05/2023 | Resource Division | 11.61 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Material Requisition To Resource Division |  |  | RTOR000443/2023-2024 | 4710/AD | 18/12/2023 | 18/12/2023 | Resource Division | 9.1 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00022/2023-2024 | BP-2023-24-06 | 25/04/2023 | 25/04/2023 | WBSEDCL | 1.09 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Payment of electric bills for new service connection under SMD, PHE Dte. |  |  | BILL/01561/2022-2023 | BP-2022-23-449 | 20/03/2023 | 20/03/2023 | WBSEDCL | 1.42 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Bamanagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001156/2023-2024 | 3719/AD | 03/11/2023 | 18/12/2023 | G.M. ENTERPRISE | 27.73 | 0 | 0 | 70
10 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Bamanagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000575/2022-2023 | 5713/AD | 13/10/2022 | 03/11/2022 | M/S SAKTI GIRI ENTERPRISE | 9.89 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Bamanagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001157/2023-2024 | 3720/AD | 03/11/2023 | 03/12/2023 | SUKUMAR HALDAR | 9.57 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Bamanagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000541/2022-2023 | 5708/AD. | 13/10/2022 | 12/11/2022 | SUMAN ENTERPRISE | 11.89 | 0 | 0 | 60
13 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Making and fixing of permanent display board at headwork site of Taktipur Abad Zone - I & II, Chandipur, Bamanagar, Gangadharpur Zone - I &II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002141/2023-2024 | 941/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.94 | 0 | 0 | 100
14 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Material Requisition To Resource Division |  |  | RTOR000992/2023-2024 | 1785/AD | 27/03/2024 | 27/03/2024 | Resource Division | 32.17 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Material Requisition To Resource Division |  |  | RTOR000811/2023-2024 | 656/AD | 30/01/2024 | 30/01/2024 | Resource Division | 2.08 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Bamanagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000552/2022-2023 | 5726/AD | 13/10/2022 | 01/04/2025 | GARGO TRADERS | 434.79 | 0 | 0 | 80
17 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Improvement of outdoor illumination arrangement with allied works at Zone-I PH-2 of Bamanagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] [SM/12733] | Assistant Engineer -II | Junior Engineer | ORD/001797/2024-2025 | 1054-AE-II-SMD | 20/08/2024 | 04/09/2024 | KUNDU ELECTRICAL ENTERPRISE | 0.9 | 0 | 0 | 100
18 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I of Bamanagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000429/2022-2023 | 3825/SMD | 29/12/2022 | 30/06/2025 | KUNDU ELECTRICAL ENTERPRISE | 21.88 | 0 | 0 | 90
19 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED BAMANAGAR PIPE WATER SUPPLY SCHEME UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/12733 | New | Allied works for pile and pile cap portion regarding the construction of 350 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile & pile cap upto pedestal at Bamanagar, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000269/2023-2024 | 1419/AD | 13/07/2023 | 01/10/2024 | GARGO TRADERS | 43.4 | 0 | 0 | 70
Total | [13 empty] | 674.77 | 0 | 0