## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT | SM/13072 | Augmentation | Laying damaged pipe line from PH-1 to Sadanandar More and Hatberia More to House of Chandika Show at Deuli Water Supply Scheme (Zone-II), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000105/2021-2022 | 1189/AD | 07/07/2021 | 21/08/2021 | M/S S AND P CONSTRUCTION | 38.01 | 27.58 | 72.55 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT | SM/13072 | Augmentation | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Deuli & Adjoining Mouzas (Kaluakhali & Mukhajyapara) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001119/2022-2023 | 8848/AD | 22/12/2022 | 05/02/2023 | BHATTACHARJEE & CO. | 39.02 | 34.58 | 88.6 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT | SM/13072 | Augmentation | Laying pipe line for uncovered habitation of Ground Water Based Augmentation Piped Water Supply Scheme for Deuli and Adjoining Mouzas (Kaluakhali, Mukhajyapara), Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000543/2024-2025 | 3714/AD | 12/09/2024 | 12/10/2024 | AHANA ENTERPRISE | 8.09 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT | SM/13072 | Augmentation | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Deuli & Adjoining Mouzas (Kaluakhali & Mukhajyapara) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001760/2022-2023 | 11942/AD | 24/02/2023 | 10/04/2023 | M/S SEIKH ENTERPRISE | 7.34 | 7.02 | 95.65 | 95
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT | SM/13072 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Deuli & Adjoining Mouzas (Kaluakhali & Mukhajyapara) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001761/2022-2023 | 11943/AD | 24/02/2023 | 10/04/2023 | M/S SEIKH ENTERPRISE | 7.08 | 6.64 | 93.77 | 85
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT | SM/13072 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Deuli & adjoining Mouzas (Kaluakhali & Mukhajyapara Mouza) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001943/2022-2023 | 5608/AD | 29/09/2022 | 13/11/2022 | M/S APEX ENGINEERING | 2.61 | 2.61 | 100 | 80
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT | SM/13072 | Augmentation | Laying pipeline at Head Work Site for washed of OHR and parallel line of Augmentation of Deuli (Zone - I) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001027/2023-2024 | 1338/AD | 05/03/2024 | 14/04/2024 | NARAYAN ENTERPRISE | 5.91 | 5.45 | 92.21 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT | SM/13072 | Augmentation | Road restoration work for the road damage due to laying of pipe line on Augmentation & Retrofitting of Deuli (Zone-I & II) PWSS, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [ at Deuli (Zone-I) ] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001632/2023-2024 | 1139/CSD | 31/10/2023 | 30/11/2023 | SUKANTA HALDER | 3.06 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT | SM/13072 | Augmentation | Supply & installation of LED board at P.H. No-1 & 2 of Deuli & Adjoining water supply scheme under South 24-Pgs Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 930/SMSD | 28/06/2024 | 13/07/2024 | WIZARDTECH SOLUTION | 0.78 | 0.78 | 100 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT | SM/13072 | Augmentation | Renovation of Pump House no. - 1 of Augmentation of Deuli (Zone - I & II) W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-I) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002458/2023-2024 | 1588/CSD | 23/02/2024 | 24/03/2024 | SUKANTA HALDER | 1.59 | 0 | 0 | 100
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT | SM/13072 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Kaluakhali Mukherjee Para, PH-1, under Canning-II Block water supply sche under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002773/2023-2024 | 140/SMSD | 05/02/2024 | 20/02/2024 | CHANDIMATA ELECTRICALS | 0.88 | 0.88 | 100 | 100
12 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT | SM/13072 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04083/2023-2024 | BP-2023-24-421 | 16/12/2023 | 16/12/2023 | WBSEDCL | 24.65 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT | SM/13072 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Deuli & Adjoining Mouza water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000523/2022-2023 | 392/SMD | 15/02/2023 | 02/08/2025 | CHANDIMATA ELECTRICALS | 21.52 | 20.22 | 93.97 | 100
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT | SM/13072 | Augmentation | Laying of Distribution System, Providing Functional Household Tap Connection (FHTC) etc. of Ground Water Based Augmentation Piped Water Supply Scheme for Deuli & Adjoining Mouzas (Kaluakhali & Mukhajyapara) Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 997] (TSM/014717) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000020/2023-2024 | 91/AD | 11/04/2023 | 19/03/2025 | MODERN CONSTRUCTION | 164.78 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT | SM/13072 | Augmentation | Bamboo pile walling for protection of pipe line for Ground Water Based of Augmentation Piped Water Supply Scheme for Deuli & Adjoining Mouzas (Kaluakhali, Mukhajyapara), Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000751/2024-2025 | 4425/AD | 05/11/2024 | 04/05/2025 | AHANA ENTERPRISE | 30.06 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DEULI & ADJOINING MOUZAS (KALUAKHALI & MUKHAJYAPARA MOUZA) IN BLOCK CANNING-II UNDER ALIPORE DIVISION, PHE DTE. IN SOUTH 24 PARGANAS DISTRICT | SM/13072 | Augmentation | Renovation of Pump House no. - 2 of Augmentation of Deuli (Zone - I & II) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-II) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002501/2023-2024 | 1598/CSD | 28/02/2024 | 29/03/2024 | NAZRUL ENTERPRISE | 2 | 0 | 0 | 100
Total | [13 empty] | 357.41 | 105.76 | 29.59