## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Sinking of 3 (three) Nos. 300mm x 200mm dia. 360 mtr. deep Tubewell by D.R. Rig method using PVC Pipe & Pre-packed Resin Bonded Gravel at 3 different Tubewell Sites for Augmentation of Canning Water Supply Scheme (Zone - II), Block - Canning - I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001436/2021-2022 | 6245/AD | 23/02/2022 | 24/04/2022 | SNEHA CONSTRUCTION | 63.19 | 38.07 | 60.24 | 70
2 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Sinking of 3 (three) Nos. 300mm x 200mm dia. 360 mtr. deep Tubewell by D.R. Rig method using PVC Pipe & Pre-packed Resin Bonded Gravel at 3 different Tubewell Sites for Augmentation of Canning Water Supply Scheme (Zone - III), Block - Canning - I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001440/2021-2022 | 6246/AD | 23/02/2022 | 24/04/2022 | BHATTACHARJEE AND CO. | 63.16 | 54.81 | 86.77 | 66
3 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Laying distribution system for piped Water Supply Scheme for Augmentation of Canning PWSS Zone-I Block Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000066/2022-2023 | 5806/AD | 17/10/2022 | 21/11/2026 | MAA LAXMI ENTERPRISE | 195.19 | 113.17 | 57.98 | 70
4 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - I, Part -A) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000069/2022-2023 | 5809/AD | 17/10/2022 | 02/07/2026 | MAA LAXMI ENTERPRISE | 39.63 | 24.73 | 62.39 | 72
5 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-II), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000211/2022-2023 | 2998/AD | 11/07/2022 | 10/08/2022 | M/S P. B. CONSTRUCTION | 6.76 | 5.94 | 87.76 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-III), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. II] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000213/2022-2023 | 3000/AD | 11/07/2022 | 10/08/2022 | SUKALPA NIRMAN | 6.77 | 5.64 | 83.39 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-III), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000214/2022-2023 | 3001/AD | 11/07/2022 | 10/08/2022 | M/S. ASIRUDDIN SEKH ENTERPRISE | 6.73 | 5.65 | 83.87 | 0
8 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-II), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. - I] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000210/2022-2023 | 2997/AD | 11/07/2022 | 10/08/2022 | M/S P. B. CONSTRUCTION | 6.98 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Laying distribution system for piped Water Supply Scheme for Augumentation of Canning PWSS Zone-II Block Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000556/2022-2023 | 5807/AD | 17/10/2022 | 03/02/2025 | AVIK ENTERPRISE | 232.69 | 167.38 | 71.93 | 80
10 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Laying distribution system for piped Water Supply Scheme for Augumentation of Canning PWSS Zone-III Block Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000557/2022-2023 | 5808/AD | 17/10/2022 | 14/02/2023 | K.P. CONSTRUCTION | 268.06 | 232.53 | 86.74 | 94
11 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - I, Part -B) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000558/2022-2023 | 5810/AD | 17/10/2022 | 02/07/2026 | MAA LAXMI ENTERPRISE | 69.38 | 0 | 0 | 72
12 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II, Part - A) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000562/2022-2023 | 5812/AD | 17/10/2022 | 16/10/2026 | AVIK ENTERPRISE | 59.17 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - III, Part - A) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000565/2022-2023 | 5815/AD | 17/10/2022 | 17/10/2023 | K.P. CONSTRUCTION | 83.63 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II, Part - B) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000563/2022-2023 | 5813/AD | 17/10/2022 | 16/10/2026 | AVIK ENTERPRISE | 55.75 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II, Part - C) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000564/2022-2023 | 5814/AD | 17/10/2022 | 16/10/2026 | AVIK ENTERPRISE | 49.11 | 0 | 0 | 96
16 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone ¿ III, Part ¿ B) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000573/2022-2023 | 5816/AD | 17/10/2022 | 31/03/2025 | K.P. CONSTRUCTION | 50.57 | 0 | 0 | 85
17 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone ¿ III, Part ¿ C) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000574/2022-2023 | 5817/AD | 17/10/2022 | 17/10/2023 | K.P. CONSTRUCTION | 61.49 | 60.01 | 97.6 | 98
18 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - I, Part -C) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000560/2022-2023 | 5811/AD | 17/10/2022 | 17/10/2023 | MAA LAXMI ENTERPRISE | 56.93 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. - I] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000207/2022-2023 | 2994/AD | 11/07/2022 | 10/08/2022 | SWASTIK CONSTRUCTION | 7 | 6.71 | 95.76 | 98
20 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000209/2022-2023 | 2996/AD | 11/07/2022 | 10/08/2022 | SWASTIK CONSTRUCTION | 6.78 | 6.07 | 89.46 | 98
21 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. II] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000208/2022-2023 | 2995/AD | 11/07/2022 | 10/08/2022 | SWASTIK CONSTRUCTION | 6.78 | 6.7 | 98.83 | 98
22 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Construction of 1 (one) no. switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-III), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. - I] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000212/2022-2023 | 2999/AD | 11/07/2022 | 10/08/2022 | SUKALPA NIRMAN | 6.99 | 6.77 | 96.84 | 95
23 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Earth work in filling between proposed Head Work Site and PWD Road at Canning W/S Scheme (Zone-II), Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001379/2022-2023 | 1061/CSD | 14/12/2022 | 03/01/2023 | SNEHA CONSTRUCTION | 0.56 | 0.56 | 99.47 | 100
24 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Sinking of 3 (three) Nos. 300mm x 200mm dia. 360 mtr. deep Tubewell by D.R. Rig method using PVC Pipe & Pre-packed Resin Bonded Gravel at 3 different Tubewell Sites for Augmentation of Canning Water Supply Scheme (Zone - I), Block - Canning - I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002413/2022-2023 | 5673/AD | 11/10/2022 | 10/12/2022 | AQUATECH ENGINEERS | 71.43 | 59.66 | 83.52 | 90
25 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Supply, Installation and commissioning of submersible pumping machinery along with allied accessories for Augmentation of Canning Zone-1, Zone-2 & Zone-3 water supply scheme under South 24 Pgs Mechanical Division PHE Dte. [Block:- Canning-I] | Assistant Engineer | Junior Engineer | ORD/000073/2023-2024 | 1010//SMD | 11/04/2023 | 11/04/2024 | M/S. S.S. ENTERPRISE | 113.4 | 84.9 | 74.87 | 70
26 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Canning W/S Scheme (Zone-I, II & III), Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (at Zone-III) (SM/13116) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001023/2023-2024 | 3308/AD | 07/10/2023 | 01/03/2025 | K.P. CONSTRUCTION | 17.47 | 0 | 0 | 95
27 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Dismantling of existing concrete road and restoration the same (Bahirsona and Kumarsha Chak Part) after laying pipe line at Augmentation of Canning Water Supply Scheme (Zone- I, II & III), Block- Canning- I under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-II) (SM/13116) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001020/2023-2024 | 3305/AD | 07/10/2023 | 30/03/2025 | AVIK ENTERPRISE | 34.3 | 0 | 0 | 0
28 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Canning W/S Scheme (Zone-I, II & III), Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (at Zone-II) (SM/13116 ) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000988/2023-2024 | 3300/AD | 07/10/2023 | 06/11/2023 | MMS CONSTRUCTIONS PVT. LTD. | 14.05 | 11.21 | 79.76 | 100
29 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Laying pipe line, construction of sluice valve chamber and other works at Canning W/S Scheme (Zone - I, II & III), Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000413/2023-2024 | 772/CSD | 02/08/2023 | 01/09/2023 | JHARNA ENTERPRISE | 2.23 | 2.21 | 99.22 | 98
30 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Supply & installation of LED board at Zone-III, PH-2&3 of Canning w/s scheme under South 24-Pgs Mechanical Division PHE Dte. [Block:Canning-I] |  |  | ORD/000892/2023-2024 | 1O64/SMSD | 10/08/2023 | 20/08/2023 | M/S. PS & ASSOCIATES | 0.78 | 0.78 | 100 | 100
31 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Extension of column pipe of Canning Zone-I TW-1&2 and Zone-2 TW-1, Daria TW-2 w/s scheme under SMD PHE Dte. |  |  | ORD/002287/2022-2023 | 135/SMSD | 24/02/2023 | 11/03/2023 | ROY & BISWAS ENGG. CO. | 0.98 | 0.96 | 98.07 | 100
32 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Inter connection and rising main with supply of specials of Augmentation of Canning W/S Scheme (Zone-I, II & III), Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (at Zone-I) (SM/13116) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001022/2023-2024 | 3307/AD | 07/10/2023 | 04/01/2025 | SARKAR ENTERPRISE | 15.95 | 0 | 0 | 98
33 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Dismantling work of Plain Cement Concrete Road and restoration work up to laying distribution work for Canning (Zone-I, II & III) W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (SM/13116) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001019/2023-2024 | 3304/AD | 07/10/2023 | 20/01/2024 | MAA LAXMI ENTERPRISE | 38.83 | 34.94 | 89.98 | 95
34 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Laying pipe line, construction of sluice valve chamber and other works at Canning W/S Scheme (Zone - I, II & III), Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001408/2023-2024 | 1147/CSD | 01/11/2023 | 01/12/2023 | JHARNA ENTERPRISE | 2.84 | 2.55 | 89.6 | 100
35 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Payment of Electric Bill for new service connection under SMD PHE Dte. |  |  | BILL/00284/2023-2024 | BP-2023-24-18 | 15/05/2023 | 15/05/2023 | WBSEDCL | 24.12 | 0 | 0 | 0
36 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01885/2023-2024 | BP-2023-24-224 | 23/08/2023 | 23/08/2023 | WBSEDCL | 9.33 | 0 | 0 | 0
37 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04231/2023-2024 | BP-2023-24-437 | 28/12/2023 | 28/12/2023 | WBSEDCL | 4.79 | 0 | 0 | 0
38 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Additional Laying of pipe line to connect the balance area of Augmentation of Canning W/S Scheme (Zone-I, II & III), Block - Canning-I, under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Zone-III) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000278/2024-2025 | 2832/AD | 04/07/2024 | 31/03/2025 | K.P. CONSTRUCTION | 75.69 | 20.53 | 27.12 | 80
39 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Laying pipe line to connect the uncovered habitation and protection work at Augmentation of Canning (Zone- I, II & III) W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000355/2024-2025 | 2827/AD | 04/07/2024 | 26/12/2025 | AVIK ENTERPRISE | 141.64 | 0 | 0 | 45
40 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Construction of 700 m³ capacity R.C.C OHR (based on Departmental Design & Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Ground Water Based Augmentation Piped Water Supply Scheme of Canning (Zone-I, II & III) of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. (Zone - I) [SM/13116] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000841/2024-2025 | 4576/AD | 15/11/2024 | 12/08/2025 | JYOTY SOLAR POWER | 220.03 | 0 | 0 | 0
41 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Augmentation of Canning Zone-I PH-3 water supply sche under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000645/2024-2025 | 1023/SMSD | 15/07/2024 | 30/07/2024 | M/S. S.S. ENTERPRISE | 0.88 | 0 | 0 | 0
42 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 4 of Dakshin Redokhali water supply scheme Adjacent to Aug. of Canning W/S Sche. under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer | Junior Engineer | ORD/000123/2024-2025 | 2291/SMD | 19/07/2024 | 17/10/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 10.82 | 0 | 0 | 100
43 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Construction of 900 m³ capacity R.C.C OHR (based on Departmental Design & Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Ground Water Based Augmentation Piped Water Supply Scheme of Canning (Zone-I, II & III) of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. (Zone - III) [SM/13116] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000842/2024-2025 | 4577/AD | 15/11/2024 | 12/08/2025 | K.P. CONSTRUCTION | 288.41 | 0 | 0 | 0
44 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Dismantling work of Plain Cement Concrete Road and restoration work (Canning Station areas) for laying distribution work of Augmentation of Canning Water Supply Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone-III) ( SM/13116) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000546/2024-2025 | 3717/AD | 12/09/2024 | 19/07/2026 | M.P. ENTERPRISE (II) | 41.04 | 4.72 | 11.5 | 98
45 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 4 of Dakshin Redokhali water supply scheme (Adjacent to Aug. of Canning W/S Sche.) under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-I] | Assistant Engineer | Junior Engineer | ORD/000240/2024-2025 | 2483/SMD | 05/08/2024 | 03/11/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 10.82 | 0 | 0 | 0
46 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Augmentation of Canning Zone-I PH-1 water supply sche under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000643/2024-2025 | 1026/SMSD | 15/07/2024 | 30/07/2024 | M/S. S.S. ENTERPRISE | 0.88 | 0 | 0 | 0
47 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Augmentation of Canning Zone-I PH-2 water supply sche under SMD,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000644/2024-2025 | 1025/SMSD | 15/07/2024 | 30/07/2024 | M/S. S.S. ENTERPRISE | 0.88 | 0 | 0 | 0
48 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing on Augmentation of Canning PWSS (Zone-I, II, and III) , Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Canning (Zone-II), Pump House No. - II) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001909/2023-2024 | 222/AD | 11/01/2024 | 07/10/2024 | M/S. BABA KAPIL MUNI ENTERPRISE | 6.54 | 0 | 0 | 100
49 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Supply & Installation of LED board at Zone-I, PH-3 of Canning (Aug) water supply scheme under South 24-Pgs Mechanical Division, PHE Dte.[SM/13116] | Assistant Engineer | Junior Engineer | ORD/000397/2024-2025 | 1225/SMSD | 30/08/2024 | 14/09/2024 | SEN ENTERPRISE | 0.39 | 0 | 0 | 100
50 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Construction of toilet including sanitary arrangement and other allied works at Canning Sub-Division Office of Canning (Zone-I, II & III) PWSS, under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001062/2024-2025 | 1293/CSD | 21/11/2024 | 20/01/2025 | D.R.CONSTRUCTION | 4.82 | 0 | 0 | 95
51 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Supply & installation of LED board at Zone-I, PH-1 & 2 of Canning (Aug) water supply scheme under South 24-Pgs Mechanical Division PHE Dte.[SM/13116] | Assistant Engineer | Junior Engineer | ORD/000384/2024-2025 | 1226/SMSD | 30/08/2024 | 14/09/2024 | SEN ENTERPRISE | 0.78 | 0 | 0 | 100
52 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Erection of display board at headwork site for various location under Canning Sub-Division of Alipore Division, PHE Dte. (South 24 Parganas) (Block Name :- Canning-I) Name of PWSS :- Budhkhali, Daria, Taldi, Dakshin Rendokhali, Moukhali, Banibadabelekhali, Uttar Angadberia, Canning (Zone-I), Canning (Zone-II), Canning (Zone-III), Adhia and Adhia (Part-B) [Kankradaha] (For 12 (Twelve) nos. Location) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD,Junior Engineer, 4 CSD,Junior Engineer,1 CSD | ORD/000964/2024-2025 | 1176/CSD | 24/10/2024 | 13/11/2024 | GANGA TUBEWELL AND HARDWARE | 2.89 | 0 | 0 | 100
53 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000731/2023-2024 | 554/AD | 25/01/2024 | 25/01/2024 | Resource Division | 226.04 | 0 | 0 | 0
54 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Restoration of Thunkati Canning Road South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division |  |  | BILL/01323/2024-2025 | BP-2024-25-622 | 27/09/2024 | 27/09/2024 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 8.73 | 0 | 0 | 0
55 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Quotation for new service(power) connection at Canning Zone-I PH-3 water supply scheme under Canning -I block PHE dte. (Application ID:-1007778243) (Ref ID:-106599139) |  |  | BILL/00396/2024-2025 | BP-2024-25-103 | 10/06/2024 | 10/06/2024 | WBSEDCL | 4.47 | 0 | 0 | 0
56 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Quotation for new service (Power) confection at Canning Zone-I PH-1 water supply scheme under Canning -I block Under SMD PHE dte. (Ref ID:-106606286) (App ID:-1007793891) |  |  | BILL/00398/2024-2025 | BP-2024-25-105 | 10/06/2024 | 10/06/2024 | WBSEDCL | 5.17 | 0 | 0 | 0
57 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Quotation for new service(power) connection Canning Zone-I ,PH-2 water supply scheme under Canning -I block under SMD PHE dte. (Ref ID:-106606285) (App ID:-1007793877) |  |  | BILL/00397/2024-2025 | BP-2024-25-104 | 10/06/2024 | 10/06/2024 | WBSEDCL | 3.95 | 0 | 0 | 0
58 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Construction of 700 m³ capacity R.C.C OHR (based on Departmental Design & Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Ground Water Based Augmentation Piped Water Supply Scheme of Canning (Zone-I, II & III) of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. (Zone - II) [SM/13116] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002853/2024-2025 | 1153/AD | 18/03/2025 | 13/12/2025 | RIVER BENZ CONSTRUCTION | 220.05 | 0 | 0 | 0
59 | SOUTH 24 PARGANAS |  | Alipore Division | Augmentation of Canning Water Supply Scheme. | SM/13116 | Augmentation | Laying of additional pipeline, road restoration works etc. under the Augmentation of Canning PWSS (Zone-I) W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001645/2026-2027 | 3712/AD | 03/08/2026 | 02/10/2026 | MAA LAXMI ENTERPRISE | 119.08 | 0 | 0 | 0
Total | [13 empty] | 3147.8 | 957.18 | 30.41