## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Bishnupur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000769/2022-2023 | 6524/AD | 11/11/2022 | 09/02/2023 | M/S. SARADA UDYOG | 104.36 | 103.88 | 99.54 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Bishnupur Zone-I PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000075/2023-2024 | 59/KSD | 02/05/2023 | 06/05/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Bishnupur Zone-II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000074/2023-2024 | 58/KSD | 02/05/2023 | 06/05/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Bishnupur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000772/2022-2023 | 6527/AD | 11/11/2022 | 11/12/2022 | M/S. PAPIYA ENTERPRISE | 6.89 | 6.7 | 97.28 | 98
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Bishnupur (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000770/2022-2023 | 6525/AD | 11/11/2022 | 26/12/2022 | SIMPLEX DRILLING CO. | 45.84 | 45.05 | 98.28 | 100
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Bishnupur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000771/2022-2023 | 6526/AD | 11/11/2022 | 11/12/2022 | SADHURHAT CO OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 13.02 | 12.93 | 99.37 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (BISHNUPUR (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001056/2022-2023 | 4647/AD | 06/09/2022 | 21/10/2022 | VOYAGER | 11.73 | 11.73 | 100 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000497/2023-2024 | 4823/AD | 20/12/2023 | 20/12/2023 | Resource Division | 83.64 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000328/2023-2024 | 3143/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00017/2023-2024 | BP-2023-24-35 | 18/05/2023 | 18/05/2023 | WBSEDCL | 5.39 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00379/2023-2024 | BP-2023-24-55 | 09/06/2023 | 09/06/2023 | WBSEDCL | 0.87 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Construction of 2 nos. 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 2 nos. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Bishnupur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000837/2022-2023 | 6845/AD | 17/11/2022 | 05/05/2025 | M/S. S.S. ENTERPRISE | 1002.71 | 663.22 | 66.14 | 67
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Allied works for pile and pile cap portion regarding the Construction of 2 nos. 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Augmentation of Bishnupur (Zone-I & II) W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000621/2023-2024 | 2431/AD | 22/08/2023 | 21/10/2023 | M/S. S.S. ENTERPRISE | 119.53 | 47.59 | 39.82 | 50
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, Zone-I & II for Augmentation of Bishnupur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Sagar] | Assistant Engineer -I | Junior Engineer | ORD/000342/2022-2023 | 3746/SMD | 29/12/2022 | 29/03/2023 | SIPRA ENTERPRISE | 23.13 | 22.29 | 96.34 | 80
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Supplying, fitting, fixing and delivery of different dia. specials for Augmentation of Bishnupur (Zone-I and II) W/S Scheme under JJM, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001418/2023-2024 | 4598/AD | 14/12/2023 | 13/01/2024 | M/S. S.S. ENTERPRISE | 12.53 | 12.52 | 99.96 | 100
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Bishnupur (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002173/2023-2024 | 811/AD | 05/02/2024 | 21/03/2024 | M/S SUNITY ENTERPRISE | 33.71 | 30.96 | 91.84 | 100
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Bishnupur (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002174/2023-2024 | 812/AD | 05/02/2024 | 06/03/2024 | M/S SWAPAN KUMAR PRADHAN | 11.77 | 10.12 | 85.96 | 100
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Making and fixing of permanent display board at headwork site of Bishnupur Zone - I & II, Gangasagar Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002150/2023-2024 | 947/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.81 | 0.4 | 49.99 | 100
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Construction of Household Tap Platform etc. at different households for Augmentation of Bishnupur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone- I & II) (SM/13117) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000337/2024-2025 | 2751/AD | 27/06/2024 | 11/08/2024 | M/S. S.S. ENTERPRISE | 109.19 | 0 | 0 | 100
20 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Supply & installation of LED board at Zone-I&II, PH-1&2 of Bishnupur Augmentation W/S Scheme under South 24-Pgs Mechanical Division PHE Dte.[Block-Sagar] |  |  | ORD/001790/2023-2024 | 1027/AE-I/SMD | 20/09/2023 | 05/10/2023 | M/S. GLOBAL POWER CONCERN | 0.82 | 0.82 | 100 | 100
21 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Zone-I & II PH No-2 of Bishnupur Augmentation W/S Scheme under JJM south 24 Pgs Mechanical Division PHE Dte [Block - Sagar] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/002306/2023-2024 | 907-AE-I-SMD | 11/08/2023 | 26/08/2023 | SIPRA ENTERPRISE | 0.9 | 0.9 | 99.44 | 100
22 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Improvement of outdoor illumination arrangement with allied works at Zone-I & II PH No-1 of Bishnupur Augmentation W/S Scheme under JJM south 24 Pgs Mechanical Division PHE Dte [Block - Sagar] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/002305/2023-2024 | 906-AE-I-SMD | 11/08/2023 | 26/08/2023 | SIPRA ENTERPRISE | 0.9 | 0.9 | 99.59 | 100
23 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000684/2023-2024 | 454/AD | 24/01/2024 | 24/01/2024 | Resource Division | 10.97 | 0 | 0 | 0
24 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED BISHNUPUR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : SAGAR, DISTRICT : SOUTH 24 PARGANAS | SM/13117 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000543/2023-2024 | 27/AD | 02/01/2024 | 02/01/2024 | Resource Division | 6.09 | 0 | 0 | 0
Total | [13 empty] | 1606.06 | 970.99 | 60.46