## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | RETROFITTING OF DISTRIBUTION SYSTEM OF ZONE-VI,DIAMOND HARBOUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION (JJM) & JAL SWAPNA UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHE | SM/13364 | Retrofitting | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VI of Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001051/2022-2023 | 301/DHSD | 15/09/2022 | 15/10/2022 | MEASURE LAND | 2.83 | 2.71 | 95.98 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | RETROFITTING OF DISTRIBUTION SYSTEM OF ZONE-VI,DIAMOND HARBOUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION (JJM) & JAL SWAPNA UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHE | SM/13364 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000345/2023-2024 | 3209/AD | 04/10/2023 | 04/10/2023 | Resource Division | 0.21 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | RETROFITTING OF DISTRIBUTION SYSTEM OF ZONE-VI,DIAMOND HARBOUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION (JJM) & JAL SWAPNA UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHE | SM/13364 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000893/2023-2024 | 747/AD | 03/02/2024 | 03/02/2024 | Resource Division | 20.38 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | RETROFITTING OF DISTRIBUTION SYSTEM OF ZONE-VI,DIAMOND HARBOUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION (JJM) & JAL SWAPNA UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHE | SM/13364 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000915/2023-2024 | 1257/AD | 02/03/2024 | 02/03/2024 | Resource Division | 0.62 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | RETROFITTING OF DISTRIBUTION SYSTEM OF ZONE-VI,DIAMOND HARBOUR-I BLOCK FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) TO ALL THE HOUSEHOLDS IN CONNECTION WITH JAL JEEVAN MISSION (JJM) & JAL SWAPNA UNDER MEGA SURFACE WATER BASED WATER SUPPLY SCHE | SM/13364 | Retrofitting | Additional balance works under the Augmentation scheme of Zone-VI at Diamond Harbour- I block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2 DHSD | ORD/000041/2025-2026 | 2031/AD | 29/04/2025 | 28/06/2025 | SADHURHAT CO OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 82 | 0 | 0 | 0
Total | [13 empty] | 106.03 | 2.71 | 2.56