## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2,3&4, Zone-I of Augmentation of Srinarayanpur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000359/2022-2023 | 3762/SMD | 29/12/2022 | 08/07/2025 | S.S. ENTERPRISES | 44.01 | 21.32 | 48.45 | 45
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Srinarayanpur (Part-III) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000780/2022-2023 | 6651/AD | 14/11/2022 | 29/12/2022 | MONDAL & CO. | 36.67 | 33.94 | 92.55 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Srinarayanpur (Part-I) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000779/2022-2023 | 6650/AD | 14/11/2022 | 29/12/2022 | M/S. DATTA ENTERPRISE | 36.67 | 33.69 | 91.87 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme [SRINARAYANPUR (PART I,II & III PWSS)] including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer, Kakdwip Sub Division |  | ORD/001041/2022-2023 | 32/AD | 04/04/2022 | 19/05/2022 | INDRANIL DUTTA & ASSOCIATES | 11.81 | 11.81 | 100 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Srinarayanpur (Part I, II & III) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001317/2022-2023 | 9882/AD | 10/01/2023 | 06/11/2023 | MAHMOOD ASSOCIATES PVT LTD | 326.43 | 72.62 | 22.25 | 25
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, construction of 02 nos. pump house, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Srinarayanpur (Part I, II & III) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-III) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001318/2022-2023 | 9883/AD | 10/01/2023 | 02/08/2025 | KAMIRUL SK AND CO. | 309.53 | 210.94 | 68.15 | 30
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, construction of 02 nos. pump house, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Srinarayanpur (Part I, II & III) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001746/2022-2023 | 11555/AD | 17/02/2023 | 14/12/2023 | SUPRITI ENTERPRISE | 309.39 | 86.63 | 28 | 30
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Srinarayanpur (Part-III) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000637/2023-2024 | 2465/AD | 24/08/2023 | 22/11/2023 | CHANCHAL ENTERPRISE & CO. | 78.12 | 58.38 | 74.72 | 40
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Srinarayanpur (Part-I, II, III) W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-III) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001213/2023-2024 | 3870/AD | 09/11/2023 | 24/12/2023 | KIRAN ENTERPRISES | 27.71 | 12.17 | 43.91 | 50
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Srinarayanpur (Part-I) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000636/2023-2024 | 2464/AD | 24/08/2023 | 23/10/2023 | ISHAN CONSTRUCTION | 35.53 | 34.29 | 96.5 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Srinarayanpur (Paer-I, II, II) W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001064/2023-2024 | 3382/AD | 11/10/2023 | 10/11/2023 | M/S MODINA ENTERPRISE | 9.49 | 9.47 | 99.69 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Srinarayanpur (Paer-I, II, II) W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001063/2023-2024 | 3381/AD | 11/10/2023 | 25/11/2023 | M/S SUNITY ENTERPRISE | 27.67 | 22.97 | 83.02 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Srinarayanpur (Part - I, II & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-III) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000966/2023-2024 | 289(I)/KSD | 18/07/2023 | 22/07/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Srinarayanpur (Part - I, II & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000944/2023-2024 | 282(I)/KSD | 13/07/2023 | 17/07/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
15 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Srinarayanpur (Part-I, II, III) W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-III) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001065/2023-2024 | 3383/AD | 11/10/2023 | 31/07/2025 | M/S. SONAMONI ENTERPRISE | 9.53 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Making and fixing of permanent display board at headwork site of Meherpur, Srinarayanpur (Part - I, II & II), Rajrajeswarpur, Ramganga PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002090/2023-2024 | 922/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.95 | 0 | 0 | 100
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of 300 cum. capacity OHR of Srinarayanpur (Part - I, II & III) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-III) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002234/2023-2024 | 720/KSD | 01/12/2023 | 11/12/2023 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0.48 | 100 | 100
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000461/2023-2024 | 4762/AD | 19/12/2023 | 19/12/2023 | Resource Division | 58.24 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000316/2023-2024 | 3125/AD | 29/09/2023 | 29/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
20 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/03523/2023-2024 | BP-2023-24-388 | 23/11/2023 | 23/11/2023 | WBSEDCL | 5.07 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04077/2023-2024 | BP-2023-24-425 | 18/12/2023 | 18/12/2023 | WBSEDCL | 8.46 | 0 | 0 | 0
22 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Srinarayanpur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13570) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000344/2024-2025 | 2756/AD | 27/06/2024 | 03/01/2027 | BIMALENDU GIRI | 116.4 | 0 | 0 | 0
23 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Srinarayanpur (Part-I) PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000547/2024-2025 | 3776/AD | 18/09/2024 | 17/11/2024 | MOSTAFIZUR HAQUE GAINE | 73.31 | 0 | 0 | 0
24 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Improvement of outdoor illumination arrangement with allied works at PH-3 of Srinarayanpur Aug W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/002922/2023-2024 | 294-AE-I-SMD | 15/01/2024 | 30/01/2024 | S.S. ENTERPRISES | 0.89 | 0 | 0 | 100
25 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Improvement of outdoor illumination arrangement with allied works at PH-4 of Srinarayanpur Aug W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/002923/2023-2024 | 293-AE-I-SMD | 15/01/2024 | 30/01/2024 | S.S. ENTERPRISES | 0.89 | 0 | 0 | 100
26 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000572/2023-2024 | 75/AD | 03/01/2024 | 03/01/2024 | Resource Division | 3.98 | 0 | 0 | 0
27 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000959/2023-2024 | 1693/AD | 22/03/2024 | 22/03/2024 | Resource Division | 29.77 | 0 | 0 | 0
28 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000742/2023-2024 | 577/AD | 29/01/2024 | 29/01/2024 | Resource Division | 2.84 | 0 | 0 | 0
29 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED SRINARAYANPUR (PART I,II & III) , PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13570 | Augmentation | Improvement of outdoor illumination arrangement with allied works at PH No-1 of Srinarayanpur Aug W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte.(SM/13570) | Assistant Engineer -II | Junior Engineer | ORD/002433/2024-2025 | 2087/AE-II/SMD | 12/03/2025 | 02/04/2025 | S.S. ENTERPRISES | 0.9 | 0 | 0 | 100
Total | [13 empty] | 1566.03 | 609.67 | 38.93