## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-II) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | SM/13575 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001898/2022-2023 | 5662/AD | 10/11/2022 | 25/12/2022 | INDRANIL DUTTA & ASSOCIATES | 0.39 | 0.39 | 100 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-II) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | SM/13575 | Augmentation | Laying of pipeline and other allied work of Augmentation of Moukhali-Kumarkhali (Zone-II) RO Plant to Model School (English Medium), Canning-II Tambuldaha GP Office, Bakultala Jr. High Madrasha etc under Moukhali-Kumarkhali W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000220/2023-2024 | 1025/AD | 13/06/2023 | 13/07/2023 | M/S. TAPAS MONDAL | 16.21 | 13.89 | 85.71 | 98
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-II) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | SM/13575 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000167/2023-2024 | 1120/AD | 22/06/2023 | 22/06/2023 | Resource Division | 0.76 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-II) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | SM/13575 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00629/2023-2024 | BP-2023-24-88 | 14/06/2023 | 14/06/2023 | WBSEDCL | 1.59 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-II) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | SM/13575 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00390/2023-2024 | BP-2023-24-53 | 09/06/2023 | 09/06/2023 | WBSEDCL | 4.75 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-II) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | SM/13575 | Augmentation | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Maukhali-Kumarkhali (Part - II) having village with maximum 124 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000785/2022-2023 | 6640/AD | 14/11/2022 | 13/01/2023 | D.N. ENTERPRISE | 47.22 | 21.61 | 45.76 | 60
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-II) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | SM/13575 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-II) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000587/2022-2023 | 644/SMD | 02/03/2023 | 31/03/2025 | SUDIP PRADHAN | 8.83 | 7.93 | 89.82 | 100
Total | [13 empty] | 79.76 | 43.82 | 54.94