## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-I) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | SM/13576 | Augmentation | 03 (three) nos. 40 mm dia. 375 mtr. deep Trial Bore by water jet method for Augmentation of Ground Water Based Mini Piped Water Supply Scheme for Moukhali-Kumarkhali (Zone - I to VI), under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001380/2022-2023 | 1062/CSD | 14/12/2022 | 23/01/2023 | M/S. M.K. NASKAR & CONSTRUCTION | 0.96 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-I) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | SM/13576 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001897/2022-2023 | 5661/AD | 10/11/2022 | 25/12/2022 | INDRANIL DUTTA & ASSOCIATES | 0.4 | 0.4 | 100 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-I) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | SM/13576 | Augmentation | Laying of pipe line at Moukhali High School and Moukhali Jr. High School (Girls) from Moukhali-Kumarkhali (Zone-I) R.O. Plant at Moukhali-Kumarkhali W/S Scheme (Zone-I), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000865/2022-2023 | 840/CSD | 12/08/2022 | 11/09/2022 | SUJIT KUMAR GHOSH | 3.43 | 2.56 | 74.61 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-I) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | SM/13576 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000166/2023-2024 | 1119/AD | 22/06/2023 | 22/06/2023 | Resource Division | 0.91 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-I) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | SM/13576 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/00382/2023-2024 | BP-2023-24-52 | 09/06/2023 | 09/06/2023 | WBSEDCL | 3.39 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-I) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | SM/13576 | Augmentation | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Maukhali-Kumarkhali (Part - I) having village with maximum 148 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000655/2022-2023 | 6677/AD | 14/11/2022 | 13/01/2023 | M/S P. B. CONSTRUCTION | 49.13 | 35.85 | 72.97 | 88
7 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-I) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | SM/13576 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, of Moukhali Kumarkhali (Part-I) Mini piped water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Canning-II] | Assistant Engineer | Junior Engineer | ORD/000586/2022-2023 | 643/SMD | 02/03/2023 | 31/05/2023 | SUDIP PRADHAN | 8.82 | 7.85 | 88.98 | 100
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEME FOR MAUKHALI KUMARKHALI (PART-I) UNDER ALIPORE DIVISION, PHE DTE, BLOCK: CANNING-II, DISTRICT : SOUTH 24 PARGANAS | SM/13576 | Augmentation | Surging of 02 (two) nos. 250mm x 150mm. dia. 360 mtr. Deep Tubewell at Moukhali-Kumarkhali W/S Scheme (Zone-I, TW-1) & (Zone-II, TW-1) under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001637/2023-2024 | 1048/CSD | 04/10/2023 | 03/11/2023 | ASHIM SHIL | 0.91 | 0.91 | 100 | 100
Total | [13 empty] | 67.95 | 47.57 | 70.01