## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF NARAYANTALA PIPED WATER SUPPLY SCHEME BLOCK BASANTI UNDER CANNING SUB DIVISION OF ALIPORE DIVISION PHE DTE. | SM/13756 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1, for Augmentation of Narayantala water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Basanti] | Assistant Engineer | Junior Engineer | ORD/000493/2022-2023 | 295/SMD | 03/02/2023 | 04/05/2023 | SRI KRISHNA NIRMAN | 11.18 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF NARAYANTALA PIPED WATER SUPPLY SCHEME BLOCK BASANTI UNDER CANNING SUB DIVISION OF ALIPORE DIVISION PHE DTE. | SM/13756 | Augmentation | Restoration of pipe line damaged due to flood like situation occurred by breaking of rivers embankment at Choradakatia under Narayantala W/S Scheme of Basanti Block under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001351/2020-2021 | 1259/CSD | 21/12/2020 | 20/01/2021 | SURYA ENTERPRISE | 4.8 | 4.73 | 98.62 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF NARAYANTALA PIPED WATER SUPPLY SCHEME BLOCK BASANTI UNDER CANNING SUB DIVISION OF ALIPORE DIVISION PHE DTE. | SM/13756 | Augmentation | Surging of 1no. Big dia Tubewell of Narayantala W/S Scheme under JJM, Block - Basanti under Canning Sub-Division under Alipore Division P.H.Engg. Dte. (TW-2) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000415/2023-2024 | 774/CSD | 02/08/2023 | 06/09/2023 | S.K.GOLUI | 2.17 | 2.15 | 99.33 | 99
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF NARAYANTALA PIPED WATER SUPPLY SCHEME BLOCK BASANTI UNDER CANNING SUB DIVISION OF ALIPORE DIVISION PHE DTE. | SM/13756 | Augmentation | Laying pipe line to connect the uncovered habitations and pipe protection work at Narayantala W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001029/2024-2025 | 4939/AD | 03/12/2024 | 01/02/2025 | DIPTI ENTERPRISE | 56.82 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF NARAYANTALA PIPED WATER SUPPLY SCHEME BLOCK BASANTI UNDER CANNING SUB DIVISION OF ALIPORE DIVISION PHE DTE. | SM/13756 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 538/AD | 25/01/2024 | 25/01/2024 | Resource Division | 40.34 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF NARAYANTALA PIPED WATER SUPPLY SCHEME BLOCK BASANTI UNDER CANNING SUB DIVISION OF ALIPORE DIVISION PHE DTE. | SM/13756 | Augmentation | Construction of OHR (200 cum.), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Augmentation Piped Water Supply Scheme for the Narayantala,Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001641/2022-2023 | 11378/AD | 13/02/2023 | 28/05/2026 | DIPTI ENTERPRISE | 319 | 84.19 | 26.39 | 48
Total | [13 empty] | 434.31 | 91.07 | 20.97