## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Kakdwip | S24 Pgns Mechanical | GROUND WATER BASED DAKSHIN KASIABAD PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, P.H.E. DTE. BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13797 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Dakshin Kasiabad water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/000434/2022-2023 | 3830/SMD | 29/12/2022 | 29/03/2023 | M/S. S.S. ENTERPRISE | 19.37 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED DAKSHIN KASIABAD PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, P.H.E. DTE. BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13797 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Kasiabad W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000951/2023-2024 | 2983/AD | 26/09/2023 | 26/10/2023 | M/S. PAPIYA ENTERPRISE | 9.47 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED DAKSHIN KASIABAD PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, P.H.E. DTE. BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13797 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Kasiabad W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000950/2023-2024 | 2982/AD | 26/09/2023 | 10/11/2023 | M/S. RABIN CON | 27.5 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED DAKSHIN KASIABAD PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, P.H.E. DTE. BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13797 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( DAKSHIN KASIABAD PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001048/2022-2023 | 3676/AD | 01/08/2022 | 15/09/2022 | LEMNISCATE | 3.86 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED DAKSHIN KASIABAD PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, P.H.E. DTE. BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13797 | New | Material Requisition To Resource Division |  |  | RTOR000447/2023-2024 | 4713/AD | 18/12/2023 | 18/12/2023 | Resource Division | 14.1 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED DAKSHIN KASIABAD PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, P.H.E. DTE. BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13797 | New | Making and fixing of permanent display board at headwork site of Harendranagar, Ramgopalpur, Uttar Kashiabad, Dakshin Kashiabad, Thangara, Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002140/2023-2024 | 940/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.94 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED DAKSHIN KASIABAD PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, P.H.E. DTE. BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13797 | New | Material Requisition To Resource Division |  |  | RTOR000588/2023-2024 | 87/AD | 03/01/2024 | 03/01/2024 | Resource Division | 9.3 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Kakdwip | Alipore Division | GROUND WATER BASED DAKSHIN KASIABAD PIPED WATER SUPPLY SCHEME, UNDER ALIPORE DIVISION, P.H.E. DTE. BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13797 | New | Construction of 300 cum. (2 nos.), 250 cum. (1 no.), 200 cum. (02 nos.) and 150 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 12 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Kashiabad, Dakshin Kashiabad, Manmathapur, Ramgopalpur, Mrinalnagar and Bhubannagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No of FHTC= 12945] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/000052/2023-2024 | 122/AD | 13/04/2023 | 01/04/2025 | GARGO TRADERS | 2798.35 | 0 | 0 | 64
Total | [13 empty] | 2882.89 | 0 | 0