## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1,2&3, of Indrapur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000364/2022-2023 | 3768/SMD | 29/12/2022 | 08/08/2025 | UNIVERSAL ENTERPRISES | 28.75 | 10.73 | 37.32 | 85
2 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (INDRAPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer, Kakdwip Sub Division |  | ORD/001038/2022-2023 | 3672/AD | 01/08/2022 | 15/09/2022 | INDRANIL DUTTA & ASSOCIATES | 6.37 | 6.37 | 100 | 100
3 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along 03 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Indrapur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1882] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000089/2023-2024 | 500/AD | 11/05/2023 | 11/09/2026 | UNITED BUILDERS | 547.12 | 404.37 | 73.91 | 97
4 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Sinking of 03 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st, 2nd and 3rd Tubewell Site of Indrapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001270/2022-2023 | 9582/AD | 03/01/2023 | 04/03/2023 | M/S. BOSE CONCERN | 73.43 | 71.19 | 96.95 | 100
5 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Making and fixing of permanent display board at headwork site of Satyadaspur, Indrapur, Dakshin Surendraganj, Uttar Surendraganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002109/2023-2024 | 930/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.81 | 0.2 | 24.97 | 100
6 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of 200 cum. capacity OHR of Indrapur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002064/2023-2024 | 758/KSD | 08/12/2023 | 13/12/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
7 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 548/AD | 12/05/2023 | 12/05/2023 | Resource Division | 10.34 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Material Requisition To Resource Division |  |  | RTOR000298/2023-2024 | 3093/AD | 28/09/2023 | 28/09/2023 | Resource Division | 24.37 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04080/2023-2024 | BP-2023-24-420 | 16/12/2023 | 16/12/2023 | WBSEDCL | 3.93 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Indrapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002042/2023-2024 | 524/AD | 25/01/2024 | 24/02/2024 | M/S. ASIRUDDIN SEKH ENTERPRISE | 11.8 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Indrapur PWSS, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13798) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000328/2024-2025 | 2730/AD | 25/06/2024 | 22/04/2025 | UNITED BUILDERS | 123.7 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Indrapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002041/2023-2024 | 523/AD | 25/01/2024 | 02/02/2025 | SK SAKIL AHAMED | 33.48 | 18.43 | 55.07 | 100
13 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Indrapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002043/2023-2024 | 525/AD | 25/01/2024 | 24/02/2024 | SIMRAN ENTERPRISE | 11.82 | 10.61 | 89.79 | 100
14 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Additional Work related to Supply & delivery of Submersible pumping machinery along with allied accessories at PH-2 of Indrapur W/S Schemes under South 24-Pgs Mechanical Division, PHE Dte. [Block-Pathar Pratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/001900/2023-2024 | 1185/SMD | 22/03/2024 | 12/04/2024 | UNIVERSAL ENTERPRISES | 10.63 | 9.93 | 93.44 | 100
15 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Improvement of outdoor illumination arrangement with allied works at PH-1 of Indrapur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] [SM/13798] | Assistant Engineer -II | Junior Engineer | ORD/001886/2024-2025 | 1019-AE-II-SMD | 09/08/2024 | 24/08/2024 | SARVATAH PROJECTS PRIVATE LIMITED | 0.83 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Material Requisition To Resource Division |  |  | RTOR000744/2023-2024 | 579/AD | 29/01/2024 | 29/01/2024 | Resource Division | 1.85 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/04942/2023-2024 | BP-2023-24-567 | 11/03/2024 | 11/03/2024 | WBSEDCL | 9.91 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Improvement of outdoor illumination arrangement with allied works at PH No-3 of Indrapur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte.(SM/13798) | Assistant Engineer -II | Junior Engineer | ORD/001152/2025-2026 | 228/AE-II/SMD | 02/05/2025 | 23/05/2025 | SARVATAH PROJECTS PRIVATE LIMITED | 0.81 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | PROPOSED GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR INDRAPUR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13798 | New | Improvement of outdoor illumination arrangement with allied works at PH-2 of Indrapur W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. .(SM/13798) | Assistant Engineer -II | Junior Engineer | ORD/002339/2024-2025 | 3092-AE-II-SMD | 21/03/2025 | 05/04/2025 | SARVATAH PROJECTS PRIVATE LIMITED | 0.67 | 0 | 0 | 100
Total | [13 empty] | 901.11 | 532.32 | 59.07