## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13800 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (PURBA SRIPATINAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000984/2022-2023 | 3669/AD | 01/08/2022 | 15/09/2022 | INDRANIL DUTTA & ASSOCIATES | 4.43 | 4.43 | 100 | 100
2 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13800 | New | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 543/AD | 12/05/2023 | 12/05/2023 | Resource Division | 8.12 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13800 | New | Material Requisition To Resource Division |  |  | RTOR000302/2023-2024 | 3097/AD | 28/09/2023 | 28/09/2023 | Resource Division | 27.56 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13800 | New | Making and fixing of permanent display board at headwork site of Upendranagar, Purba Sripatinagar, Paschim Sripatinagar, Krishnadaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002108/2023-2024 | 929/KSD | 19/12/2023 | 24/12/2023 | ANANTA KUMAR GIRI | 0.81 | 0.2 | 24.99 | 100
5 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13800 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of 150 cum. capacity OHR of Purba Sripatinagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002067/2023-2024 | 763(A)/KSD | 08/12/2023 | 13/12/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
6 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13800 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Purba Sripatinagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002036/2023-2024 | 518/AD | 25/01/2024 | 10/03/2024 | KALPANA TRADERS | 33.32 | 30.59 | 91.83 | 100
7 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13800 | New | Continuation order for the work of Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Purba Sripatinagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002392/2023-2024 | 1231/AD | 29/02/2024 | 14/04/2024 | SARADA CONSTRUCTION | 49.18 | 44.87 | 91.24 | 100
8 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13800 | New | Material Requisition To Resource Division |  |  | RTOR000677/2023-2024 | 443/AD | 24/01/2024 | 24/01/2024 | Resource Division | 0.57 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13800 | New | Payment for New Service connection of Purba Sripatinagar W/S Scheme PH-2 Application No:- 1007193436 Reference ID:- 106229306 |  |  | BILL/00965/2024-2025 | BP-2024-25-190 | 23/07/2024 | 23/07/2024 | WBSEDCL | 3.36 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13800 | New | Payment for New Service connection of Purba Sripatinagar W/S Scheme PH-1 Application No:- 1007193430 Reference ID:- 106229304 |  |  | BILL/00964/2024-2025 | BP-2024-25-189 | 23/07/2024 | 23/07/2024 | WBSEDCL | 3.63 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13800 | New | Supply & fixing of main swtch & Bus bar with allied works at PH-1 & 2 of Purba Sripatinagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Sagar] | Assistant Engineer -II | Junior Engineer | ORD/002451/2024-2025 | 1248/A-AE-II-SMD | 30/09/2024 | 15/10/2024 | PS & ASSOCIATES | 0 | 0 | NAN | 0
12 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13800 | New | Supply & fixing of main swtch & Bus bar with allied works at PH-1 & 2 of Purba Sripatinagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Sagar] | Assistant Engineer -II | Junior Engineer | ORD/002486/2024-2025 | 1248/A/AE-II/SMD | 30/09/2024 | 15/10/2024 | PS & ASSOCIATES | 0.69 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13800 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Purba Sripatinagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000366/2022-2023 | 3770/SMD | 29/12/2022 | 30/04/2025 | M/S. PS & ASSOCIATES | 19.27 | 10.74 | 55.75 | 90
14 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13800 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Purba Sripatinagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002037/2023-2024 | 519/AD | 25/01/2024 | 22/12/2024 | B.P.R. CONSTRUCTION | 11.6 | 0 | 0 | 100
15 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13800 | New | Improvement of outdoor illumination arrangement with allied works at PH-2 of Purba Sripatinagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] [SM/13800] | Assistant Engineer -II | Junior Engineer | ORD/001747/2024-2025 | 1185-AE-II-SMD | 19/09/2024 | 04/10/2024 | PS & ASSOCIATES | 0.83 | 0 | 0 | 100
16 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13800 | New | Improvement of outdoor illumination arrangement with allied works at PH-1 of Purba Sripatinagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] [SM/13800] | Assistant Engineer -II | Junior Engineer | ORD/001748/2024-2025 | 1290/A-AE-II-SMD | 23/10/2024 | 07/11/2024 | PS & ASSOCIATES | 0.83 | 0 | 0 | 100
17 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PURBA SRIPATINAGAR, UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13800 | New | Construction of 150 cum. (3 nos.), 200 cum. (2 nos.), 250 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 10 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Choto Banashyamnagar, Sibnagar, Gangapur, Purba Sripatinagar, Paschim Sripatinagar, Uttar Surendraganj Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 9779] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000024/2023-2024 | 123/AD | 13/04/2023 | 26/01/2026 | M/S. S.S. ENTERPRISE | 2760.12 | 368.07 | 13.34 | 66
Total | [13 empty] | 2924.8 | 459.4 | 15.71