## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Buraburir Tat water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I | Junior Engineer | ORD/000360/2022-2023 | 3763/SMD | 29/12/2022 | 29/03/2023 | BIJAN ENTERPRISE | 21.42 | 0 | 0 | 0
2 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Buraburir Tat W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001061/2023-2024 | 3379/AD | 11/10/2023 | 25/11/2023 | SUDIP PRADHAN | 33.31 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Buraburir Tat W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001062/2023-2024 | 3380/AD | 11/10/2023 | 10/11/2023 | M/S BHUNIA ENTERPRISE | 11.77 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (BURABURIR TAT PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer, Kakdwip Sub Division |  | ORD/001035/2022-2023 | 3665/AD | 01/08/2022 | 15/09/2022 | INDRANIL DUTTA & ASSOCIATES | 5.89 | 5.89 | 100 | 100
5 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.08.2022 to 31.01.2023 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001090/2022-2023 | 321/KSD | 26/07/2022 | 26/01/2023 | PIKASU BOSE | 2.4 | 2.19 | 91.23 | 95
6 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Hiring of Diesel Car / Luxury Taxi for supervision of works of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.08.2022 to 31.01.2023. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001091/2022-2023 | 322/KSD | 26/07/2022 | 26/01/2023 | BADSHA ALOM | 2.4 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Material Requisition To Resource Division |  |  | RTOR000301/2023-2024 | 3096/AD | 28/09/2023 | 28/09/2023 | Resource Division | 20.07 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Laboratory Maintenance of Kakdwip Sub - District Water Testing Laboratory under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte.(Period from 08.09.2022 to 07.09.2023) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/001093/2022-2023 | 399/KSD | 05/09/2022 | 05/09/2023 | ANANTA KUMAR GIRI | 0.69 | 0 | 0 | 100
9 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Pathar Pratima Block under Kakdwip Sub - Division of Alipore Division, PHE Dte. for the period from 03.12.2022 to 30.11.2023 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001085/2022-2023 | 563/KSD | 02/12/2022 | 30/11/2023 | RUPAK DAS MAHAPATRA | 4.8 | 0 | 0 | 20
10 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Hiring of Motor Launch for Kakdwip Sub Division under Alipore Division, P.H.E. Dte. in connection with execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas (Period from 01.12.2022 to 30.11.2023) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001092/2022-2023 | 537/KSD | 23/11/2022 | 23/11/2023 | RAJKUMAR MANNA | 4.36 | 1.45 | 33.15 | 20
11 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.08.2023 to 31.01.2024 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001044/2023-2024 | 326/KSD | 31/07/2023 | 31/01/2024 | PIKASU BOSE | 2.4 | 2.25 | 93.74 | 100
12 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.08.2023 to 31.01.2024. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001042/2023-2024 | 325/KSD | 31/07/2023 | 31/01/2024 | BADSHA ALOM | 2.4 | 0 | 0 | 30
13 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Buraburirtat PWSS, Mouza - Sitarampur, Burabuirtat, Gobardhanpur; Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13801) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000342/2024-2025 | 2754/AD | 27/06/2024 | 25/09/2024 | GROWING CONCERN | 99.12 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Continuation order for Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.02.2024 to 31.07.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_3, Kakdwip Sub Division | ORD/003030/2023-2024 | 259(A)/KSD | 31/01/2024 | 02/08/2024 | M/S KHAJABABA ENTERPRISE | 2.4 | 1.88 | 78.47 | 0
15 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Continuation order for Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.02.2024 to 31.07.2024 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002532/2023-2024 | 260/KSD | 31/01/2024 | 31/07/2024 | PIKASU BOSE | 2.4 | 2.29 | 95.29 | 0
16 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Pathar Pratima Block under Kakdwip Sub - Division of Alipore Division, PHE Dte. for the period from 01.12.2023 to 29.02.2024 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002531/2023-2024 | 711/KSD | 30/11/2023 | 29/02/2024 | RUPAK DAS MAHAPATRA | 1.2 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Continuation order for Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.08.2023 to 31.01.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002948/2023-2024 | 325(A)/KSD | 31/07/2023 | 31/01/2024 | M/S KHAJABABA ENTERPRISE | 2.4 | 1.05 | 43.77 | 0
18 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Laying pipe line for Buraburir Tat Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000617/2023-2024 | 2315/AD | 17/08/2023 | 16/10/2023 | GROWING CONCERN | 131.1 | 114.38 | 87.25 | 10
19 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Supplying, fitting, fixing and delivery of different dia. specials for Buraburirtat W/S Scheme under JJM, Block- Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000721/2023-2024 | 2538/AD | 28/08/2023 | 27/09/2023 | ANANTA KUMAR GIRI | 5.32 | 3.26 | 61.32 | 100
20 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Making and fixing of permanent display board at headwork site of Buraburir Tat, Sitarampur, Rakhaskhali, Gobindapur Abad PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002111/2023-2024 | 931/KSD | 19/12/2023 | 24/12/2023 | M/S B. ENTERPRISE | 0.81 | 0.4 | 49.96 | 100
21 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Providing support services for data mapping of available data within command area for preparation of GMIS of Buraburir Tat W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001995/2023-2024 | 468/KSD | 22/09/2023 | 22/10/2023 | M/S R.DUTTA & CO. | 4.34 | 4.33 | 99.72 | 100
22 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Buraburir Tat W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001280/2022-2023 | 9592/AD | 03/01/2023 | 17/02/2023 | M/S. BOSE CONCERN | 48.69 | 46.68 | 95.87 | 100
23 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Material Requisition To Resource Division |  |  | RTOR000678/2023-2024 | 444/AD | 24/01/2024 | 24/01/2024 | Resource Division | 6.75 | 0 | 0 | 0
24 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Material Requisition To Resource Division |  |  | RTOR000769/2023-2024 | 603/AD | 29/01/2024 | 29/01/2024 | Resource Division | 9.54 | 0 | 0 | 0
25 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Payment for New Service connection Bura burir Tat PH-1 W/S Scheme Application No:- 1007911206 Reference ID: 106659346 |  |  | BILL/01132/2024-2025 | BP-2024-25-229 | 08/08/2024 | 08/08/2024 | WBSEDCL | 6.68 | 0 | 0 | 0
26 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Fuel charges bill for M.V Sidheswari for the month of Dec'22 to March'23. |  |  | BILL/03229/2023-2024 | BP-2023-24-1215 | 20/03/2024 | 20/03/2024 | RAJKUMAR MANNA | 13.72 | 0 | 0 | 0
27 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Payment for New Service connection of Bura burir Tat W/S Scheme PH-2 Application No:- 1007954078 Reference ID:- 106682238 |  |  | BILL/01131/2024-2025 | BP-2024-25-228 | 08/08/2024 | 08/08/2024 | WBSEDCL | 1.14 | 0 | 0 | 0
28 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Laying Rising Main and construction of 02 nos. Pump House for providing FHTC for Buraburir Tat Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001423/2023-2024 | 4602/AD | 14/12/2023 | 08/02/2025 | BISWAJIT SAMANTA | 21.27 | 0 | 0 | 100
29 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Continuation order for Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.08.2024 to 31.01.2025 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000671/2024-2025 | 1177/KSD | 26/07/2024 | 26/01/2025 | PIKASU BOSE | 2.4 | 2.23 | 92.84 | 0
30 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying D.I. Pipe Line including design & drawing of foundation after soil investigation for Buraburirtat Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13801) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000644/2024-2025 | 4147/AD | 05/10/2024 | 02/07/2025 | GROWING CONCERN | 147.24 | 0 | 0 | 18
31 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Continuation order for Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.08.2024 to 31.01.2025. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_3, Kakdwip Sub Division | ORD/000664/2024-2025 | 1176/KSD | 26/07/2024 | 26/01/2025 | M/S KHAJABABA ENTERPRISE | 2.4 | 1.93 | 80.43 | 0
32 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Piprakhali PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11846) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000189/2024-2025 | 924/AD | 05/03/2025 | 04/05/2025 | M/S PARAMESWAR CHOWDHURY | 55.38 | 0 | 0 | 0
33 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Continuation order for Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.02.2025 to 31.07.2025 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002958/2024-2025 | 227/KSD | 28/01/2025 | 28/07/2025 | PIKASU BOSE | 2.4 | 1.12 | 46.67 | 0
34 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile and pile cap for OHR etc. at Ramdebpur W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002590/2024-2025 | 922/AD | 05/03/2025 | 04/05/2025 | CHANDAN ROY | 60.06 | 0 | 0 | 0
35 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Continuation order for Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.02.2025 to 31.07.2025 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/002898/2024-2025 | 204/KSD | 24/01/2025 | 24/07/2025 | M/S KHAJABABA ENTERPRISE | 2.4 | 0 | 0 | 0
36 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Continuation order for Hiring of Motor Launch for Kakdwip Sub Division under Alipore Division, P.H.E. Dte. in connection with execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas (Period from 01.12.2023 to 30.11.2024) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/003143/2023-2024 | 684/KSD | 24/11/2023 | 24/11/2024 | RAJKUMAR MANNA | 4.36 | 0 | 0 | 80
37 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BURABURIR TAT , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13801 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Buraburirtat PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (SM/13801) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002990/2024-2025 | 1458/KSD | 06/11/2024 | 16/11/2024 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0 | 100
Total | [13 empty] | 745.91 | 191.32 | 25.65