## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Providing Functional Household Tap Connection (FHTC) to all the households in Srinagar Water Supply Scheme, Block - Kakdwip South 24 Pgs. District under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000497/2020-2021 | 5312/AD | 18/02/2021 | 18/02/2022 | MONDAL PRECISION PRIVATE LIMITED | 105.31 | 0 | 0 | 90
2 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, for Augmentation of Srinagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I | Junior Engineer | ORD/000436/2022-2023 | 3832/SMD | 29/12/2022 | 29/03/2023 | KARTICK BAL | 21.78 | 0 | 0 | 0
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (SRINAGAR (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001061/2022-2023 | 4650/AD | 06/09/2022 | 21/10/2022 | LEMNISCATE | 6.13 | 0 | 0 | 100
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Srinagar (Zone-I & II) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000909/2023-2024 | 268(I)/KSD | 10/07/2023 | 14/07/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0 | 100
5 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000465/2023-2024 | 4725/AD | 18/12/2023 | 18/12/2023 | Resource Division | 24.69 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000274/2023-2024 | 3073/AD | 28/09/2023 | 28/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Srinagar Zone - I & II Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000427/2023-2024 | 1915/AD | 01/08/2023 | 31/08/2023 | M/S.SREEJIT ENTERPRISE | 11.8 | 0 | 0 | 60
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Sinking of 01 no. 100mm x 50mm dia. having 4 nos. Strainer upto 360 mtr (Average) depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying PVC Pipe for providing FHTC at Augmentation of Srinagar Zone-I & II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub - Division of Alipore Division, P.H.E.D. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002568/2023-2024 | 512/KSD | 15/03/2024 | 25/03/2024 | MAA LAXMI ENTERPRISE | 2.8 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Srinagar (Zone - I & II) W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000212/2024-2025 | 2595/AD | 19/06/2024 | 03/08/2024 | KHOKAN MONDAL | 28.76 | 0 | 0 | 0
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, Pile and Pile Cap for OHR etc at Sri Nagar PWSS, Block -Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13811) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000378/2024-2025 | 3044/AD | 24/07/2024 | 22/09/2024 | MAA LAXMI ENTERPRISE | 120.33 | 0 | 0 | 0
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Srinagar (Zone-I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001775/2022-2023 | 12057/AD | 27/02/2023 | 13/04/2023 | M/S MAITY CONSTRUCTION | 38.52 | 0 | 0 | 100
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Making and fixing of permanent display board at headwork site of Hardwood Point, Ganeshpur Kalinagar Zone - I & II, Kashinagar, Srinagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002145/2023-2024 | 945/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.94 | 0 | 0 | 100
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000594/2023-2024 | 93/AD | 03/01/2024 | 03/01/2024 | Resource Division | 0.83 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000812/2023-2024 | 657/AD | 30/01/2024 | 30/01/2024 | Resource Division | 12.8 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Payment for New Service connection Srinagar Aug W/S Scheme PH-2 Application No:- 1007169511 Reference ID: 106214476 |  |  | BILL/02226/2024-2025 | BP-2024-25-508 | 19/12/2024 | 19/12/2024 | WBSEDCL | 7.34 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Payment for New Service connection Srinagar Aug W/S Scheme PH-1 Application No:- 1007169503 Reference ID: 106214464 |  |  | BILL/02225/2024-2025 | BP-2024-25-507 | 19/12/2024 | 19/12/2024 | WBSEDCL | 3.95 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Augmentation of Srinagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 70] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001865/2022-2023 | 12418/AD | 09/03/2023 | 01/01/2026 | MAA LAXMI ENTERPRISE | 276.43 | 0 | 0 | 90
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Srinagar (Zone - I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-C) [No. of FHTC = 70] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002031/2022-2023 | 12998/AD | 23/03/2023 | 30/06/2025 | PREMANANDA ROY BISWAS | 179.16 | 0 | 0 | 100
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Srinagar Zone - I & II Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000426/2023-2024 | 1914/AD | 01/08/2023 | 31/08/2023 | HYDROTECH ASSOCIATES | 12.04 | 0 | 0 | 90
20 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Repairing of 1 no. Pump House & Boundary Wall at 1st Tubewell site for Srinagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13811) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002156/2024-2025 | 1984/KSD | 23/12/2024 | 17/01/2025 | LASKAR ENTERPRISE | 2 | 0 | 0 | 100
21 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED SRINAGAR (ZONE - I & II), PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13811 | Augmentation | Repairing of 1 no. Pump House & boundary wall at 2nd Tubewell site for Srinagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13811) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002157/2024-2025 | 1985/KSD | 23/12/2024 | 17/01/2025 | M/S IDEAL WORKS | 2 | 0 | 0 | 0
Total | [13 empty] | 858.39 | 0 | 0