## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (CHANDIPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001055/2022-2023 | 4145/AD | 19/08/2022 | 03/10/2022 | LEMNISCATE | 4.22 | 4.22 | 100 | 100
2 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Chandipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division | ORD/001774/2022-2023 | 12047/AD | 27/02/2023 | 29/03/2023 | M/S MAITY CONSTRUCTION | 19.26 | 17.65 | 91.61 | 100
3 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000466/2023-2024 | 4726/AD | 18/12/2023 | 18/12/2023 | Resource Division | 38.66 | 0 | 0 | 0
4 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000271/2023-2024 | 3070/AD | 28/09/2023 | 28/09/2023 | Resource Division | 0.3 | 0 | 0 | 0
5 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Payment of electricity bill for new service connection under SMD, PHE Dte. |  |  | BILL/01066/2023-2024 | BP-2023-24-147 | 24/07/2023 | 24/07/2023 | WBSEDCL | 3.59 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/000399/2023-2024 | 1874/AD | 01/08/2023 | 15/09/2023 | C.S. CONSTRUCTION | 11.18 | 0 | 0 | 100
7 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-G) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001032/2023-2024 | 3316/AD | 07/10/2023 | 21/11/2023 | JHARNA ENTERPRISE | 30.86 | 24.04 | 77.91 | 80
8 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/000398/2023-2024 | 1873/AD | 01/08/2023 | 15/09/2023 | M/S SUNITY ENTERPRISE | 11.53 | 0 | 0 | 70
9 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Making and fixing of permanent display board at headwork site of Taktipur Abad Zone - I & II, Chandipur, Bamanagar, Gangadharpur Zone - I &II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002141/2023-2024 | 941/KSD | 19/12/2023 | 24/12/2023 | BIMALENDU GIRI | 0.94 | 0.16 | 16.66 | 100
10 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Chandipur W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13812) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000217/2024-2025 | 2600/AD | 19/06/2024 | 19/07/2024 | LASKAR ENTERPRISE | 9.1 | 6.59 | 72.46 | 100
11 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000595/2023-2024 | 94/AD | 03/01/2024 | 03/01/2024 | Resource Division | 1.19 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Material Requisition To Resource Division |  |  | RTOR001000/2023-2024 | 1799/AD | 27/03/2024 | 27/03/2024 | Resource Division | 25.73 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000813/2023-2024 | 658/AD | 30/01/2024 | 30/01/2024 | Resource Division | 9.62 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | PAYMENT OF ELECTRICITY BILL FOR NEW SERVICE CONNECTION UNDER SMD PHE DTE. |  |  | BILL/05389/2023-2024 | BP-2023-24-599 | 28/03/2024 | 28/03/2024 | WBSEDCL | 3.12 | 0 | 0 | 0
15 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1 for Augmentation of Chandipur water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Kakdwip] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000435/2022-2023 | 3831/SMD | 29/12/2022 | 01/05/2025 | SEN ENTERPRISE | 11.11 | 10.17 | 91.59 | 90
16 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/000400/2023-2024 | 1899/AD | 01/08/2023 | 15/09/2023 | M/S. BRINDABAN DAS & SONS | 10.77 | 2.57 | 23.9 | 70
17 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-F) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/000401/2023-2024 | 1900/AD | 01/08/2023 | 01/04/2025 | DEV AND COMPANY | 9.51 | 0 | 0 | 40
18 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-E) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_4, Kakdwip Sub Division | ORD/001031/2023-2024 | 3315/AD | 07/10/2023 | 21/11/2023 | SARKAR ENTERPRISE | 10 | 8.51 | 85.07 | 60
19 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connection etc. for Augmentation of Chandipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13812) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000662/2024-2025 | 4211/AD | 23/10/2024 | 29/05/2025 | SARADA CONSTRUCTION | 92.01 | 0 | 0 | 61
20 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Inter connection between two nos. Tubewell for Madhusudanpur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18126) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002548/2024-2025 | 817/AD | 27/02/2025 | 13/04/2025 | PAUL CONSTRUCTION | 13.31 | 0 | 0 | 0
21 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Ganeshpur Kalinagar (Zone-I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) (SM/10336) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002555/2024-2025 | 819/AD | 27/02/2025 | 13/04/2025 | M/S. GANGA ENTERPRISE | 9.54 | 0 | 0 | 0
22 | SOUTH 24 PARGANAS |  | Alipore Division | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. At 3rd Tubewell Site for Augmentation of Ganeshpur Kalinagar Zone-I & II Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (SM/10336) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000011/2025-2026 | 1702/AD | 08/04/2025 | 23/05/2025 | PRANABANANDA CONSTRUCTION | 5.43 | 0 | 0 | 0
23 | SOUTH 24 PARGANAS |  | S24 Pgns Mechanical | AUGMENTATION OF GROUND WATER BASED CHANDIPUR, PIPE WATER SUPPLY SCHEME Phase-B, UNDER ALIPORE DIVISION, BLOCK : KAKDWIP, DISTRICT : SOUTH 24 PARGANAS | SM/13812 | Augmentation | Improvement of outdoor illumination arrangement with allied works at PH-1 of Chandipur Aug W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Kakdwip] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000582/2024-2025 | 632-AE-I-SMD | 23/04/2024 | 08/05/2024 | SEN ENTERPRISE | 0.89 | 0 | 0 | 100
Total | [13 empty] | 331.88 | 73.91 | 22.27