## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (UPENDRANAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer, Kakdwip Sub Division |  | ORD/001036/2022-2023 | 3670/AD | 01/08/2022 | 15/09/2022 | INDRANIL DUTTA & ASSOCIATES | 6.24 | 6.24 | 100 | 100
2 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 02 nos, Pump House for Upendranagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 500] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001542/2022-2023 | 11027/AD | 08/02/2023 | 09/05/2023 | SARADA CONSTRUCTION | 173.65 | 116.69 | 67.2 | 25
3 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Upendranagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 150] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001505/2022-2023 | 10991/AD | 07/02/2023 | 21/02/2026 | SARADA CONSTRUCTION | 174.6 | 72.43 | 41.48 | 80
4 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Upendranagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 1084] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002063/2022-2023 | 13005/AD | 23/03/2023 | 21/06/2023 | SARADA CONSTRUCTION | 163.54 | 136.61 | 83.53 | 50
5 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Upendranagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002083/2022-2023 | 13256/AD | 31/03/2023 | 15/05/2023 | PRADIP KUMAR JATI | 46.55 | 0 | 0 | 0
6 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Supply, installation and commissioning of submersible pumping machinery along with allied accessories at P.H. 1&2, of Upendranagar water supply scheme under South 24 Pgs. Mechanical Division, PHE Dte. [Block: Patharpratima] | Assistant Engineer -I,Assistant Engineer -II | Junior Engineer | ORD/000798/2022-2023 | 332/SMD | 07/02/2023 | 20/11/2027 | TRIDENT ENTERPRISE | 21.95 | 0 | 0 | 80
7 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Upendranagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000978/2023-2024 | 2997/AD | 26/09/2023 | 26/10/2023 | M/S KHAJABABA ENTERPRISE | 11.7 | 0 | 0 | 0
8 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Upendranagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000977/2023-2024 | 2996/AD | 26/09/2023 | 10/11/2023 | DEBASIS JANA | 33.33 | 0 | 0 | 0
9 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Upendranagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000963/2023-2024 | 286(I)/KSD | 18/07/2023 | 22/07/2023 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0.49 | 100 | 100
10 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Making and fixing of permanent display board at headwork site of Upendranagar, Purba Sripatinagar, Paschim Sripatinagar, Krishnadaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002108/2023-2024 | 929/KSD | 19/12/2023 | 24/12/2023 | ANANTA KUMAR GIRI | 0.81 | 0.2 | 24.99 | 100
11 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 536/AD | 12/05/2023 | 12/05/2023 | Resource Division | 9.53 | 0 | 0 | 0
12 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Material Requisition To Resource Division |  |  | RTOR000519/2023-2024 | 4939/AD | 22/12/2023 | 22/12/2023 | Resource Division | 19.36 | 0 | 0 | 0
13 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile & pile cap for OHR etc at Upendranagar PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13828) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000663/2024-2025 | 4212/AD | 23/10/2024 | 22/12/2024 | SARADA CONSTRUCTION | 135.89 | 0 | 0 | 0
14 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Upendranagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000121/2024-2025 | 2399/AD | 07/06/2024 | 22/07/2024 | SARADA CONSTRUCTION | 50.92 | 47.1 | 92.49 | 100
15 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Material Requisition To Resource Division |  |  | RTOR000584/2023-2024 | 58/AD | 03/01/2024 | 03/01/2024 | Resource Division | 1.65 | 0 | 0 | 0
16 | SOUTH 24 PARGANAS | Patharpratima | Alipore Division | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Material Requisition To Resource Division |  |  | RTOR000948/2023-2024 | 1682/AD | 22/03/2024 | 22/03/2024 | Resource Division | 1.98 | 0 | 0 | 0
17 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Payment for New Service connection Upendranagar PH-1 W/S Scheme Application No:- 1007199920 Reference ID: 106233519 |  |  | BILL/01206/2024-2025 | BP-2024-25-260 | 12/08/2024 | 12/08/2024 | WBSEDCL | 3.99 | 0 | 0 | 0
18 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Payment for New Service connection Upendranagar PH-2 W/S Scheme Application No:- 1007199954 Reference ID: 106233535 |  |  | BILL/01205/2024-2025 | BP-2024-25-259 | 12/08/2024 | 12/08/2024 | WBSEDCL | 6.05 | 0 | 0 | 0
19 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Improvement of outdoor illumination arrangement with allied works at PH-1 of Upendranagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] (SM/13828) | Assistant Engineer -II | Junior Engineer | ORD/002336/2024-2025 | 1821-AE-II-SMD | 28/01/2025 | 12/02/2025 | TRIDENT ENTERPRISE | 0.9 | 0 | 0 | 100
20 | SOUTH 24 PARGANAS | Patharpratima | S24 Pgns Mechanical | GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR UPENDRANAGAR , UNDER ALIPORE DIVISION, BLOCK : PATHARPRATIMA, DISTRICT : SOUTH 24 PARGANAS | SM/13828 | New | Improvement of outdoor illumination arrangement with allied works at PH-2 of Upendranagar W/S Scheme under JJM under South 24-Pgs Mechanical Division,PHE Dte. [Block-Pathar Pratima] (SM/13828) | Assistant Engineer -II | Junior Engineer | ORD/002335/2024-2025 | 1822-AE-II-SMD | 28/01/2025 | 12/02/2025 | TRIDENT ENTERPRISE | 0.9 | 0 | 0 | 100
Total | [13 empty] | 864.02 | 379.76 | 43.95